## 1. Status Resumo
| Quadro Status: | [7 empty] | Highlights
|  | Com mapeamento | Com mapeamento - A avaliar | Fora de âmbito | Por iniciar |  |  | Sem mapeamento
| Templates | Status
|  | Recolha de Info. | Desenvolvimento | Validação | Concluído | Total | % de Progresso | % de Concluídos
AML.02.01 | AML.02.01 - Customers | 8 | 6 | 0 | 3 | 17 | 35% | 17.65%
AML.03.01 | AML.03.01 - Payment accounts | 5 | 0 | 0 | 0 | 5 | 40% | 0%
AML.03.02 | AML.03.02 - Virtual IBANs | 0 | 3 | 0 | 3 | 6 | 50% | 50%
AML.03.03 | AML.03.03 - Prepaid cards | 0 | 0 | 0 | 5 | 5 | 100% | 100%
AML.03.04 | AML.03.04 - Lending and Factoring | 5 | 8 | 0 | 0 | 13 | 15% | 0%
AML.03.05 | AML.03.05 - Life insurance contracts | 0 | 0 | 0 | 4 | 4 | 100% | 100%
AML.03.06 | AML.03.06 - Currency exchange (involving cash) | 0 | 6 | 0 | 1 | 7 | 45% | 14.29%
AML.04.01 | AML.04.01 - Investment services | 0 | 11 | 0 | 0 | 11 | 60% | 0%
AML.04.03 | AML.04.03 - Wealth management | 0 | 2 | 0 | 0 | 2 | 85% | 0%
AML.04.04 | AML.04.04 - Correspondence services | 2 | 0 | 0 | 4 | 6 | 66.67% | 66.67% |  | Status | Datapoints | %
AML.04.05 | AML.04.05 - Trade finance | 5 | 0 | 0 | 0 | 5 | 20% | 0% |  | Recolha de Info. | 35 | 27.78%
AML.04.06 | AML.04.06 - E-money | 0 | 0 | 5 | 0 | 5 | 90% | 0% |  | Desenvolvimento | 45 | 35.71%
AML.04.11 | AML.04.11 - Management of UCITS/AIFS | 0 | 0 | 0 | 9 | 9 | 100% | 100% |  | Validação | 11 | 8.73%
AML.04.12 | AML.04.12 - Safe custody services | 0 | 0 | 1 | 0 | 1 | 90% | 0% |  | Concluído | 35 | 27.78%
AML.04.14 | AML.04.14 - Cash transactions | 1 | 4 | 0 | 0 | 5 | 35% | 0% |  | Total | 126 | 100%
AML.05.01 | AML.05.01 - Geographies | 9 | 2 | 0 | 6 | 17 | 35% | 35.29%
AML.06.01 | AML.06.01 - Distribution channels | 0 | 0 | 5 | 0 | 5 | 90% | 90%
AML.07.06 | AML.07.06 - Target Financial Sanctions | 0 | 3 | 0 | 0 | 3 | 5% | 0%
F4. Fora âmbito ¦ Re-especificação de campos complexos - Dem. Fin. CIB | Total | 35 | 45 | 11 | 35 | 126 | 51.67% | 27.78%
Sumário Executivo
#124

## 2. Detalhe Data Points
Detalhe Data Points
O quadro infra apresenta o Gap Analysis realizado entre os reportes AMLA e RPB, incluido também tabelas e campos fontes utilizadas no reporte RPB.
| Reporte AMLA |  |  |  |  | Reporte RPB | [6 empty] | Owner | Status | Comentário
| Template | Section | Mapa | DataPoint | Descritivo | Template | Mapa | DataPoint | Tabela Fonte | Campo Fonte | Filtros Aplicados | Descritivo | (Área) | Campo | Neyond
| AML.02.01 | Customers | Customers | C0010 | Total number of customers |  | Risco inerente ao Cliente | 2.1 a) |  |  |  |  | Analítica (FCC) | Concluído | Confirmar se o universo do data point 2d) deve entrar aqui
| AML.02.01 | Customers | Customers | C0020 | Number of customers which are Natural Persons (NP) |  | Risco inerente ao Cliente | 2.1 b) |  |  |  |  | Analítica (FCC) | Concluído
| AML.02.01 | Customers | Customers | C0030 | Number of customers which are Legal Entities (LE) |  | Risco inerente ao Cliente | 2.1 c) |  |  |  |  | Analítica (FCC) | Concluído
| AML.02.01 | Customers | Customers | C0040 | Number of customers NP who are PEPs |  | Risco inerente ao Cliente | 2.5.1 a) + 2.5.2 a) |  |  |  |  | Analítica (FCC) | Desenvolvimento | A relação não é direta. Necessário aplicar os filtro do data point 2.1 b). Adicionalmente, assumo que beneficiários não devem entrar neste subset.
| AML.02.01 | Customers | Customers | C0050 | Number of customers LE whose BO are PEPs |  | Risco inerente ao Cliente | 2.5.1 b) + 2.5.2 d) |  |  |  |  | Analítica (FCC) | Desenvolvimento | A relação não é direta. Necessário aplicar os filtro do data point 2.1 c)
| AML.02.01 | Customers | Customers | C0060 | Number of customers with at least one transaction | [8 empty] | Recolha de Info. | Confirmar com Pedro Cadete abordagem
| AML.02.01 | Customers | Customers | C0070 | Number of new customers |  | 2.1 a) + filtros de new costumers do ponto 4.1 + 4.2 | [6 empty] | Recolha de Info. | Dúvida na data de referência e clientes com operações canceladas // Customers which became a new customer to the entity in the reference year. Customers who had temporary suspended their business relationship before/within the reference year and return as a customer in the reference year should be included.
| AML.02.01 | Customers | Customers | C0080 | New Customers - Remote Onboarding |  | Área de Negócio | Dúvida na data de referência e clientes com operações canceladas // Customers which became a new customer to the entity in the reference year. Customers who had temporary suspended their business relationship before/within the reference year and return as a customer in the reference year should be included. | [5 empty] | Recolha de Info.
| AML.02.01 | Customers | Customers | C0090 | New Customers - Third Party Onboarding |  | Área de Negócio | Dúvida na data de referência e clientes com operações canceladas // Customers which became a new customer to the entity in the reference year. Customers who had temporary suspended their business relationship before/within the reference year and return as a customer in the reference year should be included. | [5 empty] | Recolha de Info.
| AML.02.01 | Customers | Customers | C0100 | New Customers - Third Party Onboarding (Non-supervised) |  | Área de Negócio | Dúvida na data de referência e clientes com operações canceladas // Customers which became a new customer to the entity in the reference year. Customers who had temporary suspended their business relationship before/within the reference year and return as a customer in the reference year should be included. | [5 empty] | Recolha de Info.
| AML.02.01 | Customers | Customers | C0110 | Number of customers which are legal entities with complex corporate structure |  | Risco inerente ao Cliente | 2.6.6 |  |  |  |  | Analítica (FCC) | Recolha de Info. | Necessário confirmar critérios internos do Banco
| AML.02.01 | Customers | Customers | C0120 | Number of customers with high-risk activities |  | Risco inerente ao Cliente | 2.6.5 |  |  |  |  | Analítica (FCC) | Recolha de Info. | Confirmar critérios do ponto 2.6.5 - Falar com Eduardo Gonzalez
| AML.02.01 | Customers | Customers | C0130 | Number of legal entities with at least 1 Beneficial Owner located in non-EEA countries (residence) |  | Risco inerente ao Cliente | Identificação dos Beneficiários: 2.4.5 b) (non-EEA: Tudo o que não é EEA,Islândia, Noruega e Liechtenstein ) // Ver entidades associadas |  |  |  |  | Analítica (FCC) | Desenvolvimento | No RDP faz menção ao número de beneficiário, enquanto no AMLA penso que seja o número das entidades onde os beneficários pertencem.
| AML.02.01 | Customers | Customers | C0140 | Number of customers with cross border transactions involving non-EEA countries | [8 empty] | Desenvolvimento
| AML.02.01 | Customers | Customers | C0150 | Number of walk-in customers | [8 empty] | Desenvolvimento
| AML.02.01 | Customers | Customers | C0160 | Number of occasional transactions carried out by walk in customers | [8 empty] | Desenvolvimento
| AML.02.01 | Customers | Customers | C0170 | Number of customers with requests from FIU | [8 empty] | Recolha de Info.
| AML.03.01 | Products | Payment accounts | C0010 | Number of payment accounts |  | Risco inerente a produtos, serviços ou operações | 3.1.1 a) |  |  |  |  | Analítica (FCC) | Recolha de Info. | Email pendente de feedback sobre universo
| AML.03.01 | Products | Payment accounts | C0020 | Total Value (EUR) of incoming transactions |  | Risco inerente a produtos, serviços ou operações | 3.2.1 c) com nuance de entradas |  |  |  |  | Analítica (FCC) | Recolha de Info.
| AML.03.01 | Products | Payment accounts | C0030 | Number of incoming transactions | [7 empty] | Analítica (FCC) | Recolha de Info.
| AML.03.01 | Products | Payment accounts | C0040 | Total Value of outgoing transactions |  | Risco inerente a produtos, serviços ou operações | 3.2.1 c) com nuance de saidas |  |  |  |  | Analítica (FCC) | Recolha de Info.
| AML.03.01 | Products | Payment accounts | C0050 | Number of outgoing transactions | [7 empty] | Analítica (FCC) | Recolha de Info.
| AML.03.02 | Products | Virtual IBANs | C0010 | Total Number of master accounts with linked vIBANS | [7 empty] | Pagamentos (Pedro David) | Desenvolvimento
| AML.03.02 | Products | Virtual IBANs | C0020 | Number of transactions on Virtual IBANs (incoming) | [7 empty] | Pagamentos (Pedro David) | Desenvolvimento
| AML.03.02 | Products | Virtual IBANs | C0030 | Total Value (EUR) of transactions on Virtual IBANs (incoming) | [7 empty] | Pagamentos (Pedro David) | Desenvolvimento
| AML.03.02 | Products | Virtual IBANs | C0040 | Number of transactions on Virtual IBANs (outgoing) | [7 empty] | Pagamentos (Pedro David) | Concluído | Será reportado o valor 0.
| AML.03.02 | Products | Virtual IBANs | C0050 | Total Value (EUR) of transactions on Virtual IBANs (outgoing) | [7 empty] | Pagamentos (Pedro David) | Concluído | Será reportado o valor 0.
| AML.03.02 | Products | Virtual IBANs | C0060 | Total Number of re-issued IBANs | [7 empty] | Pagamentos (Pedro David) | Concluído | Será reportado o valor 0.
| AML.03.03 | Products | Prepaid cards | C0010 | Total Number of Prepaid Cards issued |  | Produtos de moeda eletrónica e outros produtos pré-pagos | 3.7.1 a) (aplicar filtro de pré-pago) |  |  |  |  | Cartões (Susana Martins) | Concluído | Será reportado o valor 0.
| AML.03.03 | Products | Prepaid cards | C0020 | Total Value (EUR) of the issued prepaid cards |  | Produtos de moeda eletrónica e outros produtos pré-pagos | 3.7.1 d) |  |  |  |  | Cartões (Susana Martins) | Concluído | Será reportado o valor 0.
| AML.03.03 | Products | Prepaid cards | C0030 | Total Value (EUR) outstanding on prepaid cards issued |  | Produtos de moeda eletrónica e outros produtos pré-pagos | 3.7.1 d) - 3.7.1 c) |  |  |  |  | Cartões (Susana Martins) | Concluído | Será reportado o valor 0.
| AML.03.03 | Products | Prepaid cards | C0040 | Total number of customers using prepaid cards |  | Produtos de moeda eletrónica e outros produtos pré-pagos | Associado ao C0020 |  |  |  |  | Cartões (Susana Martins) | Concluído | Será reportado o valor 0.
| AML.03.03 | Products | Prepaid cards | C0050 | Total number of customers using prepaid cards with more than 3 prepaid cards |  | Produtos de moeda eletrónica e outros produtos pré-pagos | Associado ao C0040 (com tratamento da variável) |  |  |  |  | Cartões (Susana Martins) | Concluído | Será reportado o valor 0.
| AML.03.04 | Products | Lending and Factoring | C0010 | Total Number of outstanding loans | [8 empty] | Desenvolvimento
| AML.03.04 | Products | Lending and Factoring | C0020 | Total Value (EUR) of outstanding loans | [8 empty] | Desenvolvimento
| AML.03.04 | Products | Lending and Factoring | C0030 | Total Number of outstanding real estate loans | [8 empty] | Desenvolvimento
| AML.03.04 | Products | Lending and Factoring | C0040 | Total Number of outstanding real estate loans with third party payments | [8 empty] | Desenvolvimento
| AML.03.04 | Products | Lending and Factoring | C0050 | Total Value (EUR) of loans granted | [8 empty] | Desenvolvimento
| AML.03.04 | Products | Lending and Factoring | C0060 | Total Number of outstanding asset backed loans with cash collateral | [8 empty] | Recolha de Info.
| AML.03.04 | Products | Lending and Factoring | C0070 | Total Number of loan repayments | [8 empty] | Recolha de Info.
| AML.03.04 | Products | Lending and Factoring | C0080 | Total Number of prematurely repaid loans | [8 empty] | Recolha de Info.
| AML.03.04 | Products | Lending and Factoring | C0090 | Total Number of loan repayments from non-EEA countries | [8 empty] | Recolha de Info.
| AML.03.04 | Products | Lending and Factoring | C0100 | Total Number of consumer loans granted that are not associated to the acquisition of any product/service | [8 empty] | Recolha de Info.
| AML.03.04 | Products | Lending and Factoring | C0110 | Total Number of factoring contracts granted | [8 empty] | Desenvolvimento
| AML.03.04 | Products | Lending and Factoring | C0120 | Total Value (EUR) of factoring contracts granted | [8 empty] | Desenvolvimento
| AML.03.04 | Products | Lending and Factoring | C0130 | Total Value (EUR) of factoring contracts granted to obligors established in non-EEA countries | [8 empty] | Desenvolvimento
| AML.03.05 | Products | Life insurance contracts | C0010 | total amount (EUR) of gross written premiums (incoming) | [7 empty] | PBC (Denise Macau) | Concluído | Será reportado o valor 0.
| AML.03.05 | Products | Life insurance contracts | C0020 | total of amount (EUR) of surrender value of the insurance contracts | [7 empty] | PBC (Denise Macau) | Concluído | Será reportado o valor 0.
| AML.03.05 | Products | Life insurance contracts | C0030 | Percentage of all gross written premium (amount in EUR) paid directly to the life insurance broker | [7 empty] | PBC (Denise Macau) | Concluído | Será reportado o valor 0.
| AML.03.05 | Products | Life insurance contracts | C0040 | Number of insurance contracts that are not used for low risk contracts | [7 empty] | PBC (Denise Macau) | Concluído | Será reportado o valor 0.
| AML.03.06 | Products | Currency exchange (involving cash) | C0010 | Number of currency exchange transactions carried out (sell) |  | Operações de câmbio | Data set aplicando filtros (3.9) |  |  |  |  | N/A | Desenvolvimento
| AML.03.06 | Products | Currency exchange (involving cash) | C0020 | Number of currency exchange transactions carried out (buy) |  | Operações de câmbio | Data set aplicando filtros (3.9) |  |  |  |  | N/A | Desenvolvimento
| AML.03.06 | Products | Currency exchange (involving cash) | C0030 | Number of currency exchange transactions carried out, where the transaction is above 1000 euros (sell) |  | Operações de câmbio | Data set aplicando filtros (3.9) |  |  |  |  | N/A | Desenvolvimento
| AML.03.06 | Products | Currency exchange (involving cash) | C0040 | Number of currency exchange transactions carried out, where the transaction is above 1000 euros (buy) |  | Operações de câmbio | Data set aplicando filtros (3.9) |  |  |  |  | N/A | Desenvolvimento
| AML.03.06 | Products | Currency exchange (involving cash) | C0050 | Total Value (EUR) of currency exchange transactions carried out (sell) |  | Operações de câmbio | Data set aplicando filtros (3.9) |  |  |  |  | N/A | Desenvolvimento
| AML.03.06 | Products | Currency exchange (involving cash) | C0060 | Total Value (EUR) of currency exchange transactions carried out (buy) |  | Operações de câmbio | Data set aplicando filtros (3.9) |  |  |  |  | N/A | Desenvolvimento
| AML.03.06 | Products | Currency exchange (involving cash) | C0070 | Value (EUR) of currency exchange transactions cash-to-cash carried out |  | Operações de câmbio | 3.9.3 a) |  |  |  |  | N/A | Concluído | No RPB este datapoint é N/A.
| AML.04.01 | Services | Investment services | C0010 | number of retail clients | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Desenvolvimento
| AML.04.01 | Services | Investment services | C0020 | number of professional clients | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Desenvolvimento
| AML.04.01 | Services | Investment services | C0030 | Number of AML/CFT regulated customers outside the EEA | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Desenvolvimento
| AML.04.01 | Services | Investment services | C0040 | number of retail clients | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Desenvolvimento
| AML.04.01 | Services | Investment services | C0050 | number of professional clients | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Desenvolvimento
| AML.04.01 | Services | Investment services | C0060 | Indirect Custody Assets: Percentage of assets under custody for which the obliged entity does not have a direct business relationship with the final investor | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Desenvolvimento
| AML.04.01 | Services | Investment services | C0070 | Number of AML/CFT regulated customers outside the EEA | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Desenvolvimento
| AML.04.01 | Services | Investment services | C0080 | number of retail clients | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Desenvolvimento
| AML.04.01 | Services | Investment services | C0090 | number of professional clients | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Desenvolvimento
| AML.04.01 | Services | Investment services | C0100 | total assets under management | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Desenvolvimento
| AML.04.01 | Services | Investment services | C0110 | Number of customers for which customer holding total assets with a value of at least EUR 5 000 000 | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Desenvolvimento
| AML.04.03 | Services | Wealth management | C0010 | Total Number of customers (NP) with total assets under management over a value of at least EUR 5,000,000 AND with total assets over a value of at least EUR 50,000,000 |  |  | 2.6.1 a) (confirmar filtros) |  |  |  |  | Private Banking (Tiago Pousinha) | Desenvolvimento
| AML.04.03 | Services | Wealth management | C0020 | Total Number of customers (NP) that fall under the definition of private banking (EBA Risk Factor Guidelines) |  |  | 3.4.1 (com filtro>=0.5M) |  |  |  |  | Private Banking (Tiago Pousinha) | Desenvolvimento
| AML.04.04 | Services | Correspondence services | C0010 | Total Value (EUR) of transactions executed on behalf of the respondent client (incoming) |  |  | Data set 3.8.2 |  |  |  |  | Negócio Internacional | Recolha de Info.
| AML.04.04 | Services | Correspondence services | C0020 | Total Value (EUR) of transactions executed on behalf of the respondent client (outgoing) |  |  | Data set 3.8.2 |  |  |  |  | Negócio Internacional | Recolha de Info.
| AML.04.04 | Services | Correspondence services | C0030 | Total Value (EUR) of transactions going through payable through accounts (incoming) |  |  | Data set 3.8.2 |  |  |  |  | Negócio Internacional | Concluído | Pendente de confirmação se será reportado o valor 0 ou "N/A".
| AML.04.04 | Services | Correspondence services | C0040 | Total Value (EUR) of transactions going through payable through accounts (outgoing) |  |  | Data set 3.8.2 |  |  |  |  | Negócio Internacional | Concluído | Pendente de confirmação se será reportado o valor 0 ou "N/A".
| AML.04.04 | Services | Correspondence services | C0050 | Total Value (EUR) of transactions going through nested accounts (incoming) |  |  | Data set 3.8.2 |  |  |  |  | Negócio Internacional | Concluído | Pendente de confirmação se será reportado o valor 0 ou "N/A".
| AML.04.04 | Services | Correspondence services | C0060 | Total Value (EUR) of transactions going through nested accounts (outgoing) |  |  | Data set 3.8.2 |  |  |  |  | Negócio Internacional | Concluído | Pendente de confirmação se será reportado o valor 0 ou "N/A".
| AML.04.05 | Services | Trade finance | C0010 | Total Number of trade finance customers |  | Trade finance | 3.5.1 |  |  |  |  | Negócio Internacional / Rita Velada e Alfredo Reis | Recolha de Info.
| AML.04.05 | Services | Trade finance | C0020 | Total Number of trade finance transactions (incoming) |  | Trade finance | 3.5.2 (com filtro de incoming) |  |  |  |  | Negócio Internacional / Rita Velada e Alfredo Reis | Recolha de Info.
| AML.04.05 | Services | Trade finance | C0030 | Total Number of trade finance transactions (outgoing) |  | Trade finance | 3.5.2 (com filtro de outgoing) |  |  |  |  | Negócio Internacional / Rita Velada e Alfredo Reis | Recolha de Info.
| AML.04.05 | Services | Trade finance | C0040 | Total Value (EUR) of trade finance transactions (incoming) |  | Trade finance | 3.5.3 (com filtro de incoming) |  |  |  |  | Negócio Internacional / Rita Velada e Alfredo Reis | Recolha de Info.
| AML.04.05 | Services | Trade finance | C0050 | Total Value (EUR) of trade finance transactions (outgoing) |  | Trade finance | 3.5.3 (com filtro de outgoing) |  |  |  |  | Negócio Internacional / Rita Velada e Alfredo Reis | Recolha de Info.
| AML.04.06 | Services | E-money | C0010 | Number of e-money payment transactions (incoming) |  | Produtos de moeda eletrónica e outros produtos pré-pagos | 3.7.1 a) (aplicar filtro de e-money e incoming) |  |  |  |  | Cartões (Susana Martins/ Nuno Coelho) | Validação | Pendente de confirmação se será reportado o valor 0.
| AML.04.06 | Services | E-money | C0020 | Number of e-money payment transactions (outgoing) |  | Produtos de moeda eletrónica e outros produtos pré-pagos | 3.7.1 a) (aplicar filtro de e-money e outgoing) |  |  |  |  | Cartões (Susana Martins/ Nuno Coelho) | Validação | Pendente de confirmação se será reportado o valor 0.
| AML.04.06 | Services | E-money | C0030 | Total Value (EUR) of e-money payment transactions (incoming) |  | Produtos de moeda eletrónica e outros produtos pré-pagos | 3.7.1 d) (aplicar filtro de e-money e incoming) |  |  |  |  | Cartões (Susana Martins/ Nuno Coelho) | Validação | Pendente de confirmação se será reportado o valor 0.
| AML.04.06 | Services | E-money | C0040 | Total Value (EUR) of e-money payment transactions (outgoing) |  | Produtos de moeda eletrónica e outros produtos pré-pagos | 3.7.1 d) (aplicar filtro de e-money e outgoing) |  |  |  |  | Cartões (Susana Martins/ Nuno Coelho) | Validação | Pendente de confirmação se será reportado o valor 0.
| AML.04.06 | Services | E-money | C0050 | Value (EUR) of e-money payment transactions by non-identified customers |  | Produtos de moeda eletrónica e outros produtos pré-pagos | Associado ao C0040 (com tratamento da variável) |  |  |  |  | Cartões (Susana Martins/ Nuno Coelho) | Validação | Pendente de confirmação se será reportado o valor 0.
| AML.04.11 | Services | Management of UCITS/AIFS | C0010 | Number of retail investor customers | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Concluído | Será reportado o valor 0.
| AML.04.11 | Services | Management of UCITS/AIFS | C0020 | Number of professional investor customers | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Concluído | Será reportado o valor 0.
| AML.04.11 | Services | Management of UCITS/AIFS | C0030 | Total assets under management of UCITSs | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Concluído | Será reportado o valor 0.
| AML.04.11 | Services | Management of UCITS/AIFS | C0040 | Number of retail investor customers | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Concluído | Será reportado o valor 0.
| AML.04.11 | Services | Management of UCITS/AIFS | C0050 | Number of professional investor customers | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Concluído | Será reportado o valor 0.
| AML.04.11 | Services | Management of UCITS/AIFS | C0060 | Number of open-ended funds | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Concluído | Será reportado o valor 0.
| AML.04.11 | Services | Management of UCITS/AIFS | C0070 | Number of closed-ended funds | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Concluído | Será reportado o valor 0.
| AML.04.11 | Services | Management of UCITS/AIFS | C0080 | Total assets under management | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Concluído | Será reportado o valor 0.
| AML.04.11 | Services | Management of UCITS/AIFS | C0090 | Total assets under management in unlisted assets | [7 empty] | Fundos (Carlos Daniel/ Vladimiro Oliveira) | Concluído | Será reportado o valor 0.
| AML.04.12 | Services | Safe custody services | C0010 | Total Number of customers using safe deposit boxes |  | Registos informatizados e centralizados | 8.2.1 |  |  |  |  | EverydayBanking - Gestão de ATM´s e Cofres de Aluguer | Validação
| AML.04.14 | Services | Cash transactions | C0010 | Number of cash transactions (withdrawals) |  |  | Count das linhas do C0030 | [5 empty] | Desenvolvimento | A aguardar envio dos números do lado da Rita Mimoso
| AML.04.14 | Services | Cash transactions | C0020 | Number of cash transactions (deposits) |  |  | Count das linhas do 3.1.4 a) (sem filtro de montante) |  |  |  |  | Analítica (FCC) | Desenvolvimento | A aguardar envio dos números do lado da Rita Mimoso
| AML.04.14 | Services | Cash transactions | C0030 | Total Value (EUR) of cash transactions (withdrawals) | [8 empty] | Desenvolvimento | A aguardar envio dos números do lado da Rita Mimoso
| AML.04.14 | Services | Cash transactions | C0040 | Total Value (EUR) of cash transactions (deposits) |  |  | 3.1.4 a) (sem filtro de montante) |  |  |  |  | Analítica (FCC) | Desenvolvimento | A aguardar envio dos números do lado da Rita Mimoso
| AML.04.14 | Services | Cash transactions | C0050 | Total Number of natural persons totalling cash transactions over 20 000 EUR |  |  | Count distinct de clientes 3.1.4 a) i) (com filtro de montante 20k) |  |  |  |  | Analítica (FCC) | Recolha de Info. | A aguardar envio dos números do lado da Rita Mimoso
| AML.05.01 | Geographies | Geographies | C0010 | Country |  |  | Data set 2.1 |  |  |  |  | Analítica (FCC) | Concluído
| AML.05.01 | Geographies | Geographies | C0020 | Number of customers which are Natural Persons (NP) per country |  |  | Data set 2.1 |  |  |  |  | Analítica (FCC) | Concluído
| AML.05.01 | Geographies | Geographies | C0030 | Number of customers which are Legal Entities (LE) per country |  |  | Data set 2.1 |  |  |  |  | Analítica (FCC) | Concluído
| AML.05.01 | Geographies | Geographies | C0040 | Number of customers NP who are PEPs per country |  |  | Data set 2.1 |  |  |  |  | Analítica (FCC) | Desenvolvimento
| AML.05.01 | Geographies | Geographies | C0050 | Number of customers LE whose Beneficial Owners are PEPs per country |  |  | Data set 2.1 |  |  |  |  | Analítica (FCC) | Desenvolvimento
| AML.05.01 | Geographies | Geographies | C0060 | Number of incoming transactions by country |  |  | 5.3.1 a) i) + 5.3.2 a) i) |  |  |  |  | Analítica (FCC) | Recolha de Info. | Aguardar feedback da DB
| AML.05.01 | Geographies | Geographies | C0070 | Total value (EUR) of incoming transactions by country |  |  | 5.3.1 a) ii) + 5.3.2 a) ii) |  |  |  |  | Analítica (FCC) | Recolha de Info. | Aguardar feedback da DB
| AML.05.01 | Geographies | Geographies | C0080 | Number of outgoing transactions by country |  |  | 5.3.1 b) i) + 5.3.2 b) i) |  |  |  |  | Analítica (FCC) | Recolha de Info. | Aguardar feedback da DB
| AML.05.01 | Geographies | Geographies | C0090 | Total value (EUR) of outgoing transactions by country |  |  | 5.3.1 b) ii) + 5.3.2 b) ii) |  |  |  |  | Analítica (FCC) | Recolha de Info. | Aguardar feedback da DB
| AML.05.01 | Geographies | Geographies | C0100 | Total value (EUR) of entity's investment undertakings (CIUs) by country | [8 empty] | Concluído | Reportar com N/A
| AML.05.01 | Geographies | Geographies | C0110 | Number of investors by country | [8 empty] | Concluído | Reportar com N/A
| AML.05.01 | Geographies | Geographies | C0120 | Total value (EUR) of assets under management by country (for AMCs) | [8 empty] | Concluído | Reportar com N/A
| AML.05.01 | Geographies | Geographies | C0130 | Number of institutions established in foreign countries to whom you provide correspondent services (by country) |  |  | Count distinct clientes 5.4.2 a) |  |  |  |  | Negócio Internacional | Recolha de Info. | Aguardar feedback do Negócio Internacional
| AML.05.01 | Geographies | Geographies | C0140 | Total value of incoming funds moved on behalf of the respondent's clients by country of respondent's establishment |  |  | Count distinct clientes 5.4.2 b) |  |  |  |  | Negócio Internacional | Recolha de Info. | Aguardar feedback do Negócio Internacional
| AML.05.01 | Geographies | Geographies | C0150 | Total value of outgoing funds moved on behalf of the respondent's clients by country of respondent's establishment |  |  | 5.4.1 b) |  |  |  |  | Negócio Internacional | Recolha de Info. | Aguardar feedback do Negócio Internacional
| AML.05.01 | Geographies | Geographies | C0160 | Number of branches by country | [8 empty] | Recolha de Info.
| AML.05.01 | Geographies | Geographies | C0170 | Number of subsidiaries by country | [8 empty] | Recolha de Info.
| AML.06.01 | Distribution | Distribution channels | C0010 | Country |  | Risco inerente aos canais de distribuição | [6 empty] | Validação | Validar com DB que o mapa deverá vir a N/A
| AML.06.01 | Distribution | Distribution channels | C0020 | Number of agents by country |  | Risco inerente aos canais de distribuição | 4.3.1 |  |  |  |  | Área de Contas/ Aquisição e Preçário | Validação | Validar com DB que o mapa deverá vir a N/A
| AML.06.01 | Distribution | Distribution channels | C0030 | Number of distributors by country |  | Risco inerente aos canais de distribuição | 4.4.1 |  |  |  |  | Área de Contas/ Aquisição e Preçário | Validação | Validar com DB que o mapa deverá vir a N/A
| AML.06.01 | Distribution | Distribution channels | C0040 | Total value of gross written premiums through insurance contracts issued through brokers, broken down by country the brokers are established | [8 empty] | Validação | Validar com DB que o mapa deverá vir a N/A
| AML.06.01 | Distribution | Distribution channels | C0050 | Number of white labelling partners by country of establishment |  | PBC | [6 empty] | Validação | Validar com DB que o mapa deverá vir a N/A
| AML.07.06 | Target Financial Sanctions | Targeted Financial Sanctions and Compliance with Fund Transfers Regulation | C0020 | Outbound Transfers with Information Requests (RFI) | [7 empty] | Pagamentos | Desenvolvimento
| AML.07.06 | Target Financial Sanctions | Targeted Financial Sanctions and Compliance with Fund Transfers Regulation | C0030 | Total Outbound Transfers | [7 empty] | Pagamentos | Desenvolvimento
| AML.07.06 | Target Financial Sanctions | Targeted Financial Sanctions and Compliance with Fund Transfers Regulation | C0040 | Rejected/Returned Outbound Transfers (%) | [7 empty] | Pagamentos | Desenvolvimento

## Pressupostos (hidden)
Overview
O quadro infra apresenta o Gap Analysis realizado entre os reportes AMLA e RPB, incluido também tabelas e campos fontes utilizadas no reporte RPB.
| Tema | Reporte AMLA |  |  |  |  | Reporte RPB |  | Next Steps /
| Identificado | Template | Section | Mapa | Pressuposto | Menção no Doc | Pressuposto | Menção no Doc | Dúvidas
| Data de referência dos dados | Todos | Todos | Todos | Mensal | Date of reference: The reference point is always the end of the reporting year (31 december) | Anual | Nos termos do n.º 1 do artigo 3.º da presente Instrução, o RPB deve ser enviado ao Banco de Portugal até 31 de março de cada ano, reportando-se ao período compreendido entre 1 de janeiro e 31 de dezembro do ano anterior.
| Data de referência dos dados | AML.02.01 | Costumers | Costumers |  |  | Última posição mensal de Dezembro | Informação geral à data do termo do período de referência do RPB (31 de dezembro)
| Universo | AML.02.01 | Costumers | Costumers | Todos os clientes do Banco (incluindo todos os titulares e clientes associados a Leasing, Factoring, Descobertos, entre outros) | • A customer is a natural or legal person who maintains a business relationship or conducts an occasional transaction with a financial institution pursuant to Regulation (EU) 2024/1624. It also includes the persons referred to in Article 19(6) of that Regulation. • ‘Business relationship’ means a business, professional or commercial relationship connected with the professional activities of an obliged entity, which is set up between an obliged entity and a customer, including in the absence of a written contract and which is expected to have, at the time when the contact is established, or which subsequently acquires, an element of repetition or duration. (Article 2(19) Regulation (EU) 2024/1624 (AMLR)). |  |  | Confirmar se entra no reporte: - Clientes de operações canceladas