## Plano_DE
[7 empty] | 823.2 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8 | 16.8
[7 empty] | VAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1.575
[7 empty] | FTE REAIS | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 0.525
[7 empty] | FTE ESP. | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1 | 2.1
[8 empty] | Mês 1 | [22 empty] | Mês 2 | [22 empty] | Mês 3
[7 empty] | 2024-12-31 | 2025-01-01 | 2025-01-02 | 2025-01-03 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18
|  |  |  | # Campos | Duração (horas) | Duração (Dias) | VAL | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19 | 1900-01-20 | 1900-01-21 | 1900-01-22 | 1900-01-23 | 1900-01-24 | 1900-01-25 | 1900-01-26 | 1900-01-27 | 1900-01-28 | 1900-01-29 | 1900-01-30 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69
| Gestão Projeto |  |  | n.a. | 0 | 0
| 0. Gestão Projeto |  |  | n.a. | 51.2 | 6.4 | 0 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| 1. Set-Up |  |  | n.a. | 32 | 4 | 0 | 1899-12-31: 2; 1900-01-01: 2
| 2. Assessment ao Green Dashboard (Esp. Atual) |  |  | n.a. | 64 | 8 | 0 | 1900-01-02: 2; 1900-01-03: 2; 1900-01-04: 2; 1900-01-05: 2
| 3. Re-testes aos campos concluídos do GD âmbito projeto anterior |  |  | 23 | 82 | 10.25 | 0 | 1900-01-06: 2; 1900-01-07: 2; 1900-01-08: 2; 1900-01-09: 2; 1900-01-10: 2; 1900-01-11: 0.25
INSTRUMENT_COD_SOC | INSTRUMENT | COD_SOC |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_SUBPORTFOLIO_ID | INSTRUMENT | SUBPORTFOLIO_ID |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_DT_RFRNC | INSTRUMENT | DT_RFRNC |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_DFLT_STTS_INSTRMNT | INSTRUMENT | DFLT_STTS_INSTRMNT |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_IMPRMNT_STTS | INSTRUMENT | IMPRMNT_STTS |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_PRFRMNG_STTS | INSTRUMENT | PRFRMNG_STTS |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_TYP_INSTRMNT | INSTRUMENT | TYP_INSTRMNT |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_GRSS_CRRYNG_AMNT_INSTRMNT | INSTRUMENT | GRSS_CRRYNG_AMNT_INSTRMNT |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_ACCMLTD_CHNGS_FV_CR_INSTRMNT | INSTRUMENT | ACCMLTD_CHNGS_FV_CR_INSTRMNT |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_ACCNTNG_CLSSFCTN | INSTRUMENT | ACCNTNG_CLSSFCTN |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_OFF_BLNC_SHT_AMNT_INSTRMNT | INSTRUMENT | OFF_BLNC_SHT_AMNT_INSTRMNT |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_PRVSNS_OFF_BLNC_SHT | INSTRUMENT | PRVSNS_OFF_BLNC_SHT |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_RWA | INSTRUMENT | RWA |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_ACCMLTD_IMPRMNT_INSTRMNT | INSTRUMENT | ACCMLTD_IMPRMNT_INSTRMNT |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_COD_SOC_INTRGRP | INSTRUMENT | COD_SOC_INTRGRP |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_LCL_INSTMRNT_ID | INSTRUMENT | LCL_INSTMRNT_ID |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_FLG_INTRBSNSS | INSTRUMENT | FLG_INTRBSNSS |  | SCA SCB1 | 4 |  | 0
INSTRUMENT_INTRBSNSS_ADJ_COD | INSTRUMENT | INTRBSNSS_ADJ_COD |  | SCA SCB1 | 4 |  | 0
INSTRUMENT_COD_SOC_DSTNTN | INSTRUMENT | COD_SOC_DSTNTN |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_BSNSS_AREA_DSTNTN | INSTRUMENT | BSNSS_AREA_DSTNTN |  | SCA SCB1 | 4 |  | 0
INSTRUMENT_INTRNL_TRNSFR_RT_OFF_BLNC | INSTRUMENT | INTRNL_TRNSFR_RT_OFF_BLNC |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_IDCMB | INSTRUMENT | IDCMB |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_RWA_OFF_BLNC | INSTRUMENT | RWA_OFF_BLNC |  | SCA SCB1 | 3.5 |  | 0
| 4. Especificação de novos requisitos |  |  | 14 | 15 | 1.875 | 0 | 1900-01-11: 1.75; 1900-01-12: 0.125
INSTRUMENT_CCF | INSTRUMENT | CCF |  | SCA SCB1 | 1 |  | 0
INSTRUMENT_EAD | INSTRUMENT | EAD |  | SCA SCB1 | 1 |  | 0
INSTRUMENT_TYP_OFF_BLNC_PRDCT | INSTRUMENT | TYP_OFF_BLNC_PRDCT |  | SCA SCB1 | 1 |  | 0
INSTR_PROTECTION_COD_SOC | INSTR_PROTECTION | COD_SOC |  | SCA SCB1 | 1 |  | 0
INSTR_PROTECTION_DT_RFRNC | INSTR_PROTECTION | DT_RFRNC |  | SCA SCB1 | 1 |  | 0
INSTR_PROTECTION_INSTRMNT_ID | INSTR_PROTECTION | INSTRMNT_ID |  | SCA SCB1 | 1 |  | 0
INSTR_PROTECTION_PRTCTN_ID | INSTR_PROTECTION | PRTCTN_ID |  | SCA SCB1 | 1 |  | 0
PROTECTION_COD_SOC | PROTECTION | COD_SOC |  | SCA SCB1 | 1 |  | 0
PROTECTION_DT_RFRNC | PROTECTION | DT_RFRNC |  | SCA SCB1 | 1 |  | 0
PROTECTION_PRTCTN_ID | PROTECTION | PRTCTN_ID |  | SCA SCB1 | 1 |  | 0
PROTECTION_TYP_PRTCTN | PROTECTION | TYP_PRTCTN |  | SCA SCB1 | 1 |  | 0
PROTECTION_PRTCTN_VL | PROTECTION | PRTCTN_VL |  | SCA SCB1 | 1 |  | 0
PROTECTION_FLG_ELCTRC_VHCL | PROTECTION | FLG_ELCTRC_VHCL |  | SCA SCB1 | 2 |  | 0
INSTR_ACTIVITY_PRCNTG_ACTVTY | INSTR_ACTIVITY | PRCNTG_ACTVTY |  | SCA SCB1 | 1 |  | 0
| 5. Testes/Re-testes |  |  |  | 498.4 |  | 0
|  | Testes ao Universo |  | n.a. | 40 | 5 | 0 | 1900-01-12: 1.875; 1900-01-13: 2; 1900-01-14: 1.125
|  | Testes aos Campos |  | 45 | 382 | 47.75 | 0 | 1900-01-14: 0.875; 1900-01-15: 2; 1900-01-16: 2; 1900-01-17: 2; 1900-01-18: 2; 1900-01-19: 2; 1900-01-20: 2; 1900-01-21: 2; 1900-01-22: 2; 1900-01-23: 2; 1900-01-24: 2; 1900-01-25: 2; 1900-01-26: 2; 1900-01-27: 2; 1900-01-28: 2; 1900-01-29: 2; 1900-01-30: 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.875
INSTRUMENT_INSTRMNT_ID | INSTRUMENT | INSTRMNT_ID |  | SCA SCB1 | 22 |  | 0
INSTRUMENT_CCF | INSTRUMENT | CCF |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_EAD | INSTRUMENT | EAD |  | SCA SCB1 | 3.5 |  | 0
INSTRUMENT_AVRG_BLNC | INSTRUMENT | AVRG_BLNC |  | SCA SCB1 | 7.5 |  | 0
INSTRUMENT_NW_BSNSS | INSTRUMENT | NW_BSNSS |  | SCA SCB 2 | 15 |  | 0
INSTRUMENT_GRSS_INTRST_INCM | INSTRUMENT | GRSS_INTRST_INCM |  | SCA SCB 2 | 18 |  | 0
INSTRUMENT_GRSS_CMMSSN_INCM | INSTRUMENT | GRSS_CMMSSN_INCM |  | SCA SCB 2 | 18 |  | 0
INSTRUMENT_INTRNL_TRNSFR_RT | INSTRUMENT | INTRNL_TRNSFR_RT |  | SCA SCB1 | 7.5 |  | 0
INSTRUMENT_NT_LN_LSS_PRVSN | INSTRUMENT | NT_LN_LSS_PRVSN |  | SCA SCB1 | 7.5 |  | 0
INSTRUMENT_BSNSS_AREA | INSTRUMENT | BSNSS_AREA |  | SCA SCB1 | 35 |  | 0
INSTRUMENT_MNGMNT_PRDCT | INSTRUMENT | MNGMNT_PRDCT |  | SCA SCB1 | 18 |  | 0
INSTRUMENT_GRSS_CMMSSN_EXPNS | INSTRUMENT | GRSS_CMMSSN_EXPNS |  | SCA SCB1 | 7.5 |  | 0
INSTRUMENT_GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | INSTRUMENT | GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS |  | SCA SCB1 | 7.5 |  | 0
INSTRUMENT_AVRG_BLNC_OFF_BLNC | INSTRUMENT | AVRG_BLNC_OFF_BLNC |  | SCA SCB1 | 7.5 |  | 0
INSTRUMENT_GRSS_CMMSSN_INCM_OFF_BLNC | INSTRUMENT | GRSS_CMMSSN_INCM_OFF_BLNC |  | SCA SCB 2 | 18 |  | 0
INSTRUMENT_GRSS_CMMSSN_EXPNS_OFF_BLNC | INSTRUMENT | GRSS_CMMSSN_EXPNS_OFF_BLNC |  | SCA SCB1 | 7.5 |  | 0
INSTRUMENT_GRSS_INTRST_EXPNS | INSTRUMENT | GRSS_INTRST_EXPNS |  | SCA SCB1 | 7.5 |  | 0
INSTRUMENT_NT_LN_LSS_PRVSN_OFF_BLNC | INSTRUMENT | NT_LN_LSS_PRVSN_OFF_BLNC |  | SCA SCB1 | 7.5 |  | 0
INSTRUMENT_GRSS_INTRST_INCM_CCRR | INSTRUMENT | GRSS_INTRST_INCM_CCRR |  | SCA SCB1 | 7.5 |  | 0
INSTRUMENT_GRSS_INTRST_EXPNS_CCRR | INSTRUMENT | GRSS_INTRST_EXPNS_CCRR |  | SCA SCB1 | 7.5 |  | 0
INSTRUMENT_GRSS_CMMSSN_INCM_CCRR | INSTRUMENT | GRSS_CMMSSN_INCM_CCRR |  | SCA SCB1 | 7.5 |  | 0
INSTRUMENT_GRSS_CMMSSN_EXPNS_CCRR | INSTRUMENT | GRSS_CMMSSN_EXPNS_CCRR |  | SCA SCB1 | 7.5 |  | 0
INSTRUMENT_GNS_FNNCL_TRNSCTN_EXCHNG_CCRR | INSTRUMENT | GNS_FNNCL_TRNSCTN_EXCHNG_CCRR |  | SCA SCB1 | 7.5 |  | 0
INSTRUMENT_BSNSS_AREA_CCRR | INSTRUMENT | BSNSS_AREA_CCRR |  | SCA SCB1 | 8 |  | 0
INSTRUMENT_GRSS_CMMSSN_INCM_OFF_BLNC_CCRR | INSTRUMENT | GRSS_CMMSSN_INCM_OFF_BLNC_CCRR |  | SCA SCB1 | 7.5 |  | 0
INSTRUMENT_GRSS_CMMSSN_EXPNS_OFF_BLNC_CCRR | INSTRUMENT | GRSS_CMMSSN_EXPNS_OFF_BLNC_CCRR |  | SCA SCB1 | 7.5 |  | 0
INSTRUMENT_CNCLLD_INSTRMNT_STTS | INSTRUMENT | CNCLLD_INSTRMNT_STTS |  | SCA SCB1 | 8 |  | 0
INSTRUMENT_TYP_OFF_BLNC_PRDCT | INSTRUMENT | TYP_OFF_BLNC_PRDCT |  | SCA SCB1 | 4 |  | 0
INSTR_PROTECTION_COD_SOC | INSTR_PROTECTION | COD_SOC |  | SCA SCB1 | 3.5 |  | 0
INSTR_PROTECTION_DT_RFRNC | INSTR_PROTECTION | DT_RFRNC |  | SCA SCB1 | 3.5 |  | 0
INSTR_PROTECTION_INSTRMNT_ID | INSTR_PROTECTION | INSTRMNT_ID |  | SCA SCB1 | 3.5 |  | 0
INSTR_PROTECTION_PRTCTN_ID | INSTR_PROTECTION | PRTCTN_ID |  | SCA SCB1 | 3.5 |  | 0
INSTR_PROTECTION_TYP_RLTN | INSTR_PROTECTION | TYP_RLTN |  | SCA SCB 2 | 4 |  | 0
PROTECTION_COD_SOC | PROTECTION | COD_SOC |  | SCA SCB1 | 3.5 |  | 0
PROTECTION_DT_RFRNC | PROTECTION | DT_RFRNC |  | SCA SCB1 | 3.5 |  | 0
PROTECTION_PRTCTN_ID | PROTECTION | PRTCTN_ID |  | SCA SCB1 | 3.5 |  | 0
PROTECTION_TYP_PRTCTN | PROTECTION | TYP_PRTCTN |  | SCA SCB1 | 4 |  | 0
PROTECTION_PRTCTN_VL | PROTECTION | PRTCTN_VL |  | SCA SCB1 | 3.5 |  | 0
PROTECTION_FLG_ELCTRC_VHCL | PROTECTION | FLG_ELCTRC_VHCL |  | SCA SCB1 | 5 |  | 0
INSTR_ACTIVITY_COD_SOC | INSTR_ACTIVITY | COD_SOC |  | SCA SCB 2 | 3.5 |  | 0
INSTR_ACTIVITY_DT_RFRNC | INSTR_ACTIVITY | DT_RFRNC |  | SCA SCB 2 | 3.5 |  | 0
INSTR_ACTIVITY_INSTRMNT_ID | INSTR_ACTIVITY | INSTRMNT_ID |  | SCA SCB 2 | 3.5 |  | 0
INSTR_ACTIVITY_SSTNBL_CTGRY | INSTR_ACTIVITY | SSTNBL_CTGRY |  | SCA SCB 2 | 18 |  | 0
INSTR_ACTIVITY_PRCNTG_ACTVTY | INSTR_ACTIVITY | PRCNTG_ACTVTY |  | SCA SCB1 | 3.5 |  | 0
INSTR_ACTIVITY_SSTNBL_INDCTR | INSTR_ACTIVITY | SSTNBL_INDCTR |  | SCA SCB 2 | 18 |  | 0
|  | Re-testes |  |  | 76.4 | 9.55 | 0 | [38 empty] | 1.125 | 2 | 2 | 2 | 2 | 0.425
| 5. Documentação |  |  |  | 80 | 10 | 0 | [43 empty] | 1.575 | 2 | 2 | 2 | 2 | 0.425
x
| Horas Total | 823.2 | SMART TOTAL
| Horas Novos Requisitos |  | SMART NOVOS REQUISITOS

## Macro_Plano_2025_v1
2 corresponde a 1 dia de trabalho
Terminamos no dia 11
[10 empty] | Janeiro |  |  |  | Fevereiro |  |  | Março
| ID | Atividade |  | Status | # Campos | Duração (semana) | Duração (horas) | 2025-01-03 | 2025-01-10 | 2025-01-17 | 2025-01-24 | 2025-01-31 | 2025-02-07 | 2025-02-14 | 2025-02-21 | 2025-02-28 | 2025-03-07 | 2025-03-14
| 0. | Gestão Projeto |  |  | n.a. |  | 41.6 | 0.2 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
| 1. | Set-Up |  |  | n.a. |  | #REF! | 2025-01-03: #REF!
| 2. | Assessment ao Green Dashboard (Especificação Atual) |  |  | n.a. |  | 64 | 2025-01-10: 8
| 3. | Testes regressivos aos campos concluidos do GD (âmbito projeto anterior) |  |  | 23 | 2.05 | 82 | 2025-01-10: #REF!; 2025-01-17: #REF!
INSTRUMENT_COD_SOC | 3.1. | INSTRUMENT | COD_SOC |  |  | 0.0875 | 3.5 | 2025-01-10: 0.4375
INSTRUMENT_SUBPORTFOLIO_ID | 3.2. | INSTRUMENT | SUBPORTFOLIO_ID |  |  | 0.0875 | 3.5 | 2025-01-10: 0.4375
INSTRUMENT_DT_RFRNC | 3.3. | INSTRUMENT | DT_RFRNC |  |  | 0.0875 | 3.5 | 2025-01-10: 0.4375
INSTRUMENT_DFLT_STTS_INSTRMNT | 3.4. | INSTRUMENT | DFLT_STTS_INSTRMNT |  |  | 0.0875 | 3.5 | 2025-01-10: 0.4375
INSTRUMENT_IMPRMNT_STTS | 3.5. | INSTRUMENT | IMPRMNT_STTS |  |  | 0.0875 | 3.5 | 2025-01-10: #REF!; 2025-01-17: #REF!
INSTRUMENT_PRFRMNG_STTS | 3.6. | INSTRUMENT | PRFRMNG_STTS |  |  | 0.0875 | 3.5 | 2025-01-17: 0.4375
INSTRUMENT_TYP_INSTRMNT | 3.7. | INSTRUMENT | TYP_INSTRMNT |  |  | 0.0875 | 3.5 | 2025-01-17: 0.4375
INSTRUMENT_GRSS_CRRYNG_AMNT_INSTRMNT | 3.8. | INSTRUMENT | GRSS_CRRYNG_AMNT_INSTRMNT |  |  | 0.0875 | 3.5 | 2025-01-17: 0.4375
INSTRUMENT_ACCMLTD_CHNGS_FV_CR_INSTRMNT | 3.9. | INSTRUMENT | ACCMLTD_CHNGS_FV_CR_INSTRMNT |  |  | 0.0875 | 3.5 | 2025-01-17: 0.4375
INSTRUMENT_ACCNTNG_CLSSFCTN | 3.10. | INSTRUMENT | ACCNTNG_CLSSFCTN |  |  | 0.0875 | 3.5 | 2025-01-17: 0.4375
INSTRUMENT_OFF_BLNC_SHT_AMNT_INSTRMNT | 3.11. | INSTRUMENT | OFF_BLNC_SHT_AMNT_INSTRMNT |  |  | 0.0875 | 3.5 | 2025-01-17: 0.4375
INSTRUMENT_PRVSNS_OFF_BLNC_SHT | 3.12. | INSTRUMENT | PRVSNS_OFF_BLNC_SHT |  |  | 0.0875 | 3.5 | 2025-01-17: 0.4375
INSTRUMENT_RWA | 3.13. | INSTRUMENT | RWA |  |  | 0.0875 | 3.5 | 2025-01-17: 0.4375
INSTRUMENT_ACCMLTD_IMPRMNT_INSTRMNT | 3.14. | INSTRUMENT | ACCMLTD_IMPRMNT_INSTRMNT |  |  | 0.0875 | 3.5 | 2025-01-17: 0.4375
INSTRUMENT_COD_SOC_INTRGRP | 3.15. | INSTRUMENT | COD_SOC_INTRGRP |  |  | 0.0875 | 3.5 | 2025-01-17: 0.4375
INSTRUMENT_LCL_INSTMRNT_ID | 3.16. | INSTRUMENT | LCL_INSTMRNT_ID |  |  | 0.0875 | 3.5 | 2025-01-17: 0.4375
INSTRUMENT_FLG_INTRBSNSS | 3.17. | INSTRUMENT | FLG_INTRBSNSS |  |  | 0.1 | 4 | 2025-01-17: 0.5
INSTRUMENT_INTRBSNSS_ADJ_COD | 3.18. | INSTRUMENT | INTRBSNSS_ADJ_COD |  |  | 0.1 | 4 | 2025-01-17: 0.5
INSTRUMENT_COD_SOC_DSTNTN | 3.19. | INSTRUMENT | COD_SOC_DSTNTN |  |  | 0.0875 | 3.5 | 2025-01-17: 0.4375
INSTRUMENT_BSNSS_AREA_DSTNTN | 3.20. | INSTRUMENT | BSNSS_AREA_DSTNTN |  |  | 0.1 | 4 | 2025-01-17: 0.5
INSTRUMENT_INTRNL_TRNSFR_RT_OFF_BLNC | 3.21. | INSTRUMENT | INTRNL_TRNSFR_RT_OFF_BLNC |  |  | 0.0875 | 3.5 | 2025-01-17: 0.4375
INSTRUMENT_IDCMB | 3.22. | INSTRUMENT | IDCMB |  |  | 0.0875 | 3.5 | 2025-01-17: 0.4375
INSTRUMENT_RWA_OFF_BLNC | 3.23. | INSTRUMENT | RWA_OFF_BLNC |  |  | 0.0875 | 3.5 | 2025-01-17: 0.4375
| 4. | Re-especificações e especificação de novos requisitos |  |  | 14 | #REF! | #REF! | 2025-01-17: #REF!; 2025-01-24: #REF!
INSTRUMENT_CCF | 4.1. | INSTRUMENT | CCF |  |  | #REF! | #REF! | 2025-01-17: #REF!
INSTRUMENT_EAD | 4.2. | INSTRUMENT | EAD |  |  | #REF! | #REF! | 2025-01-17: #REF!
INSTRUMENT_TYP_OFF_BLNC_PRDCT | 4.3. | INSTRUMENT | TYP_OFF_BLNC_PRDCT |  |  | #REF! | #REF! | 2025-01-17: #REF!
INSTR_PROTECTION_COD_SOC | 4.4. | INSTR_PROTECTION | COD_SOC |  |  | #REF! | #REF! | 2025-01-17: #REF!
INSTR_PROTECTION_DT_RFRNC | 4.5. | INSTR_PROTECTION | DT_RFRNC |  |  | #REF! | #REF! | 2025-01-17: #REF!
INSTR_PROTECTION_INSTRMNT_ID | 4.6. | INSTR_PROTECTION | INSTRMNT_ID |  |  | #REF! | #REF! | 2025-01-17: #REF!
INSTR_PROTECTION_PRTCTN_ID | 4.7. | INSTR_PROTECTION | PRTCTN_ID |  |  | #REF! | #REF! | 2025-01-17: #REF!
PROTECTION_COD_SOC | 4.8. | PROTECTION | COD_SOC |  |  | #REF! | #REF! | 2025-01-17: #REF!
PROTECTION_DT_RFRNC | 4.9. | PROTECTION | DT_RFRNC |  |  | #REF! | #REF! | 2025-01-17: #REF!
PROTECTION_PRTCTN_ID | 4.10 | PROTECTION | PRTCTN_ID |  |  | #REF! | #REF! | 2025-01-17: #REF!
PROTECTION_TYP_PRTCTN | 4.11. | PROTECTION | TYP_PRTCTN |  |  | #REF! | #REF! | 2025-01-17: #REF!
PROTECTION_PRTCTN_VL | 4.12. | PROTECTION | PRTCTN_VL |  |  | #REF! | #REF! | 2025-01-17: #REF!
PROTECTION_FLG_ELCTRC_VHCL | 4.13. | PROTECTION | FLG_ELCTRC_VHCL |  |  | #REF! | #REF! | 2025-01-17: #REF!
INSTR_ACTIVITY_PRCNTG_ACTVTY | 4.14. | INSTR_ACTIVITY | PRCNTG_ACTVTY |  |  | #REF! | #REF! | 2025-01-24: #REF!
| 5. | Testes/Re-testes às métricas do GD |  |  |  |  | #REF!
| 5.1. |  | Testes ao Universo |  | n.a. |  | 40 | 2025-01-24: #REF!
| 5.2. |  | Simulação/ Testes aos Campos |  | 45 |  | #REF! | 2025-01-24: #REF!; 2025-01-31: #REF!; 2025-02-07: #REF!; 2025-02-14: #REF!; 2025-02-21: #REF!; 2025-02-28: #REF!
INSTRUMENT_INSTRMNT_ID | 5.2.1 | INSTRUMENT | INSTRMNT_ID |  |  |  | #REF! | 2025-01-24: #REF!
INSTRUMENT_CCF | 5.2.2. | INSTRUMENT | CCF |  |  |  | #REF! | 2025-01-24: #REF!
INSTRUMENT_EAD | 5.2.3. | INSTRUMENT | EAD |  |  |  | #REF! | 2025-01-24: #REF!
INSTRUMENT_AVRG_BLNC | 5.2.4. | INSTRUMENT | AVRG_BLNC |  |  |  | #REF! | 2025-01-24: #REF!
INSTRUMENT_NW_BSNSS | 5.2.5. | INSTRUMENT | NW_BSNSS |  |  |  | #REF! | 2025-01-24: #REF!; 2025-01-31: #REF!
INSTRUMENT_GRSS_INTRST_INCM | 5.2.6. | INSTRUMENT | GRSS_INTRST_INCM |  |  |  | #REF! | 2025-01-31: #REF!
INSTRUMENT_GRSS_CMMSSN_INCM | 5.2.7. | INSTRUMENT | GRSS_CMMSSN_INCM |  |  |  | #REF! | 2025-01-31: #REF!
INSTRUMENT_INTRNL_TRNSFR_RT | 5.2.8. | INSTRUMENT | INTRNL_TRNSFR_RT |  |  |  | #REF! | 2025-01-31: #REF!
INSTRUMENT_NT_LN_LSS_PRVSN | 5.2.9. | INSTRUMENT | NT_LN_LSS_PRVSN |  |  |  | #REF! | 2025-01-31: #REF!
INSTRUMENT_BSNSS_AREA | 5.2.10. | INSTRUMENT | BSNSS_AREA |  |  |  | #REF! | 2025-01-31: #REF!; 2025-02-07: #REF!
INSTRUMENT_MNGMNT_PRDCT | 5.2.11. | INSTRUMENT | MNGMNT_PRDCT |  |  |  | #REF! | 2025-02-07: #REF!
INSTRUMENT_GRSS_CMMSSN_EXPNS | 5.2.12. | INSTRUMENT | GRSS_CMMSSN_EXPNS |  |  |  | #REF! | 2025-02-07: #REF!
INSTRUMENT_GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | 5.2.13. | INSTRUMENT | GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS |  |  |  | #REF! | 2025-02-07: #REF!
INSTRUMENT_AVRG_BLNC_OFF_BLNC | 5.2.14. | INSTRUMENT | AVRG_BLNC_OFF_BLNC |  |  |  | #REF! | 2025-02-07: #REF!
INSTRUMENT_GRSS_CMMSSN_INCM_OFF_BLNC | 5.2.15. | INSTRUMENT | GRSS_CMMSSN_INCM_OFF_BLNC |  |  |  | #REF! | 2025-02-07: #REF!
INSTRUMENT_GRSS_CMMSSN_EXPNS_OFF_BLNC | 5.2.16. | INSTRUMENT | GRSS_CMMSSN_EXPNS_OFF_BLNC |  |  |  | #REF! | 2025-02-07: #REF!; 2025-02-14: #REF!
INSTRUMENT_GRSS_INTRST_EXPNS | 5.2.17. | INSTRUMENT | GRSS_INTRST_EXPNS |  |  |  | #REF! | 2025-02-14: #REF!
INSTRUMENT_NT_LN_LSS_PRVSN_OFF_BLNC | 5.2.18. | INSTRUMENT | NT_LN_LSS_PRVSN_OFF_BLNC |  |  |  | #REF! | 2025-02-14: #REF!
INSTRUMENT_GRSS_INTRST_INCM_CCRR | 5.2.19. | INSTRUMENT | GRSS_INTRST_INCM_CCRR |  |  |  | #REF! | 2025-02-14: #REF!
INSTRUMENT_GRSS_INTRST_EXPNS_CCRR | 5.2.20. | INSTRUMENT | GRSS_INTRST_EXPNS_CCRR |  |  |  | #REF! | 2025-02-14: #REF!
INSTRUMENT_GRSS_CMMSSN_INCM_CCRR | 5.2.21. | INSTRUMENT | GRSS_CMMSSN_INCM_CCRR |  |  |  | #REF! | 2025-02-14: #REF!
INSTRUMENT_GRSS_CMMSSN_EXPNS_CCRR | 5.2.22. | INSTRUMENT | GRSS_CMMSSN_EXPNS_CCRR |  |  |  | #REF! | 2025-02-14: #REF!
INSTRUMENT_GNS_FNNCL_TRNSCTN_EXCHNG_CCRR | 5.2.23. | INSTRUMENT | GNS_FNNCL_TRNSCTN_EXCHNG_CCRR |  |  |  | #REF! | 2025-02-14: #REF!
INSTRUMENT_BSNSS_AREA_CCRR | 5.2.24. | INSTRUMENT | BSNSS_AREA_CCRR |  |  |  | #REF! | 2025-02-14: #REF!
INSTRUMENT_GRSS_CMMSSN_INCM_OFF_BLNC_CCRR | 5.2.25. | INSTRUMENT | GRSS_CMMSSN_INCM_OFF_BLNC_CCRR |  |  |  | #REF! | 2025-02-14: #REF!
INSTRUMENT_GRSS_CMMSSN_EXPNS_OFF_BLNC_CCRR | 5.2.26. | INSTRUMENT | GRSS_CMMSSN_EXPNS_OFF_BLNC_CCRR |  |  |  | #REF! | 2025-02-14: #REF!
INSTRUMENT_CNCLLD_INSTRMNT_STTS | 5.2.27. | INSTRUMENT | CNCLLD_INSTRMNT_STTS |  |  |  | #REF! | 2025-02-21: #REF!
INSTRUMENT_TYP_OFF_BLNC_PRDCT | 5.2.28. | INSTRUMENT | TYP_OFF_BLNC_PRDCT |  |  |  | #REF! | 2025-02-21: #REF!
INSTR_PROTECTION_COD_SOC | 5.2.29. | INSTR_PROTECTION | COD_SOC |  |  |  | #REF! | 2025-02-21: #REF!
INSTR_PROTECTION_DT_RFRNC | 5.2.30. | INSTR_PROTECTION | DT_RFRNC |  |  |  | #REF! | 2025-02-21: #REF!
INSTR_PROTECTION_INSTRMNT_ID | 5.2.31. | INSTR_PROTECTION | INSTRMNT_ID |  |  |  | #REF! | 2025-02-21: #REF!
INSTR_PROTECTION_PRTCTN_ID | 5.2.32. | INSTR_PROTECTION | PRTCTN_ID |  |  |  | #REF! | 2025-02-21: #REF!
INSTR_PROTECTION_TYP_RLTN | 5.2.33. | INSTR_PROTECTION | TYP_RLTN |  |  |  | #REF! | 2025-02-21: #REF!
PROTECTION_COD_SOC | 5.2.34. | PROTECTION | COD_SOC |  |  |  | #REF! | 2025-02-21: #REF!
PROTECTION_DT_RFRNC | 5.2.35. | PROTECTION | DT_RFRNC |  |  |  | #REF! | 2025-02-21: #REF!
PROTECTION_PRTCTN_ID | 5.2.36. | PROTECTION | PRTCTN_ID |  |  |  | #REF! | 2025-02-21: #REF!
PROTECTION_TYP_PRTCTN | 5.2.37. | PROTECTION | TYP_PRTCTN |  |  |  | #REF! | 2025-02-21: #REF!
PROTECTION_PRTCTN_VL | 5.2.38. | PROTECTION | PRTCTN_VL |  |  |  | #REF! | 2025-02-21: #REF!
PROTECTION_FLG_ELCTRC_VHCL | 5.2.39. | PROTECTION | FLG_ELCTRC_VHCL |  |  |  | #REF! | 2025-02-21: #REF!
INSTR_ACTIVITY_COD_SOC | 5.2.40. | INSTR_ACTIVITY | COD_SOC |  |  |  | #REF! | 2025-02-21: #REF!
INSTR_ACTIVITY_DT_RFRNC | 5.2.41. | INSTR_ACTIVITY | DT_RFRNC |  |  |  | #REF! | 2025-02-21: #REF!
INSTR_ACTIVITY_INSTRMNT_ID | 5.2.42. | INSTR_ACTIVITY | INSTRMNT_ID |  |  |  | #REF! | 2025-02-21: #REF!
INSTR_ACTIVITY_SSTNBL_CTGRY | 5.2.43. | INSTR_ACTIVITY | SSTNBL_CTGRY |  |  |  | #REF! | 2025-02-21: #REF!; 2025-02-28: #REF!
INSTR_ACTIVITY_PRCNTG_ACTVTY | 5.2.44. | INSTR_ACTIVITY | PRCNTG_ACTVTY |  |  |  | #REF! | 2025-02-28: #REF!
INSTR_ACTIVITY_SSTNBL_INDCTR | 5.2.45. | INSTR_ACTIVITY | SSTNBL_INDCTR |  |  |  | #REF! | 2025-02-28: #REF!
| 5.3 |  | Re-testes |  |  |  | #REF! | 2025-02-28: #REF!; 2025-03-07: #REF!
| 6. | Documentação |  |  |  |  | 80 | 2025-03-07: #REF!; 2025-03-14: #REF!

## Lista - Âmbito Projeto GD
&
| DEZEMBRO |  |  |  | ESTR | GD | PILAR3 | GFINANCE | ESG_RISKS | LF | Comparação com lista ATUAL | [9 empty] | Comparação com lista ATUAL | [6 empty] | Estimativas
ID Data field / Field order | CONCAT | Table | Data field | Field name | Structural ECB Loan Tape | Green Dashboard | Pillar III ESG | Green Finance | ESG Risks | Leveraged Finance | ATUAL_Structural ECB Loan Tape | val_ESTR | ATUAL_Green Dashboard | val_GD | ATUAL_Pillar III ESG | val_PILAR3 | ATUAL_Green Finance | ATUAL_ESG Risks | val_ESG_RISKS | ATUAL_Leveraged Finance | Fonte manual LF | Status Data Lake | Status Data Lake (Detalhe) | AMBITO | STATUS | Est anterior | format | Complexidade (todos) | Especificação | Simulação | 2. Testes comparativos | Complexidade (code list) | 3. Val. Code List | 4. Val. Formatos | 5. Val.Controlos Corp. | Total Testes | Observações
IN.001 | INSTRUMENT_COD_SOC | INSTRUMENT | COD_SOC | Entity code of the informing society. | Y | Y | Y | N | Y | Y | Y | Igual | Y | Igual | Y | Igual | n/a | Y | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | VARCHAR2(5) | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IN.002 | INSTRUMENT_SUBPORTFOLIO_ID | INSTRUMENT | SUBPORTFOLIO_ID | Subportfolio ID | Y | Y | Y | N | Y | Y | Y | Igual | Y | Igual | Y | Igual | n/a | Y | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | Code List | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IN.007 | INSTRUMENT_DT_RFRNC | INSTRUMENT | DT_RFRNC | Reference date | Y | Y | Y | N | Y | Y | Y | Igual | Y | Igual | Y | Igual | n/a | Y | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | DATE | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IN.008 | INSTRUMENT_INSTRMNT_ID | INSTRUMENT | INSTRMNT_ID | Instrument ID | Y | Y | Y | N | Y | Y | Y | Igual | Y | Igual | Y | Igual | n/a | Y | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Alta | VARCHAR2(60) | M. Alta | 0 | 8 | 3 | n.a. | 0 | 1 | 2 | 6
IN.020 | INSTRUMENT_DFLT_STTS_INSTRMNT | INSTRUMENT | DFLT_STTS_INSTRMNT | Default status of the instrument | Y | Y | Y | N | N | Y | Y | Igual | Y | Igual | Y | Igual | n/a | N | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | Code List | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | default
IN.034 | INSTRUMENT_IMPRMNT_STTS | INSTRUMENT | IMPRMNT_STTS | Impairment status | Y | Y | Y | N | N | Y | Y | Igual | Y | Igual | Y | Igual | n/a | N | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | Code List | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | mudança de fonte ifrs
IN.044 | INSTRUMENT_PRFRMNG_STTS | INSTRUMENT | PRFRMNG_STTS | Performing status | Y | Y | Y | N | N | Y | Y | Igual | Y | Igual | Y | Igual | n/a | N | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | Code List | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | mudança de fonte ifrs
IN.055 | INSTRUMENT_TYP_INSTRMNT | INSTRUMENT | TYP_INSTRMNT | Type of instrument | Y | Y | Y | N | N | Y | Y | Igual | Y | Igual | Y | Igual | n/a | N | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | Code List | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IN.060 | INSTRUMENT_GRSS_CRRYNG_AMNT_INSTRMNT | INSTRUMENT | GRSS_CRRYNG_AMNT_INSTRMNT | Gross carrying amount | Y | Y | Y | N | Y | Y | Y | Igual | Y | Igual | Y | Igual | n/a | Y | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | FLOAT 2 decimal places | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IN.061 | INSTRUMENT_ACCMLTD_CHNGS_FV_CR_INSTRMNT | INSTRUMENT | ACCMLTD_CHNGS_FV_CR_INSTRMNT | Accumulated changes in fair value due to credit risk | Y | Y | Y | N | N | N | Y | Igual | Y | Igual | Y | Igual | n/a | N | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | FLOAT 2 decimal places | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IN.062 | INSTRUMENT_ACCNTNG_CLSSFCTN | INSTRUMENT | ACCNTNG_CLSSFCTN | Accounting portfolio | Y | Y | Y | N | N | Y | Y | Igual | Y | Igual | Y | Igual | n/a | N | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | Code List | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IN.065 | INSTRUMENT_CCF | INSTRUMENT | CCF | Credit conversion factor (CCF) according to CRR | Y | Y | N | N | N | Y | Y | Igual | N | Diferente | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | ESTR & GD | Sem alteração | Baixa | FLOAT 6 decimal places | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IN.074 | INSTRUMENT_EAD | INSTRUMENT | EAD | Regulatory EAD | Y | Y | N | N | Y | Y | Y | Igual | N | Diferente | N | Igual | n/a | Y | Igual | n/a | N | n/a | n/a | ESG_RISKS & ESTR & GD | Novo Campo | Baixa | FLOAT 2 decimal places | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | Capital
IN.078 | INSTRUMENT_OFF_BLNC_SHT_AMNT_INSTRMNT | INSTRUMENT | OFF_BLNC_SHT_AMNT_INSTRMNT | Off-balance sheet amount | Y | Y | N | N | Y | Y | Y | Igual | Y | Igual | N | Igual | n/a | Y | Igual | n/a | N | n/a | n/a | ESG_RISKS & ESTR & GD | Novo Campo | Baixa | FLOAT 2 decimal places | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IN.082 | INSTRUMENT_PRVSNS_OFF_BLNC_SHT | INSTRUMENT | PRVSNS_OFF_BLNC_SHT | Provisions associated with off-balance sheet exposures | Y | Y | N | N | N | N | Y | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | ESTR & GD | Sem alteração | Baixa | FLOAT 2 decimal places | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IN.085 | INSTRUMENT_RWA | INSTRUMENT | RWA | RWA | Y | Y | N | N | N | Y | Y | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | ESTR & GD | Sem alteração | Baixa | FLOAT 2 decimal places | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | Capital
IN.088 | INSTRUMENT_ACCMLTD_IMPRMNT_INSTRMNT | INSTRUMENT | ACCMLTD_IMPRMNT_INSTRMNT | Sum of LLPs and other allowances | Y | Y | Y | N | N | Y | Y | Igual | Y | Igual | Y | Igual | n/a | N | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | FLOAT 2 decimal places | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IN.192 | INSTRUMENT_COD_SOC_INTRGRP | INSTRUMENT | COD_SOC_INTRGRP | Cargabal identification code of the intragroup exposure | Y | Y | N | N | N | N | Y | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | ESTR & GD | Sem alteração | Baixa | VARCHAR2(5) | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IN.193 | INSTRUMENT_LCL_INSTMRNT_ID | INSTRUMENT | LCL_INSTMRNT_ID | Local Instrument ID | Y | Y | Y | N | N | N | Y | Igual | Y | Igual | Y | Igual | n/a | N | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | VARCHAR2(60) | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IN.196 | INSTRUMENT_AVRG_BLNC | INSTRUMENT | AVRG_BLNC | Average balance | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Média | FLOAT 2 decimal places | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5
IN.197 | INSTRUMENT_NW_BSNSS | INSTRUMENT | NW_BSNSS | New Business | N | Y | Y | N | N | N | N | Igual | Y | Igual | N | Diferente | n/a | N | Igual | n/a | N | n/a | n/a | GD & PILAR3 | Novo Campo | Média | Y, N | M. Alta | 0 | 8 | 3 | M. Alta | 1 | 1 | 2 | 7
IN.198 | INSTRUMENT_GRSS_INTRST_INCM | INSTRUMENT | GRSS_INTRST_INCM | Gross Interest income before distribution to SCIB under the Collabotarion Revenues distribution agreement | N | Y | Y | N | N | N | N | Igual | Y | Igual | Y | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD & PILAR3 | Sem alteração | Alta | FLOAT 2 decimal places | Alta | 0 | 6 | 6 | n.a. | 0 | 0.5 | 1 | 7.5
IN.199 | INSTRUMENT_GRSS_CMMSSN_INCM | INSTRUMENT | GRSS_CMMSSN_INCM | Gross fee and commission income before distribution to SCIB under the Collabotarion Revenues distribution agreement | N | Y | Y | N | N | N | N | Igual | Y | Igual | Y | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD & PILAR3 | Sem alteração | Alta | FLOAT 2 decimal places | Alta | 0 | 6 | 6 | n.a. | 0 | 0.5 | 1 | 7.5
IN.200 | INSTRUMENT_INTRNL_TRNSFR_RT | INSTRUMENT | INTRNL_TRNSFR_RT | Internal transfer rate amount | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Alta | FLOAT 2 decimal places | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5
IN.201 | INSTRUMENT_NT_LN_LSS_PRVSN | INSTRUMENT | NT_LN_LSS_PRVSN | Net loan-loss provisions | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Média | FLOAT 2 decimal places | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5
IN.202 | INSTRUMENT_BSNSS_AREA | INSTRUMENT | BSNSS_AREA | Business Area | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Alta | Code List | Alta | 0 | 6 | 6 | Alta | 0.5 | 0.5 | 1 | 8
IN.203 | INSTRUMENT_MNGMNT_PRDCT | INSTRUMENT | MNGMNT_PRDCT | Management Product | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Média | Code List | Alta | 0 | 6 | 6 | Alta | 0.5 | 0.5 | 1 | 8
IN.204 | INSTRUMENT_GRSS_CMMSSN_EXPNS | INSTRUMENT | GRSS_CMMSSN_EXPNS | Gross fee and commission expense before distribution to SCIB under the Collabotarion Revenues distribution agreement | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Alta | FLOAT 2 decimal places | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5
IN.205 | INSTRUMENT_GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | INSTRUMENT | GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | Gains (Losses) On Financial Transaction (gft) And Exchange Differences, before distribution to SCIB under the Collabotarion Revenues distribution agreement | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Alta | FLOAT 2 decimal places | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5
IN.206 | INSTRUMENT_FLG_INTRBSNSS | INSTRUMENT | FLG_INTRBSNSS | Flag of interbusiness | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Baixa | Y, N | M. Baixa | 0 | 1 | 1 | M. Baixa | 0.5 | 0.5 | 1 | 3
IN.207 | INSTRUMENT_INTRBSNSS_ADJ_COD | INSTRUMENT | INTRBSNSS_ADJ_COD | Interbusiness adjustment code | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Baixa | Code List | M. Baixa | 0 | 1 | 1 | M. Baixa | 0.5 | 0.5 | 1 | 3
IN.208 | INSTRUMENT_COD_SOC_DSTNTN | INSTRUMENT | COD_SOC_DSTNTN | Cargabal identification code of the destination entity | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Baixa | VARCHAR2(5) | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IN.209 | INSTRUMENT_BSNSS_AREA_DSTNTN | INSTRUMENT | BSNSS_AREA_DSTNTN | Destination Business area | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Baixa | Code List | M. Baixa | 0 | 1 | 1 | M. Baixa | 0.5 | 0.5 | 1 | 3
IN.210 | INSTRUMENT_AVRG_BLNC_OFF_BLNC | INSTRUMENT | AVRG_BLNC_OFF_BLNC | Average off balance | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Média | FLOAT 2 decimal places | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5
IN.211 | INSTRUMENT_INTRNL_TRNSFR_RT_OFF_BLNC | INSTRUMENT | INTRNL_TRNSFR_RT_OFF_BLNC | Internal transfer rate due to off balance amounts | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Baixa | FLOAT 2 decimal places | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IN.212 | INSTRUMENT_GRSS_CMMSSN_INCM_OFF_BLNC | INSTRUMENT | GRSS_CMMSSN_INCM_OFF_BLNC | Gross fee and commission income corresponding to off balance product before distribution to SCIB under the Collabotarion Revenues distribution agreement | N | Y | Y | N | N | N | N | Igual | Y | Igual | Y | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD & PILAR3 | Sem alteração | Alta | FLOAT 2 decimal places | Alta | 0 | 6 | 6 | n.a. | 0 | 0.5 | 1 | 7.5
IN.213 | INSTRUMENT_GRSS_CMMSSN_EXPNS_OFF_BLNC | INSTRUMENT | GRSS_CMMSSN_EXPNS_OFF_BLNC | Gross fee and commission expense corresponding to off balance product before distribution to SCIB under the Collabotarion Revenues distribution agreement | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Alta | FLOAT 2 decimal places | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5
IN.214 | INSTRUMENT_RWA_OFF_BLNC | INSTRUMENT | RWA_OFF_BLNC | RWA Off Balance | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Baixa | FLOAT 2 decimal places | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IN.215 | INSTRUMENT_GRSS_INTRST_EXPNS | INSTRUMENT | GRSS_INTRST_EXPNS | Gross Interest expense before distribution to SCIB under the Collabotarion Revenues distribution agreement | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Alta | FLOAT 2 decimal places | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5
IN.216 | INSTRUMENT_NT_LN_LSS_PRVSN_OFF_BLNC | INSTRUMENT | NT_LN_LSS_PRVSN_OFF_BLNC | Net loan-loss provisions corresponding to off balance exposures | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Média | FLOAT 2 decimal places | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5
IN.217 | INSTRUMENT_GRSS_INTRST_INCM_CCRR | INSTRUMENT | GRSS_INTRST_INCM_CCRR | Gross Interest income distributed to SCIB under the Collabotarion Revenues distribution agreement | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Baixa | FLOAT 2 decimal places | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5
IN.218 | INSTRUMENT_GRSS_INTRST_EXPNS_CCRR | INSTRUMENT | GRSS_INTRST_EXPNS_CCRR | Gross Interest expense distributed to SCIB under the Collabotarion Revenues distribution agreement | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Baixa | FLOAT 2 decimal places | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5
IN.219 | INSTRUMENT_GRSS_CMMSSN_INCM_CCRR | INSTRUMENT | GRSS_CMMSSN_INCM_CCRR | Gross fee and commission income distributed to SCIB under the Collabotarion Revenues distribution agreement | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Baixa | FLOAT 2 decimal places | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5
IN.220 | INSTRUMENT_GRSS_CMMSSN_EXPNS_CCRR | INSTRUMENT | GRSS_CMMSSN_EXPNS_CCRR | Gross fee and commission expense distributed to SCIB under the Collabotarion Revenues distribution agreement | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Baixa | FLOAT 2 decimal places | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5
IN.221 | INSTRUMENT_GNS_FNNCL_TRNSCTN_EXCHNG_CCRR | INSTRUMENT | GNS_FNNCL_TRNSCTN_EXCHNG_CCRR | Gains (Losses) On Financial Transaction (gft) And Exchange Differences distributed to SCIB under the Collabotarion Revenues distribution agreement | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Baixa | FLOAT 2 decimal places | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5
IN.222 | INSTRUMENT_BSNSS_AREA_CCRR | INSTRUMENT | BSNSS_AREA_CCRR | Business Area related to CIB | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Baixa | Code List | Média | 0 | 3 | 3 | Média | 0.5 | 0.5 | 1 | 5
IN.223 | INSTRUMENT_GRSS_CMMSSN_INCM_OFF_BLNC_CCRR | INSTRUMENT | GRSS_CMMSSN_INCM_OFF_BLNC_CCRR | Gross fee and commission income corresponding to off balance product distributed to SCIB under the Collabotarion Revenues distribution agreement | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Baixa | FLOAT 2 decimal places | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5
IN.224 | INSTRUMENT_GRSS_CMMSSN_EXPNS_OFF_BLNC_CCRR | INSTRUMENT | GRSS_CMMSSN_EXPNS_OFF_BLNC_CCRR | Gross fee and commission expense corresponding to off balance product distributed to SCIB under the Collabotarion Revenues distribution agreement | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Baixa | FLOAT 2 decimal places | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5
IN.233 | INSTRUMENT_CNCLLD_INSTRMNT_STTS | INSTRUMENT | CNCLLD_INSTRMNT_STTS | Cancelled instrument status | N | Y | N | N | N | N | N | Igual | Y | Igual | N | Igual | n/a | N | Igual | n/a | N | n/a | n/a | GD | Sem alteração | Alta | Code List | Média | 0 | 3 | 3 | Média | 0.5 | 0.5 | 1 | 5
IN.234 | INSTRUMENT_IDCMB | INSTRUMENT | IDCMB | IDCOMB | Y | Y | Y | N | Y | Y | Y | Igual | Y | Igual | Y | Igual | n/a | Y | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | VARCHAR2(255) | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | Contabilidade
IN.247 | INSTRUMENT_TYP_OFF_BLNC_PRDCT | INSTRUMENT | TYP_OFF_BLNC_PRDCT | Type of off balance product | Y | Y | Y | N | N | Y | Novo | Novo Campo | Novo | Novo Campo | Novo | Novo Campo | n/a | Novo | Novo Campo | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Novo Campo | Média | Code List | M. Baixa | 1 | 1 | 1 | M. Baixa | 0.5 | 0.5 | 1 | 3
IP.001 | INSTR_PROTECTION_COD_SOC | INSTR_PROTECTION | COD_SOC | Entity code of the informing society. | Y | Y | Y | N | N | N | Y | Igual | N | Diferente | Y | Igual | n/a | N | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | VARCHAR2(5) | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IP.002 | INSTR_PROTECTION_DT_RFRNC | INSTR_PROTECTION | DT_RFRNC | Reference date | Y | Y | Y | N | N | N | Y | Igual | N | Diferente | Y | Igual | n/a | N | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | DATE | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IP.003 | INSTR_PROTECTION_INSTRMNT_ID | INSTR_PROTECTION | INSTRMNT_ID | Instrument ID | Y | Y | Y | N | N | N | Y | Igual | N | Diferente | Y | Igual | n/a | N | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | VARCHAR2(60) | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IP.004 | INSTR_PROTECTION_PRTCTN_ID | INSTR_PROTECTION | PRTCTN_ID | Protection ID | Y | Y | Y | N | N | N | Y | Igual | N | Diferente | Y | Igual | n/a | N | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | VARCHAR2(60) | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
IP.007 | INSTR_PROTECTION_TYP_RLTN | INSTR_PROTECTION | TYP_RLTN | Type of relation | N | Y | Y | N | N | N | Novo | Novo Campo | Novo | Novo Campo | Novo | Novo Campo | n/a | Novo | Novo Campo | n/a | N | n/a | n/a | GD & PILAR3 | Novo Campo | Alta | Code List | M. Baixa | 0 | 1 | 1 | M. Baixa | 0.5 | 0.5 | 1 | 3
PR.001 | PROTECTION_COD_SOC | PROTECTION | COD_SOC | Entity code of the informing society. | Y | Y | Y | N | Y | N | Y | Igual | N | Diferente | Y | Igual | n/a | Y | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | VARCHAR2(5) | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
PR.003 | PROTECTION_DT_RFRNC | PROTECTION | DT_RFRNC | Reference date | Y | Y | Y | N | Y | N | Y | Igual | N | Diferente | Y | Igual | n/a | Y | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | DATE | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
PR.005 | PROTECTION_PRTCTN_ID | PROTECTION | PRTCTN_ID | Protection ID | Y | Y | Y | N | Y | N | Y | Igual | N | Diferente | Y | Igual | n/a | Y | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | VARCHAR2(60) | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
PR.014 | PROTECTION_TYP_PRTCTN | PROTECTION | TYP_PRTCTN | Protection type | Y | Y | Y | N | Y | N | Y | Igual | N | Diferente | Y | Igual | n/a | Y | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | Code List | M. Baixa | 1 | 1 | 1 | M. Baixa | 0.5 | 0.5 | 1 | 3
PR.024 | PROTECTION_PRTCTN_VL | PROTECTION | PRTCTN_VL | Appraised market value | Y | Y | Y | N | N | N | Y | Igual | N | Diferente | Y | Igual | n/a | N | Igual | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Sem alteração | Baixa | FLOAT 2 decimal places | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
PR.076 | PROTECTION_FLG_ELCTRC_VHCL | PROTECTION | FLG_ELCTRC_VHCL | Flag of electric vehicle | N | Y | N | N | N | N | Novo | Novo Campo | Novo | Novo Campo | Novo | Novo Campo | n/a | Novo | Novo Campo | n/a | N | n/a | n/a | GD | Novo Campo | Alta | Y, N | Baixa | 2 | 1.5 | 1.5 | Baixa | 0.5 | 0.5 | 1 | 3.5
AC.001 | INSTR_ACTIVITY_COD_SOC | INSTR_ACTIVITY | COD_SOC | Entity code of the informing society. | N | Y | Y | N | N | N | Novo | Novo Campo | Novo | Novo Campo | Novo | Novo Campo | n/a | Novo | Novo Campo | n/a | N | n/a | n/a | GD & PILAR3 | Nova Tabela | Média | VARCHAR2(5) | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
AC.002 | INSTR_ACTIVITY_DT_RFRNC | INSTR_ACTIVITY | DT_RFRNC | Reference date | N | Y | Y | N | N | N | Novo | Novo Campo | Novo | Novo Campo | Novo | Novo Campo | n/a | Novo | Novo Campo | n/a | N | n/a | n/a | GD & PILAR3 | Nova Tabela | Baixa | DATE | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
AC.003 | INSTR_ACTIVITY_INSTRMNT_ID | INSTR_ACTIVITY | INSTRMNT_ID | Instrument ID | N | Y | Y | N | N | N | Novo | Novo Campo | Novo | Novo Campo | Novo | Novo Campo | n/a | Novo | Novo Campo | n/a | N | n/a | n/a | GD & PILAR3 | Nova Tabela | Média | VARCHAR2(60) | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5
AC.004 | INSTR_ACTIVITY_SSTNBL_CTGRY | INSTR_ACTIVITY | SSTNBL_CTGRY | Sustainable Category Green (specific purpose) and General (general purpose) | N | Y | Y | N | N | N | Novo | Novo Campo | Novo | Novo Campo | Novo | Novo Campo | n/a | Novo | Novo Campo | n/a | N | n/a | n/a | GD & PILAR3 | Nova Tabela - Campo existente | Alta | Code List | Baixa | 0 | 1.5 | 1.5 | Baixa | 0.5 | 0.5 | 1 | 3.5
AC.005 | INSTR_ACTIVITY_PRCNTG_ACTVTY | INSTR_ACTIVITY | PRCNTG_ACTVTY | Percentage of UoP | Y | Y | Y | N | N | N | Novo | Novo Campo | Novo | Novo Campo | Novo | Novo Campo | n/a | Novo | Novo Campo | n/a | N | n/a | n/a | ESTR & GD & PILAR3 | Nova Tabela | Baixa | FLOAT 6 decimal places | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | MV
AC.008 | INSTR_ACTIVITY_SSTNBL_INDCTR | INSTR_ACTIVITY | SSTNBL_INDCTR | Sustainable Indicator | N | Y | Y | N | N | N | Novo | Novo Campo | Novo | Novo Campo | Novo | Novo Campo | n/a | Novo | Novo Campo | n/a | N | n/a | n/a | GD & PILAR3 | Nova Tabela - Campo existente | Alta | Code List | Baixa | 0 | 1.5 | 1.5 | Baixa | 0.5 | 0.5 | 1 | 3.5

## Aux
|  |  |  | 527 |  | 15 | 178.5 | [5 empty] | 285.5 |  | 527 | 364 | 163
CONCAT | Table | Data field | Est anterior | Est anterior | Complexidade (todos) | Especificação | Simulação | 2. Testes comparativos | Complexidade (code list) | 3. Val. Code List | 4. Val. Formatos | 5. Val.Controlos Corp. | Total Testes | Cenário | Tempo SC1 | Tempo SC B1 | Tempo SC B2 | Flg Concluído
INSTRUMENT_COD_SOC | INSTRUMENT | COD_SOC | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_SUBPORTFOLIO_ID | INSTRUMENT | SUBPORTFOLIO_ID | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_DT_RFRNC | INSTRUMENT | DT_RFRNC | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_INSTRMNT_ID | INSTRUMENT | INSTRMNT_ID | Alta | 25.2 | M. Alta | 0 | 12 | 3 | n.a. | 0 | 1 | 2 | 10 | SCA SCB1 | 25.2 | 25.2 | 0 | N
INSTRUMENT_DFLT_STTS_INSTRMNT | INSTRUMENT | DFLT_STTS_INSTRMNT | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_IMPRMNT_STTS | INSTRUMENT | IMPRMNT_STTS | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_PRFRMNG_STTS | INSTRUMENT | PRFRMNG_STTS | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_TYP_INSTRMNT | INSTRUMENT | TYP_INSTRMNT | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_GRSS_CRRYNG_AMNT_INSTRMNT | INSTRUMENT | GRSS_CRRYNG_AMNT_INSTRMNT | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_ACCMLTD_CHNGS_FV_CR_INSTRMNT | INSTRUMENT | ACCMLTD_CHNGS_FV_CR_INSTRMNT | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_ACCNTNG_CLSSFCTN | INSTRUMENT | ACCNTNG_CLSSFCTN | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_CCF | INSTRUMENT | CCF | Baixa | 2 | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | N
INSTRUMENT_EAD | INSTRUMENT | EAD | Baixa | 2 | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | N
INSTRUMENT_OFF_BLNC_SHT_AMNT_INSTRMNT | INSTRUMENT | OFF_BLNC_SHT_AMNT_INSTRMNT | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_PRVSNS_OFF_BLNC_SHT | INSTRUMENT | PRVSNS_OFF_BLNC_SHT | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_RWA | INSTRUMENT | RWA | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_ACCMLTD_IMPRMNT_INSTRMNT | INSTRUMENT | ACCMLTD_IMPRMNT_INSTRMNT | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_COD_SOC_INTRGRP | INSTRUMENT | COD_SOC_INTRGRP | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_LCL_INSTMRNT_ID | INSTRUMENT | LCL_INSTMRNT_ID | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_AVRG_BLNC | INSTRUMENT | AVRG_BLNC | Média | 9.1 | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5 | SCA SCB1 | 9.1 | 9.1 | 0 | N
INSTRUMENT_NW_BSNSS | INSTRUMENT | NW_BSNSS | Média | 10.1 | M. Alta | 0 | 8 | 3 | M. Alta | 1 | 1 | 2 | 7 | SCA SCB 2 | 10.1 | 0 | 10.1 | N
INSTRUMENT_GRSS_INTRST_INCM | INSTRUMENT | GRSS_INTRST_INCM | Alta | 18.1 | Alta | 0 | 8 | 6 | n.a. | 0 | 0.5 | 1 | 10 | SCA SCB 2 | 18.1 | 0 | 18.1 | N
INSTRUMENT_GRSS_CMMSSN_INCM | INSTRUMENT | GRSS_CMMSSN_INCM | Alta | 18.1 | Alta | 0 | 8 | 6 | n.a. | 0 | 0.5 | 1 | 10 | SCA SCB 2 | 18.1 | 0 | 18.1 | N
INSTRUMENT_INTRNL_TRNSFR_RT | INSTRUMENT | INTRNL_TRNSFR_RT | Alta | 18.1 | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5 | SCA SCB1 | 18.1 | 18.1 | 0 | N
INSTRUMENT_NT_LN_LSS_PRVSN | INSTRUMENT | NT_LN_LSS_PRVSN | Média | 9.1 | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5 | SCA SCB1 | 9.1 | 9.1 | 0 | N
INSTRUMENT_BSNSS_AREA | INSTRUMENT | BSNSS_AREA | Alta | 18.1 | M. Alta | 0 | 15 | 6 | Alta | 0.5 | 0.5 | 1 | 20 | SCA SCB1 | 18.1 | 18.1 | 0 | N
INSTRUMENT_MNGMNT_PRDCT | INSTRUMENT | MNGMNT_PRDCT | Média | 10.1 | Alta | 0 | 8 | 6 | Alta | 0.5 | 0.5 | 1 | 10 | SCA SCB1 | 10.1 | 10.1 | 0 | N
INSTRUMENT_GRSS_CMMSSN_EXPNS | INSTRUMENT | GRSS_CMMSSN_EXPNS | Alta | 18.1 | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5 | SCA SCB1 | 18.1 | 18.1 | 0 | N
INSTRUMENT_GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | INSTRUMENT | GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | Alta | 18.1 | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5 | SCA SCB1 | 18.1 | 18.1 | 0 | N
INSTRUMENT_FLG_INTRBSNSS | INSTRUMENT | FLG_INTRBSNSS | Baixa | 2 | M. Baixa | 0 | 1 | 1 | M. Baixa | 0.5 | 0.5 | 1 | 3 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_INTRBSNSS_ADJ_COD | INSTRUMENT | INTRBSNSS_ADJ_COD | Baixa | 2 | M. Baixa | 0 | 1 | 1 | M. Baixa | 0.5 | 0.5 | 1 | 3 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_COD_SOC_DSTNTN | INSTRUMENT | COD_SOC_DSTNTN | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_BSNSS_AREA_DSTNTN | INSTRUMENT | BSNSS_AREA_DSTNTN | Baixa | 2 | M. Baixa | 0 | 1 | 1 | M. Baixa | 0.5 | 0.5 | 1 | 3 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_AVRG_BLNC_OFF_BLNC | INSTRUMENT | AVRG_BLNC_OFF_BLNC | Média | 9.1 | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5 | SCA SCB1 | 9.1 | 9.1 | 0 | N
INSTRUMENT_INTRNL_TRNSFR_RT_OFF_BLNC | INSTRUMENT | INTRNL_TRNSFR_RT_OFF_BLNC | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_GRSS_CMMSSN_INCM_OFF_BLNC | INSTRUMENT | GRSS_CMMSSN_INCM_OFF_BLNC | Alta | 18.1 | Alta | 0 | 8 | 6 | n.a. | 0 | 0.5 | 1 | 10 | SCA SCB 2 | 18.1 | 0 | 18.1 | N
INSTRUMENT_GRSS_CMMSSN_EXPNS_OFF_BLNC | INSTRUMENT | GRSS_CMMSSN_EXPNS_OFF_BLNC | Alta | 18.1 | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5 | SCA SCB1 | 18.1 | 18.1 | 0 | N
INSTRUMENT_RWA_OFF_BLNC | INSTRUMENT | RWA_OFF_BLNC | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_GRSS_INTRST_EXPNS | INSTRUMENT | GRSS_INTRST_EXPNS | Alta | 18.1 | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5 | SCA SCB1 | 18.1 | 18.1 | 0 | N
INSTRUMENT_NT_LN_LSS_PRVSN_OFF_BLNC | INSTRUMENT | NT_LN_LSS_PRVSN_OFF_BLNC | Média | 9.1 | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5 | SCA SCB1 | 9.1 | 9.1 | 0 | N
INSTRUMENT_GRSS_INTRST_INCM_CCRR | INSTRUMENT | GRSS_INTRST_INCM_CCRR | Baixa | 2 | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5 | SCA SCB1 | 2 | 2 | 0 | N
INSTRUMENT_GRSS_INTRST_EXPNS_CCRR | INSTRUMENT | GRSS_INTRST_EXPNS_CCRR | Baixa | 2 | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5 | SCA SCB1 | 2 | 2 | 0 | N
INSTRUMENT_GRSS_CMMSSN_INCM_CCRR | INSTRUMENT | GRSS_CMMSSN_INCM_CCRR | Baixa | 2 | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5 | SCA SCB1 | 2 | 2 | 0 | N
INSTRUMENT_GRSS_CMMSSN_EXPNS_CCRR | INSTRUMENT | GRSS_CMMSSN_EXPNS_CCRR | Baixa | 2 | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5 | SCA SCB1 | 2 | 2 | 0 | N
INSTRUMENT_GNS_FNNCL_TRNSCTN_EXCHNG_CCRR | INSTRUMENT | GNS_FNNCL_TRNSCTN_EXCHNG_CCRR | Baixa | 2 | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5 | SCA SCB1 | 2 | 2 | 0 | N
INSTRUMENT_BSNSS_AREA_CCRR | INSTRUMENT | BSNSS_AREA_CCRR | Baixa | 2 | Média | 0 | 3 | 3 | Média | 0.5 | 0.5 | 1 | 5 | SCA SCB1 | 2 | 2 | 0 | N
INSTRUMENT_GRSS_CMMSSN_INCM_OFF_BLNC_CCRR | INSTRUMENT | GRSS_CMMSSN_INCM_OFF_BLNC_CCRR | Baixa | 2 | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5 | SCA SCB1 | 2 | 2 | 0 | N
INSTRUMENT_GRSS_CMMSSN_EXPNS_OFF_BLNC_CCRR | INSTRUMENT | GRSS_CMMSSN_EXPNS_OFF_BLNC_CCRR | Baixa | 2 | Média | 0 | 3 | 3 | n.a. | 0 | 0.5 | 1 | 4.5 | SCA SCB1 | 2 | 2 | 0 | N
INSTRUMENT_CNCLLD_INSTRMNT_STTS | INSTRUMENT | CNCLLD_INSTRMNT_STTS | Alta | 18.1 | Média | 0 | 3 | 3 | Média | 0.5 | 0.5 | 1 | 5 | SCA SCB1 | 18.1 | 18.1 | 0 | N
INSTRUMENT_IDCMB | INSTRUMENT | IDCMB | Baixa | 2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | Y
INSTRUMENT_TYP_OFF_BLNC_PRDCT | INSTRUMENT | TYP_OFF_BLNC_PRDCT | Média | 11.1 | M. Baixa | 1 | 1 | 1 | M. Baixa | 0.5 | 0.5 | 1 | 3 | SCA SCB1 | 11.1 | 11.1 | 0 | N
INSTR_PROTECTION_COD_SOC | INSTR_PROTECTION | COD_SOC | Baixa | 12.1 | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 12.1 | 12.1 | 0 | N
INSTR_PROTECTION_DT_RFRNC | INSTR_PROTECTION | DT_RFRNC | Baixa | 7 | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 7 | 7 | 0 | N
INSTR_PROTECTION_INSTRMNT_ID | INSTR_PROTECTION | INSTRMNT_ID | Baixa | 25.2 | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 25.2 | 25.2 | 0 | N
INSTR_PROTECTION_PRTCTN_ID | INSTR_PROTECTION | PRTCTN_ID | Baixa | 2 | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | N
INSTR_PROTECTION_TYP_RLTN | INSTR_PROTECTION | TYP_RLTN | Alta | 18.1 | M. Baixa | 0 | 1 | 1 | M. Baixa | 0.5 | 0.5 | 1 | 3 | SCA SCB 2 | 18.1 | 0 | 18.1 | N
PROTECTION_COD_SOC | PROTECTION | COD_SOC | Baixa | 12.1 | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 12.1 | 12.1 | 0 | N
PROTECTION_DT_RFRNC | PROTECTION | DT_RFRNC | Baixa | 7 | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 7 | 7 | 0 | N
PROTECTION_PRTCTN_ID | PROTECTION | PRTCTN_ID | Baixa | 2 | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 2 | 2 | 0 | N
PROTECTION_TYP_PRTCTN | PROTECTION | TYP_PRTCTN | Baixa | 1 | M. Baixa | 1 | 1 | 1 | M. Baixa | 0.5 | 0.5 | 1 | 3 | SCA SCB1 | 1 | 1 | 0 | N
PROTECTION_PRTCTN_VL | PROTECTION | PRTCTN_VL | Baixa | 1 | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 1 | 1 | 0 | N
PROTECTION_FLG_ELCTRC_VHCL | PROTECTION | FLG_ELCTRC_VHCL | Alta | 18.1 | Baixa | 2 | 1.5 | 1.5 | Baixa | 0.5 | 0.5 | 1 | 3.5 | SCA SCB1 | 18.1 | 18.1 | 0 | N
INSTR_ACTIVITY_COD_SOC | INSTR_ACTIVITY | COD_SOC | Média | 12.1 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB 2 | 12.1 | 0 | 12.1 | N
INSTR_ACTIVITY_DT_RFRNC | INSTR_ACTIVITY | DT_RFRNC | Baixa | 7 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB 2 | 7 | 0 | 7 | N
INSTR_ACTIVITY_INSTRMNT_ID | INSTR_ACTIVITY | INSTRMNT_ID | Média | 25.2 | M. Baixa | 0 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB 2 | 25.2 | 0 | 25.2 | N
INSTR_ACTIVITY_SSTNBL_CTGRY | INSTR_ACTIVITY | SSTNBL_CTGRY | Alta | 18.1 | Alta | 0 | 8 | 1.5 | Baixa | 0.5 | 0.5 | 1 | 10 | SCA SCB 2 | 18.1 | 0 | 18.1 | N
INSTR_ACTIVITY_PRCNTG_ACTVTY | INSTR_ACTIVITY | PRCNTG_ACTVTY | Baixa | 1 | M. Baixa | 1 | 1 | 1 | n.a. | 0 | 0.5 | 1 | 2.5 | SCA SCB1 | 1 | 1 | 0 | N
INSTR_ACTIVITY_SSTNBL_INDCTR | INSTR_ACTIVITY | SSTNBL_INDCTR | Alta | 18.1 | Alta | 0 | 8 | 1.5 | Baixa | 0.5 | 0.5 | 1 | 10 | SCA SCB 2 | 18.1 | 0 | 18.1 | N

## Férias
| F | Férias | [7 empty] | Saldo |  | por marcar |  |  | Aniversário
| F1 | Férias 2024 |  |  |  |  | Filipa Carreira |  |  | 2x |  | 2x |  |  | 2025-06-06
| A | Aniversário |  |  |  |  | Rita Matias |  |  | 26 |  | 22 |  |  | 2025-06-06
Fim de semana
Feriado
Janeiro
| 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | 2025-01-18 | 2025-01-19 | 2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-23 | 2025-01-24 | 2025-01-25 | 2025-01-26 | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31
Filipa Carreira
Rita Matias
Fevereiro
| 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28
Filipa Carreira | bar: 2025-02-28
Rita Matias
Março
| 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31
Filipa Carreira | bar: 2025-03-03 to 2025-03-07; 2025-03-10 to 2025-03-14
Rita Matias | bar: 2025-03-04