## 1. Tipologias Testes GD
| Âmbito | Origem | Campo | Status | Tipologia_Testes | Necessidade de re-especificação? (campo) | Complexidade | Estimação (horas) | Total Horas | Notas
| GD | - | n.a. |  | 1. Teste de universo | Sim | Alta | 8
| GD | Modelo Verde | SSTNBL_CTGRY | Concluído | 2. Simulação | Sim | Alta | 8
| GD | Modelo Verde | SSTNBL_CTGRY | Concluído | 3. Testes comparativos (Espec. VS Impl.) | Sim | Alta | 8
| GD | Modelo Verde | SSTNBL_CTGRY | Concluído | 4. Validação de parametrizações | Sim | Alta | 8 |  | Parametrização a ser implementada: lt803
| GD | Modelo Verde | SSTNBL_CTGRY | Concluído | 6. Validação de formatos | Sim | Alta | 1
| GD | Modelo Verde | SSTNBL_CTGRY | Concluído | 7. Validação de controlos corporativos | Sim | Alta | 2
| GD | LT ESTR | DFLT_STTS_INSTRMNT | Concluído | 5. Teste comparativos com LT | Não | Baixa | 1
| GD | LT ESTR | ACCMLTD_CHNGS_FV_CR_INSTRMNT | Concluído | 5. Teste comparativos com LT | Não | Baixa | 1
| GD | LT ESTR | ACCMLTD_IMPRMNT_INSTRMNT | Concluído | 5. Teste comparativos com LT | Não | Baixa | 1
| GD | LT ESTR | ACCNTNG_CLSSFCTN | Concluído | 5. Teste comparativos com LT | Não | Baixa | 1
| GD | LT ESTR | COD_SOC | Concluído | 5. Teste comparativos com LT | Não | Baixa | 1
| GD | LT ESTR | DT_RFRNC | Concluído | 5. Teste comparativos com LT | Não | Baixa | 1
| GD | LT ESTR | GRSS_CRRYNG_AMNT_INSTRMNT | Concluído | 5. Teste comparativos com LT | Não | Baixa | 1
| GD | LT ESTR | IDCMB | Concluído | 5. Teste comparativos com LT | Não | Baixa | 1
| GD | LT ESTR | IMPRMNT_STTS | Concluído | 5. Teste comparativos com LT | Não | Baixa | 1
| GD | Outro | INSTRMNT_ID | Em Teste | 2. Simulação | Sim | Alta | 4 |  | Pendente de Business_area; Campo já simulado
| GD | Outro | INSTRMNT_ID | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Sim | Alta | 8 |  | Pendente de Business_area
| GD | Outro | INSTRMNT_ID | Em Teste | 6. Validação de formatos | Sim | Alta | 1 |  | Pendente de Business_area
| GD | LT ESTR | LCL_INSTMRNT_ID | Concluído | 5. Teste comparativos com LT | Não | Baixa | 1
| GD | LT ESTR | OFF_BLNC_SHT_AMNT_INSTRMNT | Concluído | 5. Teste comparativos com LT | Não | Baixa | 1
| GD | LT ESTR | PRFRMNG_STTS | Concluído | 5. Teste comparativos com LT | Não | Baixa | 1
| GD | LT ESTR | PRVSNS_OFF_BLNC_SHT | Concluído | 5. Teste comparativos com LT | Não | Baixa | 1
| GD | LT ESTR | SUBPORTFOLIO_ID | Concluído | 5. Teste comparativos com LT | Não | Baixa | 1
| GD | LT ESTR | TYP_INSTRMNT | Concluído | 5. Teste comparativos com LT | Não | Baixa | 1
| GD | LT ESTR | RWA | Concluído | 5. Teste comparativos com LT | Não | Baixa | 1
| GD | LT ESTR | COD_SOC_INTRGRP | Concluído | 5. Teste comparativos com LT | Não | Baixa | 1
| GD | Corporativo | BSNSS_AREA_DSTNTN | Concluído | 2. Simulação | Não | Baixa | 2
| GD | Corporativo | BSNSS_AREA_DSTNTN | Concluído | 3. Testes comparativos (Espec. VS Impl.) | Não | Baixa | 2
| GD | Corporativo | BSNSS_AREA_DSTNTN | Concluído | 6. Validação de formatos | Não | Baixa | 1
| GD | Corporativo | BSNSS_AREA_DSTNTN | Concluído | 7. Validação de controlos corporativos | Não | Baixa | 2
| GD | Corporativo | FLG_INTRBSNSS | Concluído | 2. Simulação | Não | Baixa | 2
| GD | Corporativo | FLG_INTRBSNSS | Concluído | 3. Testes comparativos (Espec. VS Impl.) | Não | Baixa | 2
| GD | Corporativo | FLG_INTRBSNSS | Concluído | 6. Validação de formatos | Não | Baixa | 1
| GD | Corporativo | FLG_INTRBSNSS | Concluído | 7. Validação de controlos corporativos | Não | Baixa | 2
| GD | Corporativo | INTRBSNSS_ADJ_COD | Concluído | 2. Simulação | Não | Baixa | 2
| GD | Corporativo | INTRBSNSS_ADJ_COD | Concluído | 3. Testes comparativos (Espec. VS Impl.) | Não | Baixa | 2
| GD | Corporativo | INTRBSNSS_ADJ_COD | Concluído | 6. Validação de formatos | Não | Baixa | 1
| GD | Corporativo | INTRBSNSS_ADJ_COD | Concluído | 7. Validação de controlos corporativos | Não | Baixa | 2
| GD | Corporativo | COD_SOC_DSTNTN | Concluído | 2. Simulação | Não | Baixa | 2
| GD | Corporativo | COD_SOC_DSTNTN | Concluído | 3. Testes comparativos (Espec. VS Impl.) | Não | Baixa | 2
| GD | Corporativo | COD_SOC_DSTNTN | Concluído | 6. Validação de formatos | Não | Baixa | 1
| GD | Corporativo | COD_SOC_DSTNTN | Concluído | 7. Validação de controlos corporativos | Não | Baixa | 2
| GD | Corporativo | RWA_OFF_BLNC | Concluído | 2. Simulação | Não | Baixa | 2 |  | 27/03/2024 (Corp): Deve ser aprovisionado localmente com o valor correspondente de não aplicável (11111111111)
| GD | Corporativo | RWA_OFF_BLNC | Concluído | 3. Testes comparativos (Espec. VS Impl.) | Não | Baixa | 2 |  | 27/03/2024 (Corp): Deve ser aprovisionado localmente com o valor correspondente de não aplicável (11111111111)
| GD | Corporativo | RWA_OFF_BLNC | Concluído | 6. Validação de formatos | Não | Baixa | 1 |  | 27/03/2024 (Corp): Deve ser aprovisionado localmente com o valor correspondente de não aplicável (11111111111)
| GD | Corporativo | RWA_OFF_BLNC | Concluído | 7. Validação de controlos corporativos | Não | Baixa | 2 |  | 27/03/2024 (Corp): Deve ser aprovisionado localmente com o valor correspondente de não aplicável (11111111111)
| GD | Rentabilidade | INTRNL_TRNSFR_RT_OFF_BLNC | Concluído | 2. Simulação | Não | Baixa | 2 |  | 27/03/2024 (Corp): O campo Internal transfer rate from off balance amounts não está incluído no âmbito de contratos do Santander Portugal. Assim, o campo deverá ser aprovisionado com o valor correspondente a não aplicável (11111111111).
| GD | Rentabilidade | INTRNL_TRNSFR_RT_OFF_BLNC | Concluído | 3. Testes comparativos (Espec. VS Impl.) | Não | Baixa | 2 |  | 27/03/2024 (Corp): O campo Internal transfer rate from off balance amounts não está incluído no âmbito de contratos do Santander Portugal. Assim, o campo deverá ser aprovisionado com o valor correspondente a não aplicável (11111111111).
| GD | Rentabilidade | INTRNL_TRNSFR_RT_OFF_BLNC | Concluído | 6. Validação de formatos | Não | Baixa | 1 |  | 27/03/2024 (Corp): O campo Internal transfer rate from off balance amounts não está incluído no âmbito de contratos do Santander Portugal. Assim, o campo deverá ser aprovisionado com o valor correspondente a não aplicável (11111111111).
| GD | Rentabilidade | INTRNL_TRNSFR_RT_OFF_BLNC | Concluído | 7. Validação de controlos corporativos | Não | Baixa | 2 |  | 27/03/2024 (Corp): O campo Internal transfer rate from off balance amounts não está incluído no âmbito de contratos do Santander Portugal. Assim, o campo deverá ser aprovisionado com o valor correspondente a não aplicável (11111111111).
| GD | Rentabilidade | BSNSS_AREA | Em Teste | 2. Simulação | Sim | Alta | 4 |  | Pendente de decisão; Campo já simulado
| GD | Rentabilidade | BSNSS_AREA | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Sim | Alta | 8 |  | Pendente de decisão
| GD | Rentabilidade | BSNSS_AREA | Em Teste | 4. Validação de parametrizações | Sim | Alta | 8 |  | Pendente de decisão
| GD | Rentabilidade | BSNSS_AREA | Em Teste | 6. Validação de formatos | Sim | Alta | 1 |  | Pendente de decisão
| GD | Rentabilidade | BSNSS_AREA | Em Teste | 7. Validação de controlos corporativos | Sim | Alta | 2 |  | Pendente de decisão
| GD | Rentabilidade | AVRG_BLNC | Em Teste | 2. Simulação | Não | Média | 4
| GD | Rentabilidade | AVRG_BLNC | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Média | 4
| GD | Rentabilidade | AVRG_BLNC | Em Teste | 4. Validação de parametrizações | Não | Média | 4 |  | Parametrização Tipo de Conta local: 831, 824
| GD | Rentabilidade | AVRG_BLNC | Em Teste | 6. Validação de formatos | Não | Média | 1
| GD | Rentabilidade | AVRG_BLNC | Em Teste | 7. Validação de controlos corporativos | Não | Média | 2
| GD | Rentabilidade | NT_LN_LSS_PRVSN | Em Teste | 2. Simulação | Não | Média | 4
| GD | Rentabilidade | NT_LN_LSS_PRVSN | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Média | 4
| GD | Rentabilidade | NT_LN_LSS_PRVSN | Em Teste | 4. Validação de parametrizações | Não | Média | 4 |  | Parametrização Tipo de Conta local: 831, 824
** | GD | Rentabilidade | NT_LN_LSS_PRVSN | Em Teste | 6. Validação de formatos | Não | Média | 1
** | GD | Rentabilidade | NT_LN_LSS_PRVSN | Em Teste | 7. Validação de controlos corporativos | Não | Média | 2
** | GD | Rentabilidade | MNGMNT_PRDCT | Em Teste | 2. Simulação | Não | Média | 4
** | GD | Rentabilidade | MNGMNT_PRDCT | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Média | 4
** | GD | Rentabilidade | MNGMNT_PRDCT | Em Teste | 4. Validação de parametrizações | Não | Média | 4
** | GD | Rentabilidade | MNGMNT_PRDCT | Em Teste | 6. Validação de formatos | Não | Média | 1
| GD | Rentabilidade | MNGMNT_PRDCT | Em Teste | 7. Validação de controlos corporativos | Não | Média | 2
| GD | Rentabilidade | NW_BSNSS | Em Teste | 2. Simulação | Não | Média | 4
| GD | Rentabilidade | NW_BSNSS | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Média | 4
** | GD | Rentabilidade | NW_BSNSS | Em Teste | 6. Validação de formatos | Não | Média | 1
** | GD | Rentabilidade | NW_BSNSS | Em Teste | 7. Validação de controlos corporativos | Não | Média | 2
** | GD | Rentabilidade | GRSS_INTRST_INCM_CCRR | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Baixa | 0.1 |  | Testar valor MISS / N.A
| GD | Rentabilidade | NT_LN_LSS_PRVSN_OFF_BLNC | Em Teste | 2. Simulação | Não | Média | 4
** | GD | Rentabilidade | NT_LN_LSS_PRVSN_OFF_BLNC | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Média | 4
| GD | Rentabilidade | NT_LN_LSS_PRVSN_OFF_BLNC | Em Teste | 4. Validação de parametrizações | Não | Média | 4
| GD | Rentabilidade | NT_LN_LSS_PRVSN_OFF_BLNC | Em Teste | 6. Validação de formatos | Não | Média | 1
| GD | Rentabilidade | NT_LN_LSS_PRVSN_OFF_BLNC | Em Teste | 7. Validação de controlos corporativos | Não | Média | 2
| GD | Rentabilidade | AVRG_BLNC_OFF_BLNC | Em Teste | 2. Simulação | Não | Média | 4
| GD | Rentabilidade | AVRG_BLNC_OFF_BLNC | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Média | 4
| GD | Rentabilidade | AVRG_BLNC_OFF_BLNC | Em Teste | 4. Validação de parametrizações | Não | Média | 4
| GD | Rentabilidade | AVRG_BLNC_OFF_BLNC | Em Teste | 6. Validação de formatos | Não | Média | 1
| GD | Rentabilidade | AVRG_BLNC_OFF_BLNC | Em Teste | 7. Validação de controlos corporativos | Não | Média | 2
| GD | Rentabilidade | BSNSS_AREA_CCRR | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Baixa | 0.1 |  | Testar valor MISS / N.A
** | GD | Rentabilidade | GRSS_CMMSSN_INCM_OFF_BLNC | Em Teste | 2. Simulação | Não | Alta | 8
** | GD | Rentabilidade | GRSS_CMMSSN_INCM_OFF_BLNC | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Alta | 8
| GD | Rentabilidade | GRSS_CMMSSN_INCM_OFF_BLNC | Em Teste | 4. Validação de parametrizações | Não | Alta | 8
| GD | Rentabilidade | GRSS_CMMSSN_INCM_OFF_BLNC | Em Teste | 6. Validação de formatos | Não | Alta | 1
| GD | Rentabilidade | GRSS_CMMSSN_INCM_OFF_BLNC | Em Teste | 7. Validação de controlos corporativos | Não | Alta | 2
| GD | Rentabilidade | GRSS_CMMSSN_EXPNS_OFF_BLNC_CCRR | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Baixa | 0.1 |  | Testar valor MISS / N.A
** | GD | Rentabilidade | GRSS_CMMSSN_EXPNS_OFF_BLNC | Em Teste | 2. Simulação | Não | Alta | 8
** | GD | Rentabilidade | GRSS_CMMSSN_EXPNS_OFF_BLNC | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Alta | 8
** | GD | Rentabilidade | GRSS_CMMSSN_EXPNS_OFF_BLNC | Em Teste | 4. Validação de parametrizações | Não | Alta | 8
** | GD | Rentabilidade | GRSS_CMMSSN_EXPNS_OFF_BLNC | Em Teste | 6. Validação de formatos | Não | Alta | 1
| GD | Rentabilidade | GRSS_CMMSSN_EXPNS_OFF_BLNC | Em Teste | 7. Validação de controlos corporativos | Não | Alta | 2
| GD | Rentabilidade | GRSS_CMMSSN_INCM_OFF_BLNC_CCRR | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Baixa | 0.1 |  | Testar valor MISS / N.A
** | GD | Rentabilidade | GRSS_INTRST_INCM | Em Teste | 2. Simulação | Não | Alta | 8
** | GD | Rentabilidade | GRSS_INTRST_INCM | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Alta | 8
| GD | Rentabilidade | GRSS_INTRST_INCM | Em Teste | 4. Validação de parametrizações | Não | Alta | 8
| GD | Rentabilidade | GRSS_INTRST_INCM | Em Teste | 6. Validação de formatos | Não | Alta | 1
| GD | Rentabilidade | GRSS_INTRST_INCM | Em Teste | 7. Validação de controlos corporativos | Não | Alta | 2
| GD | Rentabilidade | GRSS_CMMSSN_INCM | Em Teste | 2. Simulação | Não | Alta | 8
** | GD | Rentabilidade | GRSS_CMMSSN_INCM | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Alta | 8
| GD | Rentabilidade | GRSS_CMMSSN_INCM | Em Teste | 4. Validação de parametrizações | Não | Alta | 8
| GD | Rentabilidade | GRSS_CMMSSN_INCM | Em Teste | 6. Validação de formatos | Não | Alta | 1
| GD | Rentabilidade | GRSS_CMMSSN_INCM | Em Teste | 7. Validação de controlos corporativos | Não | Alta | 2
| GD | Rentabilidade | GRSS_CMMSSN_INCM_CCRR | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Baixa | 0.1 |  | Testar valor MISS / N.A
| GD | Rentabilidade | INTRNL_TRNSFR_RT | Em Teste | 2. Simulação | Não | Alta | 8
| GD | Rentabilidade | INTRNL_TRNSFR_RT | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Alta | 8
| GD | Rentabilidade | INTRNL_TRNSFR_RT | Em Teste | 4. Validação de parametrizações | Não | Alta | 8
| GD | Rentabilidade | INTRNL_TRNSFR_RT | Em Teste | 6. Validação de formatos | Não | Alta | 1
| GD | Rentabilidade | INTRNL_TRNSFR_RT | Em Teste | 7. Validação de controlos corporativos | Não | Alta | 2
| GD | Rentabilidade | GRSS_CMMSSN_EXPNS | Em Teste | 2. Simulação | Não | Alta | 8
| GD | Rentabilidade | GRSS_CMMSSN_EXPNS | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Alta | 8
| GD | Rentabilidade | GRSS_CMMSSN_EXPNS | Em Teste | 4. Validação de parametrizações | Não | Alta | 8
| GD | Rentabilidade | GRSS_CMMSSN_EXPNS | Em Teste | 6. Validação de formatos | Não | Alta | 1
| GD | Rentabilidade | GRSS_CMMSSN_EXPNS | Em Teste | 7. Validação de controlos corporativos | Não | Alta | 2
| GD | Rentabilidade | GRSS_CMMSSN_EXPNS_CCRR | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Baixa | 0.1 |  | Testar valor MISS / N.A
| GD | Rentabilidade | GRSS_INTRST_EXPNS | Em Teste | 2. Simulação | Não | Alta | 8
| GD | Rentabilidade | GRSS_INTRST_EXPNS | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Alta | 8
| GD | Rentabilidade | GRSS_INTRST_EXPNS | Em Teste | 4. Validação de parametrizações | Não | Alta | 8
| GD | Rentabilidade | GRSS_INTRST_EXPNS | Em Teste | 6. Validação de formatos | Não | Alta | 1
| GD | Rentabilidade | GRSS_INTRST_EXPNS | Em Teste | 7. Validação de controlos corporativos | Não | Alta | 2
| GD | Rentabilidade | GRSS_INTRST_EXPNS_CCRR | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Baixa | 0.1 |  | Testar valor MISS / N.A
| GD | Rentabilidade | GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | Em Teste | 2. Simulação | Não | Alta | 8
| GD | Rentabilidade | GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Alta | 8
| GD | Rentabilidade | GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | Em Teste | 4. Validação de parametrizações | Não | Alta | 8
| GD | Rentabilidade | GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | Em Teste | 6. Validação de formatos | Não | Alta | 1
| GD | Rentabilidade | GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | Em Teste | 7. Validação de controlos corporativos | Não | Alta | 2
| GD | Rentabilidade | GNS_FNNCL_TRNSCTN_EXCHNG_CCRR | Em Teste | 3. Testes comparativos (Espec. VS Impl.) | Não | Baixa | 0.1 |  | Testar valor MISS / N.A
| GD | Rentabilidade | CNCLLD_INSTRMNT_STTS | Em Correção | 2. Simulação | Sim | Alta | 8 |  | Pendente de decisão
| GD | Rentabilidade | CNCLLD_INSTRMNT_STTS | Em Correção | 3. Testes comparativos (Espec. VS Impl.) | Sim | Alta | 8 |  | Pendente de decisão
| GD | Rentabilidade | CNCLLD_INSTRMNT_STTS | Em Correção | 6. Validação de formatos | Sim | Alta | 1 |  | Pendente de decisão
| GD | Rentabilidade | CNCLLD_INSTRMNT_STTS | Em Correção | 7. Validação de controlos corporativos | Sim | Alta | 2 |  | Pendente de decisão
| GD | Modelo Verde | SSTNBL_INDCTR | Em Correção | 2. Simulação | Não | Média | 4
| GD | Modelo Verde | SSTNBL_INDCTR | Em Correção | 3. Testes comparativos (Espec. VS Impl.) | Não | Média | 4
| GD | Modelo Verde | SSTNBL_INDCTR | Em Correção | 4. Validação de parametrizações | Não | Média | 4
| GD | Modelo Verde | SSTNBL_INDCTR | Em Correção | 6. Validação de formatos | Não | Média | 1
| GD | Modelo Verde | SSTNBL_INDCTR | Em Correção | 7. Validação de controlos corporativos | Não | Média | 2
466.8
58.35
* Campo com Origem na Rentabilidade mas definido pela corporação
** Campo desconsiderado com a nova EF - instrmnt_id com sufixo do BSNSS_AREA e reporte de saldo com essa granularidade

## 2. Controlos Corporativos
Campo | LT_VALIDATION_LABEL | LT_VALIDATION_DESCRIPTION | LT_VALIDAT_TABLE | LT_VALIDAT_FIELD | LT_VALIDATION_TYPE | LT_PROC_STEP_ID | LT_PROC_VAL_NEW_STATUS | LT_VAL_EXECUTED | LT_VAL_INCIDENTS | VL_PERCENT
COD_SOC | LT_C_EN_001_01 | "Entity code of the informing society." should be a Char not null (default values not allowed) | INTRA_N1_EN | COD_SOC | NOT_NULL_CHAR | LT_C_EN | OK | 1096295 | 0 | 0
DT_RFRNC | LT_C_EN_009_01 | "Reference date." should be a Date not null (default values not allowed) | INTRA_N1_EN | DT_RFRNC | NOT_NULL_DATE | LT_C_EN | OK | 1096295 | 0 | 0
COD_SOC | LT_C_IE_001_01 | "Entity code of the informing society." should be a Char not null (default values not allowed) | INTRA_N1_IE | COD_SOC | NOT_NULL_CHAR | LT_C_IE | OK | 2490665 | 0 | 0
DT_RFRNC | LT_C_IE_002_01 | "Reference date" should be a Date not null (default values not allowed) | INTRA_N1_IE | DT_RFRNC | NOT_NULL_DATE | LT_C_IE | OK | 2490665 | 0 | 0
INSTRMNT_ID | LT_C_IE_004_01 | "Instrument ID" should be a Char not null (default values not allowed) | INTRA_N1_IE | INSTRMNT_ID | NOT_NULL_CHAR | LT_C_IE | OK | 2490665 | 0 | 0
COD_SOC | LT_C_IN_001_01 | "Entity code of the informing society." should be a Char not null (default values not allowed) | INTRA_N1_IN | COD_SOC | NOT_NULL_CHAR | LT_C_IN | OK | 2002411 | 0 | 0
DT_RFRNC | LT_C_IN_007_01 | "Reference date" should be a Date not null (default values not allowed) | INTRA_N1_IN | DT_RFRNC | NOT_NULL_DATE | LT_C_IN | OK | 2002411 | 0 | 0
INSTRMNT_ID | LT_C_IN_008_01 | "Instrument ID" should be a Char not null (default values not allowed) | INTRA_N1_IN | INSTRMNT_ID | NOT_NULL_CHAR | LT_C_IN | OK | 2002411 | 0 | 0
DFLT_STTS_INSTRMNT | LT_C_IN_020_01 | "Default status of the instrument" should be a num not null (default values for not applicable fields not allowed) | INSTRUMENT | DFLT_STTS_INSTRMNT | NOT_NULL_NUM_NA | LT_C_IN | KO | 2002411 | 96182 | 4.8033
PRFRMNG_STTS | LT_C_IN_044_01 | "Performing status" should be a num not null (default values for not applicable fields not allowed) | INSTRUMENT | PRFRMNG_STTS | NOT_NULL_NUM_NA | LT_C_IN | OK | 2002411 | 0 | 0
LCL_INSTMRNT_ID | LT_C_IN_193_01 | "Local Instrument ID" should be a Char not null (default values not allowed) | INTRA_N1_IN | LCL_INSTMRNT_ID | NOT_NULL_CHAR | LT_C_IN | KO | 2002411 | 2002411 | 100
SSTNBL_INDCTR | LT_C_IN_194_01 | "Sustainable Indicator" should be a Char not null (default values for not applicable fields not allowed) | INSTRUMENT | SSTNBL_INDCTR | NOT_NULL_NA | LT_C_IN | KO | 2002318 | 2002318 | 100
SSTNBL_CTGRY | LT_C_IN_195_01 | "Sustainable Category" should be a Char not null (default values for not applicable fields not allowed) | INSTRUMENT | SSTNBL_CTGRY | NOT_NULL_NA | LT_C_IN | KO | 2002318 | 2002318 | 100
NW_BSNSS | LT_C_IN_197_01 | "New Business" should be a Char not null (default values for not applicable fields not allowed) | INSTRUMENT | NW_BSNSS | NOT_NULL_NA | LT_C_IN | KO | 2002411 | 2002411 | 100
BSNSS_AREA | LT_C_IN_202_01 | "Business Area" should be a Char not null (default values for not applicable fields not allowed) | INSTRUMENT | BSNSS_AREA | NOT_NULL_NA | LT_C_IN | KO | 2002411 | 2002411 | 100
FLG_INTRBSNSS | LT_C_IN_206_01 | "Flag of interbusiness" should be a Char not null (default values for not applicable fields not allowed) | INSTRUMENT | FLG_INTRBSNSS | NOT_NULL_NA | LT_C_IN | KO | 2002411 | 2002411 | 100
BSNSS_AREA_CCRR | LT_C_IN_222_01 | "Business Area related to CIB" should be a Char not null (default values for not applicable fields not allowed) | INSTRUMENT | BSNSS_AREA_CCRR | NOT_NULL_NA | LT_C_IN | KO | 2002411 | 2002411 | 100
CNCLLD_INSTRMNT_STTS | LT_C_IN_245_01 | "Flag of instrument cancelled" should be a Char not null (default values for not applicable fields not allowed) | INSTRUMENT | FLG_INSTRMNT_CNCLLD | NOT_NULL_NA | LT_C_IN | KO | 2002411 | 2002411 | 100
IDCMB | LT_C_IN_246_01 | "IDCOMB" should be a Char not null (default values not allowed) | INTRA_N1_IN | IDCMB | NOT_NULL_CHAR | LT_C_IN | KO | 2002411 | 1 | 0
COD_SOC | LT_C_IP_001_01 | "Entity code of the informing society." should be a Char not null (default values not allowed) | INTRA_N1_IP | COD_SOC | NOT_NULL_CHAR | LT_C_IP | OK | 731165 | 0 | 0
DT_RFRNC | LT_C_IP_002_01 | "Reference date" should be a Date not null (default values not allowed) | INTRA_N1_IP | DT_RFRNC | NOT_NULL_DATE | LT_C_IP | OK | 731165 | 0 | 0
INSTRMNT_ID | LT_C_IP_003_01 | "Instrument ID" should be a Char not null (default values not allowed) | INTRA_N1_IP | INSTRMNT_ID | NOT_NULL_CHAR | LT_C_IP | OK | 731165 | 0 | 0
COD_SOC | LT_C_PR_001_01 | "Entity code of the informing society." should be a Char not null (default values not allowed) | INTRA_N1_PR | COD_SOC | NOT_NULL_CHAR | LT_C_PR | OK | 456960 | 0 | 0
DT_RFRNC | LT_C_PR_003_01 | "Reference date" should be a Date not null (default values not allowed) | INTRA_N1_PR | DT_RFRNC | NOT_NULL_DATE | LT_C_PR | OK | 456960 | 0 | 0
INSTRMNT_ID | LT_D_IN_008_01 | Duplicates by "Instrument ID" in INSTRUMENT table | INSTRUMENT | INSTRMNT_ID | DUPLICATES PK | LT_D_ | OK | 2003033 | 0 | 0
INSTRMNT_ID | LT_D_IP_003_01 | Duplicates by "Instrument ID" and "Protection ID" in INSTR_PROTECTION table | INSTR_PROTECTION | INSTRMNT_ID | DUPLICATES PK | LT_D_ | OK | 731165 | 0 | 0
COD_SOC | LT_F_EN_001_01 | "Entity code of the informing society." should match the information on the Codelist | ENTITY | COD_SOC | LISTA | LT_F_EN | OK | 1096295 | 0 | 0
DT_RFRNC | LT_F_EN_009_01 | "Reference date." must have a Date format (yyyy-mm-dd) | ENTITY | DT_RFRNC | FORMAT_DATE | LT_F_EN | OK | 1096295 | 0 | 0
COD_SOC | LT_F_IE_001_01 | "Entity code of the informing society." should match the information on the Codelist | INSTR_ENTITY | COD_SOC | LISTA | LT_F_IE | OK | 2490665 | 0 | 0
DT_RFRNC | LT_F_IE_002_01 | "Reference date" must have a Date format (yyyy-mm-dd) | INSTR_ENTITY | DT_RFRNC | FORMAT_DATE | LT_F_IE | OK | 2490665 | 0 | 0
INSTRMNT_ID | LT_F_IE_004_01 | "Instrument ID" should have Char format (variable length allowed between 1 and 60 characters) | INSTR_ENTITY | INSTRMNT_ID | FORMAT_CHAR | LT_F_IE | OK | 2490665 | 0 | 0
COD_SOC | LT_F_IN_001_01 | "Entity code of the informing society." should match the information on the Codelist | INSTRUMENT | COD_SOC | LISTA | LT_F_IN | OK | 2003033 | 0 | 0
SUBPORTFOLIO_ID | LT_F_IN_002_01 | "Subportfolio ID" should match the information on the Codelist | INSTRUMENT | SUBPORTFOLIO_ID | LISTA | LT_F_IN | OK | 2003033 | 0 | 0
DT_RFRNC | LT_F_IN_007_01 | "Reference date" must have a Date format (yyyy-mm-dd) | INSTRUMENT | DT_RFRNC | FORMAT_DATE | LT_F_IN | OK | 2003033 | 0 | 0
INSTRMNT_ID | LT_F_IN_008_01 | "Instrument ID" should have Char format (variable length allowed between 1 and 60 characters) | INSTRUMENT | INSTRMNT_ID | FORMAT_CHAR | LT_F_IN | OK | 2003033 | 0 | 0
DFLT_STTS_INSTRMNT | LT_F_IN_020_01 | "Default status of the instrument" should match the information on the Codelist | INSTRUMENT | DFLT_STTS_INSTRMNT | LISTA | LT_F_IN | OK | 2003033 | 0 | 0
IMPRMNT_STTS | LT_F_IN_034_01 | "Impairment status" should match the information on the Codelist | INSTRUMENT | IMPRMNT_STTS | LISTA | LT_F_IN | OK | 2003033 | 0 | 0
PRFRMNG_STTS | LT_F_IN_044_01 | "Performing status" should match the information on the Codelist | INSTRUMENT | PRFRMNG_STTS | LISTA | LT_F_IN | OK | 2003033 | 0 | 0
TYP_INSTRMNT | LT_F_IN_055_01 | "Type of instrument" should match the information on the Codelist | INSTRUMENT | TYP_INSTRMNT | LISTA | LT_F_IN | OK | 2003033 | 0 | 0
GRSS_CRRYNG_AMNT_INSTRMNT | LT_F_IN_060_01 | "Gross carrying amount" should have a Format numeric (2 decimal places) | INSTRUMENT | GRSS_CRRYNG_AMNT_INSTRMNT | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
ACCMLTD_CHNGS_FV_CR_INSTRMNT | LT_F_IN_061_01 | "Accumulated changes in fair value due to credit risk" should have a Format numeric (2 decimal places) | INSTRUMENT | ACCMLTD_CHNGS_FV_CR_INSTRMNT | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
ACCNTNG_CLSSFCTN | LT_F_IN_062_01 | "Accounting portfolio" should match the information on the Codelist | INSTRUMENT | ACCNTNG_CLSSFCTN | LISTA | LT_F_IN | OK | 2003033 | 0 | 0
OFF_BLNC_SHT_AMNT_INSTRMNT | LT_F_IN_078_01 | "Off-balance sheet amount" should have a Format numeric (2 decimal places) | INSTRUMENT | OFF_BLNC_SHT_AMNT_INSTRMNT | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
PRVSNS_OFF_BLNC_SHT | LT_F_IN_082_01 | "Provisions associated with off-balance sheet exposures " should have a Format numeric (2 decimal places) | INSTRUMENT | PRVSNS_OFF_BLNC_SHT | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
RWA | LT_F_IN_085_01 | "RWA" should have a Format numeric (2 decimal places) | INSTRUMENT | RWA | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
ACCMLTD_IMPRMNT_INSTRMNT | LT_F_IN_088_01 | "Sum of LLPs and other allowances" should have a Format numeric (2 decimal places) | INSTRUMENT | ACCMLTD_IMPRMNT_INSTRMNT | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
COD_SOC_INTRGRP | LT_F_IN_192_01 | "Cargabal society code of the intragroup exposure" should match the information on the Codelist | INSTRUMENT | COD_SOC_INTRGRP | LISTA | LT_F_IN | KO | 2003033 | 744 | 0.0371
LCL_INSTMRNT_ID | LT_F_IN_193_01 | "Local Instrument ID" should have Char format (variable length allowed between 1 and 60 characters) | INSTRUMENT | LCL_INSTMRNT_ID | FORMAT_CHAR | LT_F_IN | OK | 2003033 | 0 | 0
SSTNBL_INDCTR | LT_F_IN_194_01 | "Sustainable Indicator" should match the information on the Codelist | INSTRUMENT | SSTNBL_INDCTR | LISTA | LT_F_IN | KO | 2003033 | 2003033 | 100
SSTNBL_CTGRY | LT_F_IN_195_01 | "Sustainable Category" should match the information on the Codelist | INSTRUMENT | SSTNBL_CTGRY | LISTA | LT_F_IN | KO | 2003033 | 2003033 | 100
AVRG_BLNC | LT_F_IN_196_01 | "Average balance" should have a Format numeric (2 decimal places) | INSTRUMENT | AVRG_BLNC | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
NW_BSNSS | LT_F_IN_197_01 | "New Business" should match the information on the Codelist | INSTRUMENT | NW_BSNSS | LISTA | LT_F_IN | KO | 2003033 | 2003033 | 100
GRSS_INTRST_INCM | LT_F_IN_198_01 | "Gross Interest income before distribution to SCIB under the Collabotarion Revenues distribution agreement" should have a Format numeric (2 decimal places) | INSTRUMENT | GRSS_INTRST_INCM | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
GRSS_CMMSSN_INCM | LT_F_IN_199_01 | "Gross fee and commission income before distribution to SCIB under the Collabotarion Revenues distribution agreement" should have a Format numeric (2 decimal places) | INSTRUMENT | GRSS_FEE_CMMSSN_INCM | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
INTRNL_TRNSFR_RT | LT_F_IN_200_01 | "Internal transfer rate amount" should have a Format numeric (2 decimal places) | INSTRUMENT | INTRNL_TRNSFR_RT | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
NT_LN_LSS_PRVSN | LT_F_IN_201_01 | "Net loan-loss provisions" should have a Format numeric (2 decimal places) | INSTRUMENT | NT_LN_LSS_PRVSN | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
BSNSS_AREA | LT_F_IN_202_01 | "Business Area" should match the information on the Codelist | INSTRUMENT | BSNSS_AREA | LISTA | LT_F_IN | KO | 2003033 | 2003033 | 100
MNGMNT_PRDCT | LT_F_IN_203_01 | "Management Product" should match the information on the Codelist | INSTRUMENT | MNGMNT_PRDCT | LISTA | LT_F_IN | KO | 2003033 | 2003033 | 100
GRSS_CMMSSN_EXPNS | LT_F_IN_204_01 | "Gross fee and commission expense before distribution to SCIB under the Collabotarion Revenues distribution agreement" should have a Format numeric (2 decimal places) | INSTRUMENT | GRSS_FEE_CMMSSN_EXPNS | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | LT_F_IN_205_01 | "Gains (Losses) On Financial Transaction (gft) And Exchange Differences, before distribution to SCIB under the Collabotarion Revenues distribution agreement" should have a Format numeric (2 decimal places) | INSTRUMENT | GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
FLG_INTRBSNSS | LT_F_IN_206_01 | "Flag of interbusiness" should match the information on the Codelist | INSTRUMENT | FLG_INTRBSNSS | LISTA | LT_F_IN | KO | 2003033 | 2003033 | 100
INTRBSNSS_ADJ_COD | LT_F_IN_207_01 | "Interbusiness adjustment code" should match the information on the Codelist | INSTRUMENT | INTRBSNSS_ADJ_COD | LISTA | LT_F_IN | KO | 2003033 | 2003033 | 100
COD_SOC_DSTNTN | LT_F_IN_208_01 | "Cargabal identification code of the destination entity" should match the information on the Codelist | INSTRUMENT | COD_SOC_DSTNTN | LISTA | LT_F_IN | KO | 2003033 | 2003033 | 100
BSNSS_AREA_DSTNTN | LT_F_IN_209_01 | "Destination Business area" should match the information on the Codelist | INSTRUMENT | BSNSS_AREA_DSTNTN | LISTA | LT_F_IN | KO | 2003033 | 2003033 | 100
AVRG_BLNC_OFF_BLNC | LT_F_IN_210_01 | "Average balance corresponding to undrawn balances committed" should have a Format numeric (2 decimal places) | INSTRUMENT | AVRG_BLNC_OFF_BLNC | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
INTRNL_TRNSFR_RT_OFF_BLNC | LT_F_IN_211_01 | "Internal transfer rate amount" corresponding to undrawn balances committed should have a Format numeric (2 decimal places) | INSTRUMENT | INTRNL_TRNSFR_RT_OFF_BLNC | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
GRSS_CMMSSN_INCM_OFF_BLNC | LT_F_IN_212_01 | "Gross fee and commission income corresponding to undrawn balances committed" should have a Format numeric (2 decimal places) | INSTRUMENT | GRSS_FEE_CMMSSN_INCM_OFF_BLNC | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
GRSS_CMMSSN_EXPNS_OFF_BLNC | LT_F_IN_213_01 | "Gross fee and commission expense corresponding to undrawn balances committed" should have a Format numeric (2 decimal places) | INSTRUMENT | GRSS_FEE_CMMSSN_EXPNS_OFF_BLNC | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
RWA_OFF_BLNC | LT_F_IN_214_01 | "RWA Off Balance" should have a Format numeric (2 decimal places) | INSTRUMENT | RWA_OFF_BLNC | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
GRSS_INTRST_EXPNS | LT_F_IN_215_01 | "Gross Interest expense before distribution to SCIB under the Collabotarion Revenues distribution agreement" should have a Format numeric (2 decimal places) | INSTRUMENT | GRSS_INTRST_EXPNS | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
NT_LN_LSS_PRVSN_OFF_BLNC | LT_F_IN_216_01 | "Net loan-loss provisions corresponding to undrawn balances committed" should have a Format numeric (2 decimal places) | INSTRUMENT | NT_LN_LSS_PRVSN_OFF_BLNC | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
GRSS_INTRST_INCM_CCRR | LT_F_IN_217_01 | "Gross Interest income distributed to SCIB under the Collabotarion Revenues distribution agreement" should have a Format numeric (2 decimal places) | INSTRUMENT | GRSS_INTRST_INCM_CCRR | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
GRSS_INTRST_EXPNS_CCRR | LT_F_IN_218_01 | "Gross Interest expense distributed to SCIB under the Collabotarion Revenues distribution agreement" should have a Format numeric (2 decimal places) | INSTRUMENT | GRSS_INTRST_EXPNS_CCRR | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
GRSS_CMMSSN_INCM_CCRR | LT_F_IN_219_01 | "Gross fee and commission income distributed to SCIB under the Collabotarion Revenues distribution agreement" should have a Format numeric (2 decimal places) | INSTRUMENT | GRSS_FEE_CMMSSN_INCM_CCRR | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
GRSS_CMMSSN_EXPNS_CCRR | LT_F_IN_220_01 | "Gross fee and commission expense distributed to SCIB under the Collabotarion Revenues distribution agreement" should have a Format numeric (2 decimal places) | INSTRUMENT | GRSS_FEE_CMMSSN_EXPNS_CCRR | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
GNS_FNNCL_TRNSCTN_EXCHNG_CCRR | LT_F_IN_221_01 | "Gains (Losses) On Financial Transaction (gft) And Exchange Differences distributed to SCIB under the Collabotarion Revenues distribution agreement" should have a Format numeric (2 decimal places) | INSTRUMENT | GNS_FNNCL_TRNSCTN_EXCHNG_CCRR | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
BSNSS_AREA_CCRR | LT_F_IN_222_01 | "Business Area related to CIB" should match the information on the Codelist | INSTRUMENT | BSNSS_AREA_CCRR | LISTA | LT_F_IN | KO | 2003033 | 2003033 | 100
GRSS_CMMSSN_INCM_OFF_BLNC_CCRR | LT_F_IN_223_01 | "Gross fee and commission income corresponding to undrawn balances committed distributed to SCIB under the Collabotarion Revenues distribution agreement" should have a Format numeric (2 decimal places) | INSTRUMENT | GRSS_FEE_CMMSSN_INCM_OFF_BLNC_CCRR | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
GRSS_CMMSSN_EXPNS_OFF_BLNC_CCRR | LT_F_IN_224_01 | "Gross fee and commission expense corresponding to undrawn balances committed distributed to SCIB under the Collabotarion Revenues distribution agreement" should have a Format numeric (2 decimal places) | INSTRUMENT | GRSS_FEE_CMMSSN_EXPNS_OFF_BLNC_CCRR | FORMAT_NUM | LT_F_IN | OK | 2003033 | 0 | 0
CNCLLD_INSTRMNT_STTS | LT_F_IN_245_01 | "Flag of instrument cancelled" should match the information on the Codelist | INSTRUMENT | FLG_INSTRMNT_CNCLLD | LISTA | LT_F_IN | KO | 2003033 | 2003033 | 100
IDCMB | LT_F_IN_246_01 | "IDCOMB" should match the information on the Codelist | INSTRUMENT | IDCMB | LISTA | LT_F_IN | KO | 2003033 | 2003033 | 100
COD_SOC | LT_F_IP_001_01 | "Entity code of the informing society." should match the information on the Codelist | INSTR_PROTECTION | COD_SOC | LISTA | LT_F_IP | OK | 731165 | 0 | 0
DT_RFRNC | LT_F_IP_002_01 | "Reference date" must have a Date format (yyyy-mm-dd) | INSTR_PROTECTION | DT_RFRNC | FORMAT_DATE | LT_F_IP | OK | 731165 | 0 | 0
INSTRMNT_ID | LT_F_IP_003_01 | "Instrument ID" should have Char format (variable length allowed between 1 and 60 characters) | INSTR_PROTECTION | INSTRMNT_ID | FORMAT_CHAR | LT_F_IP | OK | 731165 | 0 | 0
COD_SOC | LT_F_PR_001_01 | "Entity code of the informing society." should match the information on the Codelist | PROTECTION | COD_SOC | LISTA | LT_F_PR | OK | 456960 | 0 | 0
DT_RFRNC | LT_F_PR_003_01 | "Reference date" must have a Date format (yyyy-mm-dd) | PROTECTION | DT_RFRNC | FORMAT_DATE | LT_F_PR | OK | 456960 | 0 | 0
INSTRMNT_ID | LT_I_IE_004_01 | Any "Instrument ID" in INSTR_ENTITY table must be linked to at least one record in INSTRUMENT table by "Instrument ID" | INSTR_ENTITY | INSTRMNT_ID | INTEGRITY PK CONSTRAINT | LT_I_ | OK | 2490665 | 0 | 0
TYP_INSTRMNT | LT_I_IN_008_01 | For instruments with "Type of instrument" other than 'Missing' and other that '1005 - Debt securities', any "Instrument ID" in INSTRUMENT table must be linked to at least one record in INSTR_ENTITY table by "Instrument ID" | INSTRUMENT | TYP_INSTRMNT | INTEGRITY PK CONSTRAINT | LT_I_ | OK | 2001306 | 0 | 0
INSTRMNT_ID | LT_I_IP_003_01 | Any "Instrument ID" in INSTR_PROTECTION table must be linked to at least one record in INSTRUMENT table by "Instrument ID" | INSTR_PROTECTION | INSTRMNT_ID | INTEGRITY PK CONSTRAINT | LT_I_ | OK | 731165 | 0 | 0
DT_RFRNC | LT_K_EN_009_01 | "Reference date." must not be later than the current date | INTRA_N1_EN | DT_RFRNC | RELACION_FECHA | LT_K_EN | OK | 1096295 | 0 | 0
DT_RFRNC | LT_K_IE_002_01 | "Reference date" must not be later than the current date | INTRA_N1_IE | DT_RFRNC | RELACION_FECHA | LT_K_IE | OK | 2490665 | 0 | 0
DT_RFRNC | LT_K_IN_007_01 | "Reference date" must not be later than the current date | INTRA_N1_IN | DT_RFRNC | RELACION_FECHA | LT_K_IN | OK | 2002411 | 0 | 0
IMPRMNT_STTS | LT_K_IN_034_01 | "Impairment status" can only be '23 - Stage 1 (IFRS)' or '24 - Stage 2 (IFRS)' or '25 - Stage 3 (IFRS)' or default values(Since Santander Group is IFRS compliance and do not apply General Accounting Accepted Principles (GAAP) on a consolidated basis) | INTRA_N1_IN | IMPRMNT_STTS | LISTA | LT_K_IN | OK | 2002411 | 0 | 0
RWA_OFF_BLNC | LT_K_IN_214_01 | "RWA Off Balance" can only be default values (since values will be populated using bank-internal masterscale) | INTRA_N1_IN | RWA_OFF_BLNC | LISTA | LT_K_IN | OK | 2002411 | 0 | 0
DT_RFRNC | LT_K_IP_002_01 | "Reference date" must not be later than the current date | INTRA_N1_IP | DT_RFRNC | RELACION_FECHA | LT_K_IP | OK | 731165 | 0 | 0
DT_RFRNC | LT_K_PR_003_01 | "Reference date" must not be later than the current date | INTRA_N1_PR | DT_RFRNC | RELACION_FECHA | LT_K_PR | OK | 456960 | 0 | 0
DT_RFRNC | LT_O_EN_009_01 | "Reference date" must be later than 01 December 2020 | ENTITY | DT_RFRNC | RELACION_FECHA | LT_O_EN | OK | 1096295 | 0 | 0
DT_RFRNC | LT_O_IE_002_01 | "Reference date" must be later than 01 December 2020 | INSTR_ENTITY | DT_RFRNC | RELACION_FECHA | LT_O_IE | OK | 2490665 | 0 | 0
DT_RFRNC | LT_O_IN_007_01 | "Reference date" must be later than 01 December 2020 | INSTRUMENT | DT_RFRNC | RELACION_FECHA | LT_O_IN | OK | 2002411 | 0 | 0
GRSS_CRRYNG_AMNT_INSTRMNT | LT_O_IN_060_01 | "Gross carrying amount" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | GRSS_CRRYNG_AMNT_INSTRMNT | RELACION_NUM_DF | LT_O_IN | KO | 2002411 | 31379 | 1.5671
ACCMLTD_CHNGS_FV_CR_INSTRMNT | LT_O_IN_061_01 | "Accumulated changes in fair value due to credit risk" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | ACCMLTD_CHNGS_FV_CR_INSTRMNT | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
OFF_BLNC_SHT_AMNT_INSTRMNT | LT_O_IN_078_01 | "Off-balance sheet amount" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | OFF_BLNC_SHT_AMNT_INSTRMNT | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
PRVSNS_OFF_BLNC_SHT | LT_O_IN_082_01 | "Provisions associated with off-balance sheet exposures " shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | PRVSNS_OFF_BLNC_SHT | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
RWA | LT_O_IN_085_01 | "RWA" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | RWA | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
ACCMLTD_IMPRMNT_INSTRMNT | LT_O_IN_088_01 | "Sum of LLPs and other allowances" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | ACCMLTD_IMPRMNT_INSTRMNT | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
AVRG_BLNC | LT_O_IN_196_01 | "Average balance" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | AVRG_BLNC | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
GRSS_INTRST_INCM | LT_O_IN_198_01 | "Gross Interest income before distribution to SCIB under the Collabotarion Revenues distribution agreement" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | GRSS_INTRST_INCM | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
GRSS_CMMSSN_INCM | LT_O_IN_199_01 | "Gross fee and commission income before distribution to SCIB under the Collabotarion Revenues distribution agreement" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | GRSS_FEE_CMMSSN_INCM | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
INTRNL_TRNSFR_RT | LT_O_IN_200_01 | "Internal transfer rate amount" shall be smaller or equal to 0; Positive values trigger attention | INSTRUMENT | INTRNL_TRNSFR_RT | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
NT_LN_LSS_PRVSN | LT_O_IN_201_01 | "Net loan-loss provisions" shall be larger than or equal to 0; Negative values trigger attention | INSTRUMENT | NT_LN_LSS_PRVSN | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
GRSS_CMMSSN_EXPNS | LT_O_IN_204_01 | "Gross fee and commission expense before distribution to SCIB under the Collabotarion Revenues distribution agreement" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | GRSS_FEE_CMMSSN_EXPNS | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | LT_O_IN_205_01 | "Gains (Losses) On Financial Transaction (gft) And Exchange Differences, before distribution to SCIB under the Collabotarion Revenues distribution agreement" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
AVRG_BLNC_OFF_BLNC | LT_O_IN_210_01 | "Average balance corresponding to undrawn balances committed" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | AVRG_BLNC_OFF_BLNC | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
INTRNL_TRNSFR_RT_OFF_BLNC | LT_O_IN_211_01 | "Internal transfer rate amount corresponding to undrawn balances committed" shall be smaller or equal to 0; Positive values trigger attention | INSTRUMENT | INTRNL_TRNSFR_RT_OFF_BLNC | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
GRSS_CMMSSN_INCM_OFF_BLNC | LT_O_IN_212_01 | "Gross fee and commission income corresponding to undrawn balances committed" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | GRSS_FEE_CMMSSN_INCM_OFF_BLNC | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
GRSS_CMMSSN_EXPNS_OFF_BLNC | LT_O_IN_213_01 | "Gross fee and commission expense corresponding to undrawn balances committed" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | GRSS_FEE_CMMSSN_EXPNS_OFF_BLNC | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
GRSS_INTRST_EXPNS | LT_O_IN_215_01 | "Gross Interest expense before distribution to SCIB under the Collabotarion Revenues distribution agreement" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | GRSS_INTRST_EXPNS | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
GRSS_INTRST_INCM_CCRR | LT_O_IN_217_01 | "Gross Interest income distributed to SCIB under the Collabotarion Revenues distribution agreement" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | GRSS_INTRST_INCM_CCRR | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
GRSS_INTRST_EXPNS_CCRR | LT_O_IN_218_01 | "Gross Interest expense distributed to SCIB under the Collabotarion Revenues distribution agreement" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | GRSS_INTRST_EXPNS_CCRR | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
GRSS_CMMSSN_INCM_CCRR | LT_O_IN_219_01 | "Gross fee and commission income distributed to SCIB under the Collabotarion Revenues distribution agreement" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | GRSS_FEE_CMMSSN_INCM_CCRR | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
GRSS_CMMSSN_EXPNS_CCRR | LT_O_IN_220_01 | "Gross fee and commission expense distributed to SCIB under the Collabotarion Revenues distribution agreement" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | GRSS_FEE_CMMSSN_EXPNS_CCRR | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
GNS_FNNCL_TRNSCTN_EXCHNG_CCRR | LT_O_IN_221_01 | "Gains (Losses) On Financial Transaction (gft) And Exchange Differences distributed to SCIB under the Collabotarion Revenues distribution agreement" shall be larger or equal to 0; Negative values trigger attention | INSTRUMENT | GNS_FNNCL_TRNSCTN_EXCHNG_CCRR | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
GRSS_CMMSSN_INCM_OFF_BLNC_CCRR | LT_O_IN_223_01 | "Gross fee and commission income corresponding to undrawn balances committed distributed to SCIB under the Collabotarion Revenues distribution agreement" shall be larger than or equal to 0; Negative values trigger attention | INSTRUMENT | GRSS_FEE_CMMSSN_INCM_OFF_BLNC_CCRR | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
GRSS_CMMSSN_EXPNS_OFF_BLNC_CCRR | LT_O_IN_224_01 | "Gross fee and commission expense corresponding to undrawn balances committed distributed to SCIB under the Collabotarion Revenues distribution agreement" shall be larger than or equal to 0; Negative values trigger attention | INSTRUMENT | GRSS_FEE_CMMSSN_EXPNS_OFF_BLNC_CCRR | RELACION_NUM_DF | LT_O_IN | OK | 2002411 | 0 | 0
DT_RFRNC | LT_O_IP_002_01 | "Reference date" must be later than 01 December 2020 | INSTR_PROTECTION | DT_RFRNC | RELACION_FECHA | LT_O_IP | OK | 731165 | 0 | 0
DT_RFRNC | LT_O_PR_003_01 | "Reference date" must be later than 01 December 2020 | PROTECTION | DT_RFRNC | RELACION_FECHA | LT_O_PR | OK | 456960 | 0 | 0
SUBPORTFOLIO_ID | LT_R_IN_002_01 | If "Leverage finance flag" is set to 'Y' then "Subportfolio ID" must be classified as 'SNF - Non-financial corporations' | INTRA_REL_P_IN | SUBPORTFOLIO_ID | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
DFLT_STTS_INSTRMNT | LT_R_IN_020_01 | If "ISDA credit event declared" is equal to 'Y', then "Default status of the instrument" must be set as '18 - Default because both unlikely to pay and more than 90/180 days past due', '19 - Default because unlikely to pay' or '20 - Default because more than 90/180 days past due' | INTER_REL_P_X2 | DFLT_STTS_INSTRMNT | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
DFLT_STTS_INSTRMNT | LT_R_IN_020_03 | If "Protection called" is set as 'Y' then "Default status of the instrument" has to be set as '18 - Default because both unlikely to pay and more than 90/180 days past due', '19 - Default because unlikely to pay' or '20 - Default because more than 90/180 days past due' | INTER_REL_P_X3 | DFLT_STTS_INSTRMNT | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
DFLT_STTS_INSTRMNT | LT_R_IN_020_04 | If "Leverage finance flag" is set to 'Y' and "Covenant status" is equal to '4 - In breach with at least one material financial covenant' then "Default status of the instrument" must be '18 - Default because both unlikely to pay and more than 90/180 days past due', '19 - Default because unlikely to pay' or '20 - Default because more than 90/180 days past due' | INTRA_REL_P_IN | DFLT_STTS_INSTRMNT | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
IMPRMNT_STTS | LT_R_IN_034_01 | if "Days past due at reference date" is between 30 and 90 days and "Subportfolio ID" is not classified as 'VRPL - FV with changes in PL' then "Impairment status" must be '24 - Stage 2 (IFRS)' or '25 - Stage 3 (IFRS)' | INTRA_REL_P_IN | IMPRMNT_STTS | REL_CAMPOS | LT_R_IN | KO | 9703 | 1 | 0.0103
IMPRMNT_STTS | LT_R_IN_034_02 | if "Default status of the instrument" is set as '18 - Default because both unlikely to pay and more than 90/180 days past due', '19 - Default because unlikely to pay' or '20 - Default because more than 90/180 days past due' and "Subportfolio ID" is not classified as 'VRPL - FV with changes in PL' then "Impairment status" is set as "25 - Stage 3 (IFRS)" | INTRA_REL_P_IN | IMPRMNT_STTS | REL_CAMPOS | LT_R_IN | KO | 92666 | 3283 | 3.5428
IMPRMNT_STTS | LT_R_IN_034_03 | if "Default status of the instrument" is set as '14 - Not in default' and "Subportfolio ID" is not classified as 'VRPL - FV with changes in PL' then "Impairment status" cannot be 25 - Stage 3 (IFRS)' | INTRA_REL_P_IN | IMPRMNT_STTS | REL_CAMPOS | LT_R_IN | KO | 1813562 | 4684 | 0.2583
IMPRMNT_STTS | LT_R_IN_034_05 | if "Performing status" is '11 - Performing' and "Subportfolio ID" is not classified as 'VRPL - FV with changes in PL' then "Impairment status" cannot be '25 - Stage 3 (IFRS)' | INTRA_REL_P_IN | IMPRMNT_STTS | REL_CAMPOS | LT_R_IN | OK | 1905178 | 0 | 0
IMPRMNT_STTS | LT_R_IN_034_09 | If "Debtor on watch-list (Y/N)" is set as 'Y' and "Subportfolio ID" is not classified as 'VRPL - FV with changes in PL' then "Impairment status" has to be set as '24 - Stage 2 (IFRS)' or '25 - Stage 3 (IFRS)' | INTER_REL_P_X2 | IMPRMNT_STTS | REL_CAMPOS | LT_R_IN | KO | 18441 | 2850 | 15.4547
IMPRMNT_STTS | LT_R_IN_034_11 | If "Accounting portfolio"equals '6 - IFRS: Financial assets at amortised cost', '8 - IFRS: Financial assets at fair value through other comprehensive income' or '14 - IFRS: Cash balances at central banks and other demand deposits', then "Impairment status" cannot be 'Not applicable' | INTER_REL_P_X1 | IMPRMNT_STTS | REL_CAMPOS | LT_R_IN | OK | 1724899 | 0 | 0
IMPRMNT_STTS | LT_R_IN_034_12 | If "Subportfolio ID" is classified as 'S1 - Stage 1', then "Impairment status" must equal '23 - Stage 1 (IFRS)' | INTER_REL_P_X1 | IMPRMNT_STTS | REL_CAMPOS | LT_R_IN | OK | 1472964 | 0 | 0
IMPRMNT_STTS | LT_R_IN_034_13 | If "Subportfolio ID" is classified as 'S2 - Stage 2', then "Impairment status" must equal '24 - Stage 2 (IFRS)' | INTER_REL_P_X1 | IMPRMNT_STTS | REL_CAMPOS | LT_R_IN | OK | 432214 | 0 | 0
IMPRMNT_STTS | LT_R_IN_034_14 | If "Subportfolio ID" is classified as 'S3 - Stage 3', then "Impairment status" must equal '25 - Stage 3 (IFRS)' | INTER_REL_P_X1 | IMPRMNT_STTS | REL_CAMPOS | LT_R_IN | OK | 97233 | 0 | 0
PRFRMNG_STTS | LT_R_IN_044_01 | If "Default status of the instrument" is '18 - Default because both unlikely to pay and more than 90/180 days past due' or '19 - Default because unlikely to pay' or '20 - Default because more than 90/180 days past due', then "Performing status" must equal to '1 - Non Performing' | INTRA_REL_P_IN | PRFRMNG_STTS | REL_CAMPOS | LT_R_IN | KO | 92666 | 3283 | 3.5428
PRFRMNG_STTS | LT_R_IN_044_02 | If "Previous performing status" is populated other than default values then "Performing status" must be populated other than default values | INTRA_REL_P_IN | PRFRMNG_STTS | REL_CAMPOS | LT_R_IN | OK | 114216 | 0 | 0
PRFRMNG_STTS | LT_R_IN_044_03 | If "Default status of the instrument" is set as '14 - Not in default' and "Impairment status" is set as '23 - Stage 1 (IFRS)' then "Performing status" must be '11 - Performing' | INTRA_REL_P_IN | PRFRMNG_STTS | REL_CAMPOS | LT_R_IN | OK | 1408741 | 0 | 0
PRFRMNG_STTS | LT_R_IN_044_07 | If "Protection called" is set as 'Y' then "Performing status" (instrument level) has to be set as '1 - Non-performing' | INTER_REL_P_X3 | PRFRMNG_STTS | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
PRFRMNG_STTS | LT_R_IN_044_08 | If "Subportfolio ID" is classified as 'P - Performing', then "Performing status" (instrument level) has to be set as '11 - Performing' | INTER_REL_P_X1 | PRFRMNG_STTS | REL_CAMPOS | LT_R_IN | OK | 1905178 | 0 | 0
PRFRMNG_STTS | LT_R_IN_044_09 | If "Subportfolio ID" is classified as 'NP - Non-Performing', then "Performing status" (instrument level) has to be set as '1 - Non-Performing' | INTER_REL_P_X1 | PRFRMNG_STTS | REL_CAMPOS | LT_R_IN | OK | 97233 | 0 | 0
PRFRMNG_STTS | LT_R_IN_044_10 | If "Most recent appraised market value at the time when the instrument was classified as non-performing" is set as 'Not applicable' and the protection is other than "personal guarantee", then the "Performing status" must be '11 - Performing'. (We consider "personal guarantee" when "Protection ID" matches the "Protection Provider ID" (Guarantor) or "Tax ID" (Protection level) is populated other than default value and the "Protection type" equals '7 - Other protection') | INTER_REL_P_X3 | PRFRMNG_STTS | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
PRFRMNG_STTS | LT_R_IN_044_11 | If "Impairment status" is '25 - Stage 3 (IFRS)', then "Performing status" must equal to '1 - Non Performing' | INTRA_REL_P_IN | PRFRMNG_STTS | REL_CAMPOS | LT_R_IN | OK | 97233 | 0 | 0
PRFRMNG_STTS | LT_R_IN_044_12 | If "Performing status" at entity level is set as '1 - Non Performing' then "Performing status" at instrument level should be '1 - Non Performing' | INTER_REL_P_X2 | PRFRMNG_STTS | REL_CAMPOS | LT_R_IN | KO | 113163 | 15043 | 13.2932
GRSS_CRRYNG_AMNT_INSTRMNT | LT_R_IN_060_01 | If "Accounting portfolio" is '6 - IFRS: Financial assets at amortised cost' or '14 - IFRS: Cash balances at central banks and other demand deposits' or '8 - IFRS: Financial assets at fair value through other comprehensive income', then "Gross carrying amount" should be equal to "Carrying amount" plus "Sum of LLPs and other allowances" | INTRA_REL_P_IN | GRSS_CRRYNG_AMNT_INSTRMNT | REL_CAMPOS | LT_R_IN | OK | 1724899 | 0 | 0
GRSS_CRRYNG_AMNT_INSTRMNT | LT_R_IN_060_02 | If "Accounting portfolio" is '4 - IFRS: Financial assets designated at fair value through profit or loss' or '41 - IFRS: Non-trading financial assets mandatorily at fair value through profit or loss', then "Gross carrying amount" should be equal to "Carrying amount" plus "Accumulated changes in fair value due to credit risk" | INTRA_REL_P_IN | GRSS_CRRYNG_AMNT_INSTRMNT | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
GRSS_CRRYNG_AMNT_INSTRMNT | LT_R_IN_060_03 | If "Subportfolio ID" is classified as 'COM - Loan Commitments' or 'GUAR - Guarantees' or 'OCOM - Other commitments', then "Gross carrying amount" must be 0 or default value | INTRA_REL_P_IN | GRSS_CRRYNG_AMNT_INSTRMNT | REL_CAMPOS | LT_R_IN | OK | 277512 | 0 | 0
ACCMLTD_CHNGS_FV_CR_INSTRMNT | LT_R_IN_061_01 | If "Accounting portfolio" is '6 - IFRS: Financial assets at amortised cost' or '14 - IFRS: Cash balances at central banks and other demand deposits' or '8 - IFRS: Financial assets at fair value through other comprehensive income', then "Accumulated changes in fair value due to credit risk" should be a default value | INTRA_REL_P_IN | ACCMLTD_CHNGS_FV_CR_INSTRMNT | REL_CAMPOS | LT_R_IN | OK | 305642 | 0 | 0
ACCMLTD_CHNGS_FV_CR_INSTRMNT | LT_R_IN_061_02 | If "Subportfolio ID" is classified as 'VRPL - Fair value through profit and loss' and 'P - Performing', then "Accumulated changes in fair value due to credit risk" should be 'Not Applicable' or zero | INTRA_REL_P_IN | ACCMLTD_CHNGS_FV_CR_INSTRMNT | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
ACCNTNG_CLSSFCTN | LT_R_IN_062_01 | If "Subportfolio ID" is classified as 'CA - Amortized Cost', then "Accounting portfolio" must equal '6 - IFRS: Financial assets at amortised cost' | INTRA_REL_P_IN | ACCNTNG_CLSSFCTN | REL_CAMPOS | LT_R_IN | OK | 1724797 | 0 | 0
ACCNTNG_CLSSFCTN | LT_R_IN_062_02 | If "Subportfolio ID" is classified as 'CASH - Cash and cash balances', then "Accounting portfolio" must equal '14 - IFRS: Cash balances at central banks and other demand deposits' | INTRA_REL_P_IN | ACCNTNG_CLSSFCTN | REL_CAMPOS | LT_R_IN | OK | 93 | 0 | 0
ACCNTNG_CLSSFCTN | LT_R_IN_062_03 | If "Subportfolio ID" is classified as 'VRPL - Fair value through profit and loss', then "Accounting portfolio" must equal '4 - IFRS: Financial assets designated at fair value through profit or loss' or '41 - IFRS: Non-trading financial assets mandatorily at fair value through profit or loss' | INTRA_REL_P_IN | ACCNTNG_CLSSFCTN | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
ACCNTNG_CLSSFCTN | LT_R_IN_062_04 | If "Subportfolio ID" is classified as 'VRPN - Fair value through other comprehensive income', then "Accounting portfolio" must equal '8 - IFRS: Financial assets at fair value through other comprehensive income' | INTRA_REL_P_IN | ACCNTNG_CLSSFCTN | REL_CAMPOS | LT_R_IN | OK | 9 | 0 | 0
OFF_BLNC_SHT_AMNT_INSTRMNT | LT_R_IN_078_01 | "Off-balance sheet amount" must be greater or equal from "Provisions associated with off-balance sheet exposures ". | INTRA_REL_P_IN | OFF_BLNC_SHT_AMNT_INSTRMNT | REL_CAMPOS | LT_R_IN | KO | 2002318 | 317 | 0.0158
OFF_BLNC_SHT_AMNT_INSTRMNT | LT_R_IN_078_02 | If "IFRS 9 accounting CCF" is populated other than default values and other than 100%, then "Off-balance sheet amount" cannot be 'Not applicable' | INTRA_REL_P_IN | OFF_BLNC_SHT_AMNT_INSTRMNT | REL_CAMPOS | LT_R_IN | OK | 1646037 | 0 | 0
OFF_BLNC_SHT_AMNT_INSTRMNT | LT_R_IN_078_03 | If "IFRS 9 accounting CCF" is populated with 'Not applicable', then "Off-balance sheet amount" should be 'Not applicable' nor zero | INTRA_REL_P_IN | OFF_BLNC_SHT_AMNT_INSTRMNT | REL_CAMPOS | LT_R_IN | OK | 253 | 0 | 0
OFF_BLNC_SHT_AMNT_INSTRMNT | LT_R_IN_078_04 | If "Subportfolio ID" is classified as 'VRPL - Fair value through profit and loss', then "Off-balance sheet amount" should be 'Not Applicable' or zero | INTRA_REL_P_IN | OFF_BLNC_SHT_AMNT_INSTRMNT | REL_CAMPOS | LT_R_IN | OK | 3 | 0 | 0
PRVSNS_OFF_BLNC_SHT | LT_R_IN_082_01 | If "Off-balance sheet amount" is populated as 'Not applicable', then "Provisions associated with off-balance sheet exposures " must be a default value | INTRA_REL_P_IN | PRVSNS_OFF_BLNC_SHT | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
PRVSNS_OFF_BLNC_SHT | LT_R_IN_082_02 | If "Subportfolio ID" is classified as 'VRPL - Fair value through profit and loss', then "Provisions associated with off-balance sheet exposures" should be 'Not Applicable' or zero | INTRA_REL_P_IN | PRVSNS_OFF_BLNC_SHT | REL_CAMPOS | LT_R_IN | OK | 3 | 0 | 0
ACCMLTD_IMPRMNT_INSTRMNT | LT_R_IN_088_01 | If "Accounting portfolio"equals '2 - IFRS: Financial assets held for trading', '4 - IFRS: Financial assets designated at fair value through profit or loss' or '41 - IFRS: Non-trading financial assets mandatorily at fair value through profit or loss', then "Sum of LLPs and other allowances" must equal default values | INTRA_REL_P_IN | ACCMLTD_IMPRMNT_INSTRMNT | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
ACCMLTD_IMPRMNT_INSTRMNT | LT_R_IN_088_02 | If "Subportfolio ID" is classified as 'COM - Loan Commitments' or 'GUAR - Guarantees' or 'OCOM - Other commitments', then "Sum of LLPs and other allowances" must be 0 or default value | INTRA_REL_P_IN | ACCMLTD_IMPRMNT_INSTRMNT | REL_CAMPOS | LT_R_IN | OK | 277512 | 0 | 0
ACCMLTD_IMPRMNT_INSTRMNT | LT_R_IN_088_03 | If "Subportfolio ID" is classified as 'VRPL - Fair value through profit and loss', then "Sum of LLPs and other allowances" should be 'Not Applicable' or zero | INTRA_REL_P_IN | ACCMLTD_IMPRMNT_INSTRMNT | REL_CAMPOS | LT_R_IN | OK | 3 | 0 | 0
SSTNBL_INDCTR | LT_R_IN_194_01 | If "Sustainable Category" is set as 'SCA0103% - Other Dedicated Purposes' or ' SC0204 - General Purpose – Default' then "Sustainable Indicator" cannot be set as '1 - Aligned Under SFCS' | INTRA_REL_P_IN | SSTNBL_INDCTR | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
SSTNBL_INDCTR | LT_R_IN_194_02 | If "Sustainable Category" is set as 'SCA02% - GENERAL PURPOSE' and Subporfolio_ID as 'HOG - Households' then "Sustainable Indicator" cannot be set as '1 - Aligned under SFCS' nor '2 - Aligned under other criteria' | INTRA_REL_P_IN | SSTNBL_INDCTR | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
SSTNBL_CTGRY | LT_R_IN_195_01 | If "Taxonomy-eligible CAPEX (CCM) Ratio" is populated with 'Not Applicable' values then "Sustainable category" must be 'SCA02% - GENERAL PURPOSE' | INTER_REL_P_X2 | SSTNBL_CTGRY | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
SSTNBL_CTGRY | LT_R_IN_195_02 | If "Taxonomy-eligible Turnover (CCM) Ratio" is populated with 'Not Applicable' values then "Sustainable category" must be 'SCA02% - GENERAL PURPOSE' | INTER_REL_P_X2 | SSTNBL_CTGRY | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
SSTNBL_CTGRY | LT_R_IN_195_03 | If "Taxonomy-eligible CAPEX (CCA) Ratio" is populated with 'Not Applicable' values then "Sustainable category" must be 'SCA02% - GENERAL PURPOSE' | INTER_REL_P_X2 | SSTNBL_CTGRY | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
SSTNBL_CTGRY | LT_R_IN_195_04 | If "Taxonomy-eligible Turnover (CCA) Ratio" is populated with 'Not Applicable' values then "Sustainable category" must be 'SCA02% - GENERAL PURPOSE' | INTER_REL_P_X2 | SSTNBL_CTGRY | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
SSTNBL_CTGRY | LT_R_IN_195_05 | If "Taxonomy-aligned CAPEX (CCM) - Enabling Ratio" is populated with 'Not Applicable' values then "Sustainable category" must be 'SCA02% - GENERAL PURPOSE' | INTER_REL_P_X2 | SSTNBL_CTGRY | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
SSTNBL_CTGRY | LT_R_IN_195_06 | If "Taxonomy-aligned CAPEX (CCA) - Enabling Ratio" is populated with 'Not Applicable' values then "Sustainable category" must be 'SCA02% - GENERAL PURPOSE' | INTER_REL_P_X2 | SSTNBL_CTGRY | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
SSTNBL_CTGRY | LT_R_IN_195_07 | If "Taxonomy-aligned CAPEX (CCM) - Transitional Ratio" is populated with 'Not Applicable' values then "Sustainable category" must be 'SCA02% - GENERAL PURPOSE' | INTER_REL_P_X2 | SSTNBL_CTGRY | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
SSTNBL_CTGRY | LT_R_IN_195_08 | If "Environmentally sustainable CAPEX (CCM) Ratio" is populated with 'Not Applicable' values then "Sustainable category" must be 'SCA02% - GENERAL PURPOSE' | INTER_REL_P_X2 | SSTNBL_CTGRY | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
SSTNBL_CTGRY | LT_R_IN_195_09 | If "Environmentally sustainable CAPEX (CCA) Ratio" is populated with 'Not Applicable' values then "Sustainable category" must be 'SCA02% - GENERAL PURPOSE' | INTER_REL_P_X2 | SSTNBL_CTGRY | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
SSTNBL_CTGRY | LT_R_IN_195_10 | If "Taxonomy-aligned Turnover (CCM) - Enabling Ratio" is populated with 'Not Applicable' values then "Sustainable category" must be 'SCA02% - GENERAL PURPOSE' | INTER_REL_P_X2 | SSTNBL_CTGRY | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
SSTNBL_CTGRY | LT_R_IN_195_11 | If "Taxonomy-aligned Turnover (CCA) - Enabling Ratio" is populated with 'Not Applicable' values then "Sustainable category" must be 'SCA02% - GENERAL PURPOSE' | INTER_REL_P_X2 | SSTNBL_CTGRY | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
SSTNBL_CTGRY | LT_R_IN_195_12 | If "Taxonomy-aligned Turnover (CCM) - Transitional Ratio" is populated with 'Not Applicable' values then "Sustainable category" must be 'SCA02% - GENERAL PURPOSE' | INTER_REL_P_X2 | SSTNBL_CTGRY | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
SSTNBL_CTGRY | LT_R_IN_195_13 | If "Environmentally sustainable Turnover (CCM) Ratio" is populated with 'Not Applicable' values then "Sustainable category" must be 'SCA02% - GENERAL PURPOSE' | INTER_REL_P_X2 | SSTNBL_CTGRY | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
SSTNBL_CTGRY | LT_R_IN_195_14 | If "Environmentally sustainable Turnover (CCA) Ratio" is populated with 'Not Applicable' values then "Sustainable category" must be 'SCA02% - GENERAL PURPOSE' | INTER_REL_P_X2 | SSTNBL_CTGRY | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
GRSS_INTRST_INCM | LT_R_IN_198_01 | If "Gross Interest income distributed to SCIB under the Collabotarion Revenues distribution agreement" is populated with other than default values then "Gross Interest income before distribution to SCIB under the Collabotarion Revenues distribution agreement" cannot be 'Not Applicable | INTRA_REL_P_IN | GRSS_INTRST_INCM | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
GRSS_INTRST_INCM | LT_R_IN_198_02 | If "Gross Interest income distributed to SCIB under the Collabotarion Revenues distribution agreement" and "Gross Interest income before distribution to SCIB under the Collabotarion Revenues distribution agreement" are populated with other than default values then "Gross Interest income distributed to SCIB under the Collabotarion Revenues distribution agreement" must be less or equal to "Gross Interest income before distribution to SCIB under the Collabotarion Revenues distribution agreement" | INTRA_REL_P_IN | GRSS_INTRST_INCM | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
GRSS_CMMSSN_INCM | LT_R_IN_199_01 | If "Gross Interest fee and comission income distributed to SCIB under the Collabotarion Revenues distribution agreement" is populated with other than default values then "Gross Interest fee and comission income before distribution to SCIB under the Collabotarion Revenues distribution agreement" cannot be 'Not Applicable | INTRA_REL_P_IN | GRSS_FEE_CMMSSN_INCM | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
GRSS_CMMSSN_INCM | LT_R_IN_199_02 | If "Gross Interest fee and comission income distributed to SCIB under the Collabotarion Revenues distribution agreement" and "Gross Interest fee and comission income before distribution to SCIB under the Collabotarion Revenues distribution agreement" are populated with other than default values then "Gross Interest fee and comission income distributed to SCIB under the Collabotarion Revenues distribution agreement" must be less or equal to "Gross Interest fee and comission income before distribution to SCIB under the Collabotarion Revenues distribution agreement" | INTRA_REL_P_IN | GRSS_FEE_CMMSSN_INCM | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
MNGMNT_PRDCT | LT_R_IN_203_01 | If "Off-balance sheet amount" is populated with other than default values or zero amount and "Gross Carrying Amount Instrument" is populated as 'Not applicable' or zero amount and "Type of Instrument" is populated as '2001 - Guarantees' then "Management Product" should be 'PRDCT0201 - Contingent Risk' | INTRA_REL_P_IN | MNGMNT_PRDCT | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
MNGMNT_PRDCT | LT_R_IN_203_02 | If "Off-balance sheet amount" is populated with other than default values or zero amount and "Gross Carrying Amount Instrument" is populated as 'Not applicable' or zero amount and "Type of Instrument" is populated with other values than '2001 - Guarantees' then "Management Product" should be 'PRDCT0202 - Undrawn balances Committed' | INTRA_REL_P_IN | MNGMNT_PRDCT | REL_CAMPOS | LT_R_IN | OK | 277518 | 0 | 0
MNGMNT_PRDCT | LT_R_IN_203_03 | If "Gross Carrying Amount Instrument" is populated with other than default values or zero amount then"Management Product" should be populated as 'PRDCT010101 - Mortgages', 'PRDCT01010201 - Project & Acquisition Finance', 'PRDCT01010202 - Syndicated Loans', 'PRDCT01010203 - Capital Finance', 'PRDCT01010204 - Asset Based Finance (ABF)', 'PRDCT01010205 - Leveraged Finance', 'PRDCT01010206 - Export & Agency Finance', 'PRDCT01010207 - Trade & Working Capital Solutions' or 'PRDCT010103 - Other Loans & Advances' | INTRA_REL_P_IN | MNGMNT_PRDCT | REL_CAMPOS | LT_R_IN | OK | 1724892 | 0 | 0
GRSS_CMMSSN_EXPNS | LT_R_IN_204_01 | If "Gross Interest fee and comission expenses distributed to SCIB under the Collabotarion Revenues distribution agreement" is populated with other than default values then "Gross Interest fee and comission expenses before distribution to SCIB under the Collabotarion Revenues distribution agreement" cannot be 'Not Applicable | INTRA_REL_P_IN | GRSS_FEE_CMMSSN_EXPNS | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
GRSS_CMMSSN_EXPNS | LT_R_IN_204_02 | If "Gross Interest fee and comission expenses distributed to SCIB under the Collabotarion Revenues distribution agreement" and "Gross Interest fee and comission expenses before distribution to SCIB under the Collabotarion Revenues distribution agreement" are populated with other than default values then "Gross Interest fee and comission expenses distributed to SCIB under the Collabotarion Revenues distribution agreement" must be less or equal to "Gross Interest fee and comission expenses before distribution to SCIB under the Collabotarion Revenues distribution agreement" | INTRA_REL_P_IN | GRSS_FEE_CMMSSN_EXPNS | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | LT_R_IN_205_01 | If "Gains (Losses) On Financial Transaction (gft) And Exchange Differences distributed to SCIB under the Collabotarion Revenues distribution agreement" is populated with other than default values then "Gains (Losses) On Financial Transaction (gft) And Exchange Differences, before distribution to SCIB under the Collabotarion Revenues distribution agreement" cannot be 'Not Applicable | INTRA_REL_P_IN | GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | LT_R_IN_205_02 | If "Gains (Losses) On Financial Transaction (gft) And Exchange Differences distributed to SCIB under the Collabotarion Revenues distribution agreement" and "Gains (Losses) On Financial Transaction (gft) And Exchange Differences, before distribution to SCIB under the Collabotarion Revenues distribution agreement" are populated with other than default values then "Gains (Losses) On Financial Transaction (gft) And Exchange Differences distributed to SCIB under the Collabotarion Revenues distribution agreement" must be less or equal to "Gains (Losses) On Financial Transaction (gft) And Exchange Differences, before distribution to SCIB under the Collabotarion Revenues distribution agreement" | INTRA_REL_P_IN | GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
INTRBSNSS_ADJ_COD | LT_R_IN_207_01 | If "Flag of interbusiness" is set to 'N', then "Interbusiness adjustment code" should be 'Not Applicable' | INTRA_REL_P_IN | INTRBSNSS_ADJ_COD | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
INTRBSNSS_ADJ_COD | LT_R_IN_207_02 | If "Flag of interbusiness" is set to 'Y', then "Interbusiness adjustment code" cannot be 'Not applicable' | INTRA_REL_P_IN | INTRBSNSS_ADJ_COD | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
COD_SOC_DSTNTN | LT_R_IN_208_01 | If "Flag of interbusiness" is set to 'N', then "Destination society" should be 'Not Applicable' | INTRA_REL_P_IN | COD_SOC_DSTNTN | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
COD_SOC_DSTNTN | LT_R_IN_208_02 | If "Flag of interbusiness" is set to 'Y', then "Destination society" cannot be 'Not Applicable' | INTRA_REL_P_IN | COD_SOC_DSTNTN | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
BSNSS_AREA_DSTNTN | LT_R_IN_209_01 | If "Flag of interbusiness" is set to 'N', then "Destination Business area" should be 'Not Applicable' | INTRA_REL_P_IN | BSNSS_AREA_DSTNTN | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
BSNSS_AREA_DSTNTN | LT_R_IN_209_02 | If "Flag of interbusiness" is set to 'Y', then "Destination Business area" cannot be 'Not applicable' | INTRA_REL_P_IN | BSNSS_AREA_DSTNTN | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
BSNSS_AREA_DSTNTN | LT_R_IN_209_03 | If "Flag of interbusiness" is set to 'Y' and "Destination society" not equal "Entity code of the informing society." then "Destination Business area" cannot be equal to "Business area" | INTRA_REL_P_IN | BSNSS_AREA_DSTNTN | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
AVRG_BLNC_OFF_BLNC | LT_R_IN_210_01 | If "Management Product" is populated as 'PRDCT0202 - Undrawn balances Committed' or 'PRDCT0201 - Contingent Risk' then "Average off balance " cannot be 'Not applicable' | INTRA_REL_P_IN | AVRG_BLNC_OFF_BLNC | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
INTRNL_TRNSFR_RT_OFF_BLNC | LT_R_IN_211_01 | If "Management Product" is populated as 'PRDCT0202 - Undrawn balances Committed' or 'PRDCT0201 - Contingent Risk' then "Internal transfer rate due to off balance amounts" cannot be 'Not Applicable' | INTRA_REL_P_IN | INTRNL_TRNSFR_RT_OFF_BLNC | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
GRSS_CMMSSN_INCM_OFF_BLNC | LT_R_IN_212_01 | If "Management Product" is populated as 'PRDCT0202 - Undrawn balances Committed' or 'PRDCT0201 - Contingent Risk' then "Gross fee and commission income corresponding to undrawn balances committed" cannot be 'Not Applicable' | INTRA_REL_P_IN | GRSS_FEE_CMMSSN_INCM_OFF_BLNC | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
GRSS_CMMSSN_INCM_OFF_BLNC | LT_R_IN_212_02 | If "Gross Interest fee and comission income corresponding to undrawn balances distributed to SCIB under the Collabotarion Revenues distribution agreement" is populated with other than default values then "Gross Interest fee and comission income corresponding to undrawn balances before distribution to SCIB under the Collabotarion Revenues distribution agreement" cannot be 'Not Applicable | INTRA_REL_P_IN | GRSS_FEE_CMMSSN_INCM_OFF_BLNC | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
GRSS_CMMSSN_INCM_OFF_BLNC | LT_R_IN_212_03 | If "Gross Interest fee and comission income corresponding to undrawn balances distributed to SCIB under the Collabotarion Revenues distribution agreement" and "Gross Interest fee and comission income corresponding to undrawn balances before distribution to SCIB under the Collabotarion Revenues distribution agreement" are populated with other than default values then "Gross Interest fee and comission income corresponding to undrawn balances distributed to SCIB under the Collabotarion Revenues distribution agreement" must be less or equal to "Gross Interest fee and comission income corresponding to undrawn balances before distribution to SCIB under the Collabotarion Revenues distribution agreement" | INTRA_REL_P_IN | GRSS_FEE_CMMSSN_INCM_OFF_BLNC | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
GRSS_CMMSSN_EXPNS_OFF_BLNC | LT_R_IN_213_01 | If "Management Product" is populated as 'PRDCT0202 - Undrawn balances Committed' or 'PRDCT0201 - Contingent Risk' then "Gross fee and commission expense corresponding to undrawn balances committed" cannot be 'Not Applicable' | INTRA_REL_P_IN | GRSS_FEE_CMMSSN_EXPNS_OFF_BLNC | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
GRSS_CMMSSN_EXPNS_OFF_BLNC | LT_R_IN_213_02 | If "Gross Interest fee and comission expense corresponding to undrawn balances distributed to SCIB under the Collabotarion Revenues distribution agreement" is populated with other than default values then "Gross Interest fee and comission expense corresponding to undrawn balances before distribution to SCIB under the Collabotarion Revenues distribution agreement" cannot be 'Not Applicable | INTRA_REL_P_IN | GRSS_FEE_CMMSSN_EXPNS_OFF_BLNC | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
GRSS_CMMSSN_EXPNS_OFF_BLNC | LT_R_IN_213_03 | If "Gross Interest fee and comission expense corresponding to undrawn balances distributed to SCIB under the Collabotarion Revenues distribution agreement" and "Gross Interest fee and comission expense corresponding to undrawn balances before distribution to SCIB under the Collabotarion Revenues distribution agreement" are populated with other than default values then "Gross Interest fee and comission expense corresponding to undrawn balances distributed to SCIB under the Collabotarion Revenues distribution agreement" must be less or equal to "Gross Interest fee and comission expense corresponding to undrawn balances before distribution to SCIB under the Collabotarion Revenues distribution agreement" | INTRA_REL_P_IN | GRSS_FEE_CMMSSN_EXPNS_OFF_BLNC | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
GRSS_INTRST_EXPNS | LT_R_IN_215_01 | If "Gross Interest expenses distributed to SCIB under the Collabotarion Revenues distribution agreement" is populated with other than default values then "Gross Interest expenses before distribution to SCIB under the Collabotarion Revenues distribution agreement" cannot be 'Not Applicable | INTRA_REL_P_IN | GRSS_INTRST_EXPNS | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
GRSS_INTRST_EXPNS | LT_R_IN_215_02 | If "Gross Interest expenses distributed to SCIB under the Collabotarion Revenues distribution agreement" and "Gross Interest expenses before distribution to SCIB under the Collabotarion Revenues distribution agreement" are populated with other than default values then "Gross Interest expenses distributed to SCIB under the Collabotarion Revenues distribution agreement" must be less or equal to "Gross Interest expenses before distribution to SCIB under the Collabotarion Revenues distribution agreement" | INTRA_REL_P_IN | GRSS_INTRST_EXPNS | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
NT_LN_LSS_PRVSN_OFF_BLNC | LT_R_IN_216_01 | If "Management Product" is populated as 'PRDCT0202 - Undrawn balances Committed' or 'PRDCT0201 - Contingent Risk' then "Net loan-loss provisions corresponding to undrawn balances committed" cannot be 'Not Applicable' | INTRA_REL_P_IN | NT_LN_LSS_PRVSN_OFF_BLNC | REL_CAMPOS | LT_R_IN | OK | 0 | 0 | 0
COD_SOC | LT_S_EN_001_01 | "Entity code of the informing society" can only be informed as one value in ENTITY table | ENTITY | COD_SOC | STRUCTURE | LT_S_EN | OK | 1096295 | 0 | 0
DT_RFRNC | LT_S_EN_009_01 | "Reference date" can only be informed as one value in ENTITY table | ENTITY | DT_RFRNC | STRUCTURE | LT_S_EN | OK | 1096295 | 0 | 0
COD_SOC | LT_S_IE_001_01 | "Entity code of the informing society" can only be informed as one value in INSTR_ENTITY table | INSTR_ENTITY | COD_SOC | STRUCTURE | LT_S_IE | OK | 2490665 | 0 | 0
DT_RFRNC | LT_S_IE_002_01 | "Reference date" can only be informed as one value in INSTR_ENTITY table | INSTR_ENTITY | DT_RFRNC | STRUCTURE | LT_S_IE | OK | 2490665 | 0 | 0
COD_SOC | LT_S_IN_001_01 | "Entity code of the informing society" can only be informed as one value in INSTRUMENT table | INSTRUMENT | COD_SOC | STRUCTURE | LT_S_IN | OK | 2003033 | 0 | 0
DT_RFRNC | LT_S_IN_007_01 | "Reference date" can only be informed as one value in INSTRUMENT table | INSTRUMENT | DT_RFRNC | STRUCTURE | LT_S_IN | OK | 2003033 | 0 | 0
COD_SOC | LT_S_IP_001_01 | "Entity code of the informing society" can only be informed as one value in INSTR_PROTECTION table | INSTR_PROTECTION | COD_SOC | STRUCTURE | LT_S_IP | OK | 731165 | 0 | 0
DT_RFRNC | LT_S_IP_002_01 | "Reference date" can only be informed as one value in INSTR_PROTECTION table | INSTR_PROTECTION | DT_RFRNC | STRUCTURE | LT_S_IP | OK | 731165 | 0 | 0
COD_SOC | LT_S_PR_001_01 | "Entity code of the informing society" can only be informed as one value in PROTECTION table | PROTECTION | COD_SOC | STRUCTURE | LT_S_PR | OK | 456960 | 0 | 0
DT_RFRNC | LT_S_PR_003_01 | "Reference date" can only be informed as one value in PROTECTION table | PROTECTION | DT_RFRNC | STRUCTURE | LT_S_PR | OK | 456960 | 0 | 0

## 3. Plano
| Âmbito | Origem | Campo | Status | Total Horas
| GD | Rentabilidade | AVRG_BLNC | Em Teste | 15
| GD | Modelo Verde | SSTNBL_CTGRY | Concluído | 0
| GD | LT ESTR | DFLT_STTS_INSTRMNT | Concluído | 0
| GD | LT ESTR | ACCMLTD_CHNGS_FV_CR_INSTRMNT | Concluído | 0
| GD | LT ESTR | ACCMLTD_IMPRMNT_INSTRMNT | Concluído | 0
| GD | LT ESTR | ACCNTNG_CLSSFCTN | Concluído | 0
| GD | LT ESTR | COD_SOC | Concluído | 0
| GD | LT ESTR | DT_RFRNC | Concluído | 0
| GD | LT ESTR | GRSS_CRRYNG_AMNT_INSTRMNT | Concluído | 0
| GD | LT ESTR | IDCMB | Concluído | 0
| GD | LT ESTR | IMPRMNT_STTS | Concluído | 0
| GD | Rentabilidade | AVRG_BLNC_OFF_BLNC | Em Teste | 15
| GD | LT ESTR | LCL_INSTMRNT_ID | Concluído | 0
| GD | LT ESTR | OFF_BLNC_SHT_AMNT_INSTRMNT | Concluído | 0
| GD | LT ESTR | PRFRMNG_STTS | Concluído | 0
| GD | LT ESTR | PRVSNS_OFF_BLNC_SHT | Concluído | 0
| GD | LT ESTR | SUBPORTFOLIO_ID | Concluído | 0
| GD | LT ESTR | TYP_INSTRMNT | Concluído | 0
| GD | LT ESTR | RWA | Concluído | 0
| GD | LT ESTR | COD_SOC_INTRGRP | Concluído | 0
| GD | Corporativo | BSNSS_AREA_DSTNTN | Concluído | 0
| GD | Corporativo | FLG_INTRBSNSS | Concluído | 0
| GD | Corporativo | INTRBSNSS_ADJ_COD | Concluído | 0
| GD | Corporativo | COD_SOC_DSTNTN | Concluído | 0
| GD | Corporativo | RWA_OFF_BLNC | Concluído | 0
| GD | Rentabilidade | INTRNL_TRNSFR_RT_OFF_BLNC | Concluído | 0
| GD | Rentabilidade | BSNSS_AREA | Em Teste | 23
| GD | Rentabilidade | BSNSS_AREA_CCRR | Em Teste | 0.1
| GD | Rentabilidade | CNCLLD_INSTRMNT_STTS | Em Correção | 19
| GD | Rentabilidade | GNS_FNNCL_TRNSCTN_EXCHNG_CCRR | Em Teste | 0.1
| GD | Rentabilidade | GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | Em Teste | 27
| GD | Rentabilidade | GRSS_CMMSSN_EXPNS | Em Teste | 27
| GD | Rentabilidade | GRSS_CMMSSN_EXPNS_CCRR | Em Teste | 0.1
| GD | Rentabilidade | GRSS_CMMSSN_EXPNS_OFF_BLNC | Em Teste | 27
| GD | Rentabilidade | GRSS_CMMSSN_EXPNS_OFF_BLNC_CCRR | Em Teste | 0.1
| GD | Rentabilidade | GRSS_CMMSSN_INCM | Em Teste | 27
| GD | Rentabilidade | GRSS_CMMSSN_INCM_CCRR | Em Teste | 0.1
| GD | Rentabilidade | GRSS_CMMSSN_INCM_OFF_BLNC | Em Teste | 27
| GD | Rentabilidade | GRSS_CMMSSN_INCM_OFF_BLNC_CCRR | Em Teste | 0.1
| GD | Rentabilidade | GRSS_INTRST_EXPNS | Em Teste | 27
| GD | Rentabilidade | GRSS_INTRST_EXPNS_CCRR | Em Teste | 0.1
| GD | Rentabilidade | GRSS_INTRST_INCM | Em Teste | 27
| GD | Rentabilidade | GRSS_INTRST_INCM_CCRR | Em Teste | 0.1
| GD | Outro | INSTRMNT_ID | Em Teste | 13
| GD | Rentabilidade | INTRNL_TRNSFR_RT | Em Teste | 27
| GD | Rentabilidade | MNGMNT_PRDCT | Em Teste | 15
| GD | - | n.a. |  | 8
| GD | Rentabilidade | NT_LN_LSS_PRVSN | Em Teste | 15
| GD | Rentabilidade | NT_LN_LSS_PRVSN_OFF_BLNC | Em Teste | 15
| GD | Rentabilidade | NW_BSNSS | Em Teste | 11
| GD | Modelo Verde | SSTNBL_INDCTR | Em Correção | 15
380.8
47.6
**
**
**
**
**
**
**
**
**
**
**
**
**
**
**
**
**
**
**
* Campo com Origem na Rentabilidade mas definido pela corporação
** Campo desconsiderado com a nova EF - instrmnt_id com sufixo do BSNSS_AREA e reporte de saldo com essa granularidade

## Auxiliar
Tipologia de testes |  | Estimação Horas
Complexidade
Categorização de Testes | Descrição | Baixa | Média | Alta
1. Teste de universo | 1. Validação de universo de contratos quando comparado âmbito "CDG" e "PM" 2. Controlos sobre o desdobramento de chaves nas relações FR-MIS | 8 | 8 | 8
2. Simulação | Simulação da especificação funcional. Suplementarmente, realizar reuniões de validações e esclarecimentos funcionais junto do negócio/owner. | 2 | 4 | 8
3. Testes comparativos (Espec. VS Impl.) | A partir da simulação realizada, comparar resultados com a implementação de IT. | 2 | 4 | 8
4. Validação de parametrizações | A partir da simulação realizada, comparar com as parametrizações implementadas por IT. | 2 | 4 | 8
5. Teste comparativos com LT | Garantir que a informação do campo da LT-ESTR âmbito 'PM' está espelhado no âmbito 'CDG'. | 1 | 1 | 1
6. Validação de formatos | Validação de formato de acordo com o que é esperado pela Corporação (incluindo validação de codelists, missing e default values) | 1 | 1 | 1
7. Validação de controlos corporativos | Validar controlos corporativos e se a especificação cumpre os requisitos. | 2 | 2 | 2
Status
Concluído
Por iniciar
Em Teste
Em Correção
Cancelado

## Tipologias de Testes GD (2)
Origem | Campo | Status | Tipologia de testes | ID Categoria | Categorização de Testes | Descrição
Modelo Verde | SSTNBL_CTGRY | Concluído | 1,2,3,4,6,7 | 1 | Testes End-to-End / Amostragem | - Simulação da EF; - Testes de comparação com o desenvolvido por IT: - Validação de escolha de BSNSS_AREA e construção do instrmnt_id - Validação de saldos associados ao campo em análise - Identificação da origem de incidências.
LT ESTR | DFLT_STTS_INSTRMNT | Concluído | 5.7 | 2 | Testes / Validações Funcionais - EF | - Garantir que o que está desenvolvido se encontra de acordo com a EF do campo; - Validações e esclarecimentos funcionais junto do negócio/owner.
LT ESTR | ACCMLTD_CHNGS_FV_CR_INSTRMNT | Concluído | 5.7 | 3 | Testes / Validações às parametrizações | - Garantir que as parametrizações carregadas se encontram OK; - Validações e esclarecimentos funcionais junto do negócio/owner.
LT ESTR | ACCMLTD_IMPRMNT_INSTRMNT | Concluído | 5.7 | 4 | Testes de Informação Corporativa | - Garantir que a informação do campo corporativo está de acordo com a info que a corporação espera receber.
LT ESTR | ACCNTNG_CLSSFCTN | Concluído | 5.7 | 5 | Testes de Informação LT ESTR - Comparação com 'PM' | - Garantir que a informação do campo da LT-ESTR âmbito 'PM' está espelhado no âmbito 'CDG'.
LT ESTR | COD_SOC | Concluído | 5.7 | 6 | Controlos - Garantir Traçabilidade da tradução de chaves | - Controlos sobre o desdobramento de chaves nas relações FR-MIS (N:N) - Controlos sobre o desdobramento de chaves nas relações MASTER-MIS (N:N)
LT ESTR | DT_RFRNC | Concluído | 5.7 | 7 | Re-Testes | - Re-Teste dos campos com incidência aberta
LT ESTR | GRSS_CRRYNG_AMNT_INSTRMNT | Concluído | 5.7
LT ESTR | IDCMB | Concluído | 5.7
LT ESTR | IMPRMNT_STTS | Concluído | 5.7
LT ESTR | INSTRMNT_ID | Concluído | 5.7
LT ESTR | LCL_INSTMRNT_ID | Concluído | 5.7
LT ESTR | OFF_BLNC_SHT_AMNT_INSTRMNT | Concluído | 5.7
LT ESTR | PRFRMNG_STTS | Concluído | 5.7
LT ESTR | PRVSNS_OFF_BLNC_SHT | Concluído | 5.7
LT ESTR | SUBPORTFOLIO_ID | Concluído | 5.7
LT ESTR | TYP_INSTRMNT | Concluído | 5.7
LT ESTR | RWA | Concluído | 5.7
LT ESTR | COD_SOC_INTRGRP | Concluído | 5.7
Corporativo | BSNSS_AREA_DSTNTN | Concluído | 4.7
Corporativo | FLG_INTRBSNSS | Concluído | 4.7
Corporativo | INTRBSNSS_ADJ_COD | Concluído | 4.7
Corporativo | COD_SOC_DSTNTN | Concluído | 4.7
Corporativo | RWA_OFF_BLNC | Concluído | 4.7
Rentabilidade* | INTRNL_TRNSFR_RT_OFF_BLNC | Concluído | 4.7
Rentabilidade | BSNSS_AREA | Em Teste | 1,2,3,4,6,7
Rentabilidade | AVRG_BLNC | Em Teste | 1,2,3,6,7
Rentabilidade | NT_LN_LSS_PRVSN | Em Teste | 1,2,3,6,7
Rentabilidade | MNGMNT_PRDCT | Em Teste | 1,2,3,4,6,7
Rentabilidade | NW_BSNSS | Em Teste | 1,2,3,6,7
Rentabilidade | GRSS_INTRST_INCM_CCRR | Em Teste | 1,2,3,6,7
Rentabilidade | NT_LN_LSS_PRVSN_OFF_BLNC | Em Teste | 1,2,3,6,7
Rentabilidade | AVRG_BLNC_OFF_BLNC | Em Teste | 1,2,3,6,7
Rentabilidade | BSNSS_AREA_CCRR ** | Em Teste | 1,2,3,4,6,7
Rentabilidade | GRSS_CMMSSN_INCM_OFF_BLNC | Em Teste | 1,2,3,6,7
Rentabilidade | GRSS_CMMSSN_EXPNS_OFF_BLNC_CCRR ** | Em Teste | 1,2,3,6,7
Rentabilidade | GRSS_CMMSSN_EXPNS_OFF_BLNC | Em Teste | 1,2,3,6,7
Rentabilidade | GRSS_CMMSSN_INCM_OFF_BLNC_CCRR ** | Em Teste | 1,2,3,6,7
Rentabilidade | GRSS_INTRST_INCM | Em Teste | 1,2,3,6,7
Rentabilidade | GRSS_CMMSSN_INCM | Em Teste | 1,2,3,6,7
Rentabilidade | GRSS_CMMSSN_INCM_CCRR ** | Em Teste | 1,2,3,6,7
Rentabilidade | INTRNL_TRNSFR_RT | Em Teste | 1,2,3,6,7
Rentabilidade | GRSS_CMMSSN_EXPNS | Em Teste | 1,2,3,6,7
Rentabilidade | GRSS_CMMSSN_EXPNS_CCRR ** | Em Teste | 1,2,3,6,7
Rentabilidade | GRSS_INTRST_EXPNS | Em Teste | 1,2,3,6,7
Rentabilidade | GRSS_INTRST_EXPNS_CCRR ** | Em Teste | 1,2,3,6,7
Rentabilidade | GNS_FNNCL_TRNSCTN_EXCHNG_DFFRNCS | Em Teste | 1,2,3,6,7
Rentabilidade | GNS_FNNCL_TRNSCTN_EXCHNG_CCRR ** | Em Teste | 1,2,3,6,7
Calculado | CNCLLD_INSTRMNT_STTS | Em Correção | 1,2,3,4,6,7
Modelo Verde | SSTNBL_INDCTR | Em Correção | 1,2,3,6,7
* Campo com Origem na Rentabilidade mas definido pela corporação
** Campo desconsiderado com a nova EF - instrmnt_id com sufixo do BSNSS_AREA e reporte de saldo com essa granularidade